## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2022-12-07
Total program |  |  | (1)
School | GSF | Contribution | Project Spend | Contribution vs. Projects
Arts & Science | 1075461.7321 | 3663826 | 1311460.625 | 2352365.375
Blair | 121421.4269 | 413652 | 1387917.5 | -974265.5
Divinity | 57814.7309 | 196960 | 1466350 | -1269390
Engineering | 537962.3327 | 1832701 | 330000 | 1502701
Law | 120155.4846 | 409339 | 722694.5 | -313355.5
SOM Basic Sciences | 280022.3999 | 953965 | 932546.875 | 21418.125
Nursing | 106166.7 | 361683 | 62100 | 299583
Owen | 59008.3617 | 201027 | 0 | 201027
Peabody | 390796.8848 | 1331346 | 3023525.5 | -1692179.5
| 2748810.0535 | 9364499 | 9236595 | 127904

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2022-12-07
| Projects |  |  |  | (1) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | Estimated FY23 FRP
1 | Design | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 145000 | 145000
2 | Programming / Planning | 10086 | Blair | Blair School of Music - Replace Boiler | 550000 | 17000
3 | Construction | 10098 | SOM Basic Sciences | MRB III 4th Floor - Replace Controls (Phase 2 of 5) | 1216485.5 | 1216485.5
4 | Construction | 10146 | Nursing | Godchaux Hall - HVAC Engineering | TBD | 62100
5 | Construction | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5
6 | Construction | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 245917.5
7 | Design | 20431 | Divinity | Divinity - AHU 5N (5 & 6) Replacement with Benton | 4375000 | 1093750
8 | Design | 20489 | Divinity | Divinity - AHU 1N (1 & 3) Replacement | 3726000 | 372600
9 | Construction | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5
10 | Programming / Planning | 20506 | Peabody | Wyatt Center - Window Replacement (4th Floor) | 1100000 | 1100000
11 | Bidding | 20562 | Peabody | Wyatt Center - VAV Replacement | 285480 | 214110
12 | Award | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870
13 | Bidding | 20573 | Peabody | Wyatt Center - Roof Replacement | 750000 | 750000
14 | Award | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202
15 | Design | 20577 | Blair | Blair School of Music - Air Handling Unit Replacement | 4500000 | 1125000
16 | Design | 20644 | Peabody | Peabody Administration - Envelope Repairs | 560000 | 560000
17 | Design | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | TBD | TBD
18 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | TBD | 135000
19 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | TBD | 195000
20 | Design | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | TBD | 24950
21 | Design | 20700 | Arts & Science | SC Chemistry (SC7) - Steam Generator 1 Removal and Connection to Central Plant Steam | TBD | 2500
22 | Programming / Planning | 20701 | Arts & Science | SC Science & Engineering (SC5) - Chemical Discharge Replacement | TBD | TBD
23 | Bidding | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 175000 | 175000
[5 empty] | 20613166.5 | 9236595

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | Contribution | Projects | MRB III Adj | Revised Projects | Contribution vs. Projects
Arts & Science | 1075461.7321 | 3.6638 | 0.80932 | 0.50214 | 1.3115 | 2.3524
Blair | 121421.4269 | 0.41365 | 1.3879 |  | 1.3879 | -0.97427
Divinity | 57814.7309 | 0.19696 | 1.4664 |  | 1.4664 | -1.2694
Engineering | 537962.3327 | 1.8327 | 0.33 |  | 0.33 | 1.5027
Law | 120155.4846 | 0.40934 | 0.72269 |  | 0.72269 | -0.31336
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.4347 | -0.50214 | 0.93255 | 0.021418
Nursing | 106166.7 | 0.36168 | 0.0621 |  | 0.0621 | 0.29958
Owen | 59008.3617 | 0.20103 | 0 |  | 0 | 0.20103
Peabody | 390796.8848 | 1.3313 | 3.0235 |  | 3.0235 | -1.6922
| 2748810.0535 | 9.3645 | 9.2366 |  | 9.2366 | 0.1279
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
Estimated Budget
|  | MRB III BIO/SCI | 1434687.5
|  | A&S | 502140.625
|  | SOM | 932546.875
1434687.5

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24
|  | 3.41 |  |  | 3.97
School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29
Contribution |  | 9364499 | Contribution |  | 11029283.29
Anticipated spend |  | 9236595 | Anticipated spend |  | 0
Remaining funds |  | 127904 | Remaining funds |  | 11029283.29

## Project Status
Facility Renewal Program: Projects
| Capex / opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Anticipated FRP funding | Project status update
1 | Operating | 10085 | 4591 | N/A | 21000 - Peabody College: Office of the Dean | Peabody | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Design | Sean Rewers | 145000 | 22000 | 17500 | 17500 | 0 | 145000 | 11/22/2022 Walkthrough with ICT has been completed, feasibility study should come back in early December.
2 | Capital | 10086 | 8557 | CP_400007 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Replace Boiler | Programming / Planning | Hans Mooy | 550000 | 18700 | 17000 | 17000 | 3400 | 17000 | 11/30/2022 Project activated. AEI and Envision reviewing drawings for steam connection and HW/CW as alternate cost.
3 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III 4th Floor - Replace Controls (Phase 2 of 5) | Construction | Hans Mooy | 1216485.5 | 1216485.5 | 1172951 | 1172951 | 257845 | 1216485.5 | 11/22/2022 Construction continues. Project should be complete mid-February 2023.
4 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | Godchaux Hall | Godchaux Hall - HVAC Engineering | Construction | Sean Rewers | TBD | 62100 | 52900 | 62100 | 39675 | 62100 | 11/22/2022 Added scope for design/engineering of HHW for Godchaux/Frist approved. Design/engineering underway with completion of CDs scheduled for 12/15/22.
5 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | Law School | Law School - Fire Alarm System Replacement | Construction | Bob Grummon | 1445389 | 1445389 | 1348533 | 1348533 | 1198950 | 722694.5 | 11/28/2022 Work is completed awaiting fire marshal sign off after exams are completed.
6 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 8725 | 245917.5 | 11/22/2022 PO has been issued. Preliminary design drawings have been submitted for the elevator. Alternates have been approved. Elevator mechanical room to be relocated out to the upper patio. Construction to start summer of 2023.
7 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement with Benton | Design | Hans Mooy | 4375000 | 139640 | 112475 | 122975 | 30138.6 | 1093750 | 11/28/2022 Design meetings continue
8 | Capital | 20489 | 8051 |  | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 1N (1 & 3) Replacement | Design | Hans Mooy | 3726000 | 0 | 0 | 0 | 0 | 372600 | 11/28/2022 Design to continue after 5N goes to bid.
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 407000 | 79415.5 | 11/22/2022 Final construction to be completed over winter break. Hatch installation, window replacement, and final metal work to be completed.
10 | Capital | 20506 | 1170 |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement (4th Floor) | Programming / Planning | Ben Bedock | 1100000 | 0 | 0 | 0 | 0 | 1100000 | 11/22/2022 Working with appropriate parties to determine scope of work. Summer 2023 construction
11 | Capital | 20562 | 4564 |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Bidding | Sean Rewers | 285480 | 0 | 0 | 0 | 0 | 214110 | 11/28/2022 Project walkthrough was completed and bids should be received by the end of the month. Working with JCI for updated controls pricing. Construction still planned for summer 2023.
12 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Award | Ben Bedock | 781870 | 781870 | 17050 | 709050 | 8700 | 781870 | 11/22/2022 Project has been awarded to Oracle/Premier elevator. PO process is currently underway. Just received Provost approval so PO can move forward. Construction to be completed over summer.
13 | Capital | 20573 | 8047 |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Bidding | Ben Bedock | 750000 | 0 | 0 | 0 | 0 | 750000 | 11/22/2022 Addendum to scope is currently being developed. Project is currently out to bid.
14 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Award | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 0 | 218202 | 11/28/2022 Coils are being ordered and require about 6 weeks lead time. Construction should be starting in the first of the year 2023.
15 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 4500000 | 53750 | 50283 | 50283 | 11700 | 1125000 | 11/22/2022 Approval to continue design...meetings continue.
16 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Design | Ben Bedock | 560000 | 2050 | 0 | 2050 | 0 | 560000 | 11/22/2022 PO is currently underway for testing of the windows for hazardous materials. Once results have been submitted, scope can be developed for the windows followed by the bidding process.
17 | Capital | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Design | Ben Bedock | TBD | 0 | 0 | 0 | 0 | TBD | 11/22/2022 Met with appropriate parties to determine scope of work. Scope to be written and project to go out to bid. Work to be completed summer 2023.
18 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | TBD | 135000 | 135000 | 135000 | 0 | 135000 | 11/28/2022 Design PO is through and user meetings are being set up with the occupants. After these meetings well have a better idea where the project is heading and will begin the design.
19 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | TBD | 195000 | 0 | 195000 | 0 | 195000 | 11/28/2022 Design PO has been issued and user meetings are being set-up now. After these user meetings we will have a better idea on the direction we are taking the project.
20 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | TBD | 24950 | 24950 | 24950 | 0 | 24950 | 11/28/2022 Design walkthrough has been completed, Awaiting drawings from Enfinity Engineering, which should be completed in early December.
21 | Capital | 20700 | 851 | CP_400170 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Steam Generator 1 Removal and Connection to Central Plant Steam | Design | Sean Rewers | TBD | 2500 | 2500 | 2500 | 0 | 2500 | 11/22/2022 Awaiting a contact for the existing system. During our walkthrough we noticed some damage to the existing system that was not covered in the current design. A new design may need to be done to completely remove existing and install a small, less intricate system.
22 | TBD | 20701 | 4399 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC Science & Engineering (SC5) - Chemical Discharge Replacement | Programming / Planning | Sean Rewers | TBD | 0 | 0 | 0 | 0 | TBD | 11/28/2022 Awaiting a contact for the original chemical discharge system. There was some damage noted to the existing tanks which may mean we have to redesign the entire system.
23 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Bidding | Ben Bedock | 175000 | 13550 | 13550 | 13550 | 0 | 175000 | 11/22/2022 Project currently out to bid.
[11 empty] | 20613166.5 | 5115926.5 | 3852957 | 4761707 | 1966133.6 | 9236595
Projects to be added
OGSM - roof replacement (areas not impacted by remodel) ~$200k
Bryan building - HVAC, domestic water line replacement ~TBD
MRB III 9th Floor - Replace Controls (Phase 3 of 5) ~1.5m
Projects to be discussed

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget | FRP_Funding
12000 - Arts and Science: Office of the Dean | 781870 | 809320 | 809320
BENSON OLD CENTRAL | 0 | 0 | 0
SC CHEMISTRY | 781870 | 784370 | 784370
WILSON HALL | 0 | 24950 | 24950
SC SCIENCE & ENGINEERING | 0 | 0 | 0
13000 - Blair: Office of the Dean | 5377890 | 400340 | 1387917.5
BLAIR SCHOOL OF MUSIC | 5377890 | 400340 | 1387917.5
14000 - Divinity: Office of the Dean | 8101000 | 139640 | 1466350
DIVINITY | 8101000 | 139640 | 1466350
15000 - Engineering: Office of the Dean | 0 | 330000 | 330000
1025 16TH AVE S | 0 | 135000 | 135000
KECK FREE ELECTRON LASER CTR | 0 | 195000 | 195000
17100 - Law: Business Affairs | 1445389 | 1445389 | 722694.5
Law School | 1445389 | 1445389 | 722694.5
18200 - Basic Sciences: Office of the Dean | 1434687.5 | 1434687.5 | 1434687.5
MRB III BIO/SCI | 1434687.5 | 1434687.5 | 1434687.5
21000 - Peabody College: Office of the Dean | 3472330 | 494450 | 3023525.5
JESUP PSYCHOLOGY | 456850 | 456850 | 79415.5
One Magnolia Circle | 145000 | 22000 | 145000
PEABODY ADMINISTRATION | 560000 | 2050 | 560000
WYATT CENTER | 2310480 | 13550 | 2239110
19100 - Nursing: Business Affairs | 0 | 62100 | 62100
Godchaux Hall | 0 | 62100 | 62100
Grand Total | 20613166.5 | 5115926.5 | 9236595
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## 10085
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10085 | 4591 | N/A | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Design | Sean Rewers | 22000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
[5 empty] | Balance |  | 0

## 10098
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III 4th Floor - Replace Controls (Phase 2 of 5) | Construction | Hans Mooy | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
[5 empty] | Balance |  | 0

## 10146
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Engineering | Construction | Sean Rewers | 62100
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
[5 empty] | Balance |  | 0

## 20179
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Construction | Bob Grummon | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
[5 empty] | Balance |  | 0

## 20336
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
327890
[5 empty] | Balance |  | 0

## 20431
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity - AHU 5N (5 & 6) Replacement with Benton | Design | Hans Mooy | 139640
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
139640
[5 empty] | Balance |  | 0

## 20497
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Construction | Ben Bedock | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
456850
[5 empty] | Balance |  | 0

## 20566
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Award | Ben Bedock | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
781870
[5 empty] | Balance |  | 0

## 20574
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Award | Sean Rewers | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
[5 empty] | Balance |  | 0

## 20577
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 53750
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
[5 empty] | Balance |  | 0

## 20644
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Design | Ben Bedock | 2050
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
[5 empty] | Balance |  | 0

## 20667
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 135000
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
[5 empty] | Balance |  | 0

## 20668
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 195000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
[5 empty] | Balance |  | 0

## 20698
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 24950
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
24950
[5 empty] | Balance |  | 0

## 20700
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20700 | 851 | CP_400170 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Steam Generator 1 Removal and Connection to Central Plant Steam | Design | Sean Rewers | 2500
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
[5 empty] | Balance |  | 0

## 20702
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Bidding | Ben Bedock | 13550
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
[5 empty] | Balance |  | 0

## JE Log
Completed journal entries
Sources |  | Journal entries to be processed
crowhus_07262022_FRP | 9364499 | tbd | 0
Total sources | 9364499
Uses
crowhus_07272022_FRP | 2018595.5
crowhus_08312022_FRP | 85900
crowhus_09302022_FRP | 197362.5
crowhus_10312022_FRP | 791392
crowhus_11302022_FRP | 776870
Total Uses | 3870120
(less) tbd | 0
Balance | 5494379

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - OWEN | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.