## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2023-06-09
Total program - FY23 |  |  | (1)
School | GSF | Contribution | Estimated FRP | Contribution vs. Estimated
Arts & Science | 1075461.7321 | 3663826 | 2895123.625 | 768702.375
Blair | 121421.4269 | 413652 | 574290 | -160638
Divinity | 57814.7309 | 196960 | 96362.5 | 100597.5
Engineering | 537962.3327 | 1832701 | 353000 | 1479701
Law | 120155.4846 | 409339 | 1206134.5 | -796795.5
SOM Basic Sciences | 280022.3999 | 953965 | 1036871.875 | -82906.875
Nursing | 106166.7 | 361683 | 4900 | 356783
Owen | 59008.3617 | 201027 | 300000 | -98973
Peabody | 390796.8848 | 1331346 | 2953937.76 | -1622591.76
| 2748810.0535 | 9364499 | 9420620.26 | -56121.26
Total program - FY24 |  |  | (1)
School | GSF | Contribution | Estimated FRP | Contribution vs. Estimated
Arts & Science | 1059147 | 4204813.59 | 1497725 | 2707088.59
Blair | 121421 | 482041.37 | 926600 | -444558.63
Divinity | 58263 | 231304.11 | 4000000 | -3768695.89
Engineering | 552478 | 2193337.66 | 0 | 2193337.66
Law | 120155 | 477015.35 | 0 | 477015.35
SOM Basic Sciences | 265674 | 1054725.78 | 870675 | 184050.78
Nursing | 105746 | 419811.62 | 0 | 419811.62
Owen | 99140 | 393585.8 | 0 | 393585.8
Peabody | 396133 | 1572648.01 | 0 | 1572648.01
| 2748810.0535 | 11029283.29 | 7295000 | 3734283.29

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2023-06-09
| Projects |  |  |  | (1) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | Estimated FY23 FRP | Estimated FY24 FRP
1 | Financial Closeout | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000 | 0
2 | Closeout | 10098 | SOM Basic Sciences | MRB III 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | 0
3 | Design | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 0 | 4900 | TBD
4 | Closeout | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0
5 | Construction | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | 0
6 | Construction | 20431 | Divinity | Divinity - AHU 5N (5 & 6) Replacement | 4375000 | 69862.5 | 4000000
7 | Bidding | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2910000 | 81100 | 1028900
8 | Design | 20489 | Divinity | Divinity - AHU 1N (1&3) Replacement with Benton | 3726000 | 26500 | 0
9 | Construction | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | 0
10 | Construction | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | 0
11 | Construction | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | 0
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0
13 | Construction | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | 0
14 | Construction | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | 0
15 | Construction | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | 0
16 | Design | 20577 | Blair | Blair School of Music - Air Handling Unit Replacement | 4500000 | 223000 | 0
17 | Construction | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | 0
18 | Award | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | 0
19 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 146500 | 146500 | TBD
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 206500 | 206500 | TBD
21 | Design | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 29250 | 29250 | TBD
22 | Construction | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 0
23 | Award | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0
24 | Construction | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | 0
25 | Construction | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 715000 | 0
26 | Planning | 20723 | SOM Basic Sciences | MRB III 4,5,8,9th Floor - Replace Controls (Phase 3) | 1500000 | 160500 | 1339500
27 | Design | 20724 | Blair | Blair School of Music - Steam Line | 950000 | 23400 | 926600
28 | Construction | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | 0
29 | Design | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 0 | 0 | TBD
30 | Construction | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | 0
31 | Not Started | 20772 | Owen | Owen - Roof Replacement (Slate Portion) | 0 | 0 | TBD
32 | Award | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | 0
[5 empty] | 28172492.76 | 9420620.26 | 7295000

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 estimated FRP funding for Projects | MRB III Adj | FY23 revised estimated FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 estimated FRP funding for Projects | MRB III Adj | FY24 revised estimated FRP | Contribution vs. FY24 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 2.3368 | 0.55832 | 2.8951 | 0.7687 | 4.2048 | 1.0289 | 0.46882 | 1.4977 | 2.7071
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 0.9266 |  | 0.9266 | -0.44456
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 4 |  | 4 | -3.7687
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0 |  | 0 | 2.1933
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0 |  | 0 | 0.47702
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | 1.3395 | -0.46882 | 0.87067 | 0.18405
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0 |  | 0 | 0.41981
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 0 |  | 0 | 0.39359
Peabody | 390796.8848 | 1.3313 | 2.9539 |  | 2.9539 | -1.6226 | 1.5726 | 0 |  | 0 | 1.5726
| 2748810.0535 | 9.3645 | 9.4206 |  | 9.4206 | -0.056121 | 11.0293 | 7.295 |  | 7.295 | 3.7343
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | Estimated Budget |  |  |  |  | Estimated Budget
|  | MRB III BIO/SCI | 1595187.5 |  |  |  |  | 1339500
|  | A&S | 558315.625 |  |  |  |  | 468825
|  | SOM | 1036871.875 |  |  |  |  | 870675
|  |  | 1595187.5 |  |  |  |  | 1339500

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24
|  | 3.41 |  |  | 3.97
School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29
Contribution |  | 9364499 | Contribution |  | 11029283.29
Anticipated spend |  | 9420620.26 | Anticipated spend |  | 7295000
Remaining funds |  | -56121.26 | Remaining funds |  | 3734283.29

## Project Status
Facility Renewal Program: Projects
JE LOG_FY23'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | FY23 FRP Cash Transferred | FY23 FRP Estimated | FY23 FRP Total Contribution | FY24 FRP Estimated | FY25 FRP Estimated | FY23-x | FY24-x | FY25-x | Project status update
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Financial Closeout | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 22000 | 0 | 22000 | 0 | 0 | yes | no | no | 03/22/2023 Project is in closeout.
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III 4th Floor - Replace Controls (Phase 2) | Closeout | Hans Mooy | 1216485.5 | 1216485.5 | 1212059.54 | 1212059.54 | 1212059.54 | 1216485.5 | 0 | 1216485.5 | 0 | 0 | yes | no | no | 05/23/2023 Year End Warranty Walkthrough set for 12/04/2023 at 2:30
3 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 62100 | 62100 | 62100 | 62100 | 4900 | 0 | 4900 | TBD | TBD | yes | yes | yes | 05/30/2023 Project will be bid out this summer for FY24 construction
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | Law School | Law School - Fire Alarm System Replacement | Closeout | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 | 722694.5 | 0 | 722694.5 | 0 | 0 | yes | no | no | 05/24/2023 Work is complete. Fire Marshal asked that a radio antennae be installed, but did not make it a condition of completion.
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 89125 | 327890 | 0 | 327890 | 0 | 0 | yes | no | no | 05/22/2023 Construction started on the new elevator mechanical room. Once room is completed, elevator modernization to start.
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 4375000 | 139640 | 126225 | 126225 | 82281.22 | 69862.5 | 0 | 69862.5 | 4000000 | 0 | yes | yes | no | 05/22/2023 FM Sylvan had been awarded the project. An LOI is currently being signed. Construction start is set for January 2024.
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 2910000 | 2790000 | 120500 | 1825148 | 69750 | 81100 | 0 | 81100 | 1028900 | 0 | yes | yes | no | 05/01/2023 Construction documents are complete. CDs have been submitted for permit and contractor proposals are due 5/2. Construction is expected to start in May and complete for tenants to occupy the building in August 2023.
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 3726000 | 26500 | 15895 | 15895 | 1222.5 | 26500 | 0 | 26500 | 0 | TBD | yes | no | yes | 05/22/2023 Design meetings continue...a document page flip is set for 06/05/23.
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 407000 | 79415.5 | 0 | 79415.5 | 0 | 0 | yes | no | no | 05/22/2023 Windows to ship on 05/30. Once received, windows will be installed ASAP.
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 0 | 344155.26 | 0 | 344155.26 | 0 | 0 | yes | no | no | 05/22/2023 Window repairs from the 3rd floor down has started. New window installation on the 4th floor to begin on 06/12/2023
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 75970 | 405791 | 0 | 405791 | 0 | 0 | yes | no | no | 05/23/2023 Construction has started. Contractors are working from the top level down removing old VAVs and replacing one at a time.
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | no | no | yes | 03/24/2023 Working with appropriate parties to determine scope of work.
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 | 781870 | 709050 | 709050 | 217250 | 781870 | 0 | 781870 | 0 | 0 | yes | no | no | 05/22/2023 Staging and preparing the space for the elevators has started. Construction to start on 06/12 and go for two weeks on the penthouse elevator.
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 0 | 1232681 | 0 | 1232681 | 0 | 0 | yes | no | no | 05/22/2023 Materials have been delivered on 05/17. Construction started 05/22.
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 42360 | 218202 | 0 | 218202 | 0 | 0 | yes | no | no | 05/23/2023 Construction is ongoing. 1 AHU has had the coils replaced and they are currently working on the 2nd AHU, in the loading dock are now.
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 4500000 | 223000 | 220566.21 | 220566.21 | 168841.21 | 223000 | 0 | 223000 | 0 | TBD | yes | no | yes | 05/22/2023 Project on hold until FRP funding available FY25 or FY26
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 | 630554 | 570996 | 570996 | 175193.4 | 630554 | 0 | 630554 | 0 | 0 | yes | no | no | 05/22/2023 Window work has been completed. Roof replacement to start on 05/22.
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875 | 125875 | 0 | 112250 | 0 | 125875 | 0 | 125875 | 0 | 0 | yes | no | no | 05/22/2023 PO process has started.
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500 | 146500 | 146500 | 146500 | 0 | 146500 | 0 | 146500 | TBD | 0 | yes | yes | no | 05/24/2023 We are awaiting OPR packet from CX. Design team has pulled together a recommendation letter and begun some work on the initial design.
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500 | 206500 | 206500 | 206500 | 0 | 206500 | 0 | 206500 | TBD | 0 | yes | yes | no | 05/24/2023 Awaitin OPR packet from CX. We will have a walkthrough this month with the design team and they will begin initial design.
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250 | 29250 | 24950 | 29250 | 21207.5 | 29250 | 0 | 29250 | TBD | 0 | yes | yes | no | 05/23/2023 First page flip has been completed on the design. We will have a second page flip in June with the lab occupants to iron out the lower level requirements. We will be trying to get fire departments signal testing done this summer, we are awaiting a proposal from a contractor.
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 80000 | 79623 | 69954 | 69954 | 2500 | 79623 | 0 | 79623 | 0 | 0 | yes | no | no | 05/23/2023 Construction has started. Sylvan has welded up the condensate return and replaced the steam supply valve. Domestic water in the are has been capped. SG 1 has been disconnected and demo has started.
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 500000 | 499093 | 0 | 0 | 0 | 499093 | 0 | 499093 | 0 | 0 | yes | no | no | 05/30/2023 We have reached out to EHS to see if they can test the water entering the tank, and may be changing the scope depending on those results.
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 53751.49 | 239341 | 0 | 239341 | 0 | 0 | yes | no | no | 05/22/2023 Construction started on 05/15.
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000 | 715000 | 21250 | 616510 | 17400 | 715000 | 0 | 715000 | 0 | 0 | yes | no | no | 05/23/2023 Demo to begin on 5/30/23. Construction to be complete late July.
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III 4,5,8,9th Floor - Replace Controls (Phase 3) | Planning | Hans Mooy | 1500000 | 160500 | 155232.52 | 155232.52 | 133807.52 | 160500 | 0 | 160500 | 1339500 | 0 | yes | yes | no | 05/23/2023 Project to be bid July 2023.
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 950000 | 23400 | 21480 | 21480 | 0 | 23400 | 0 | 23400 | 926600 | 0 | yes | yes | no | 05/22/2023 Design meetings continue.
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 0 | 300000 | 0 | 300000 | 0 | 0 | yes | no | no | 05/22/2023 Construction to start once SLC roof is complete. Awaiting proposed start date.
29 | TBD | 20767 | 8673 |  | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Sean Rewers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | no | yes | no | 05/23/2023 We have received a quote for the grout injection. I have walked the exterior with a landscape contractor who is getting us a quote in May for hydro excavation and plant replacement. Project is slated for FY 24.
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 0 | 24997 | 0 | 24997 | 0 | 0 | yes | no | no | 05/30/2023 Sylvan has installed ductwork and has been working on getting the VAV and electrical installed. Project i son track.
31 | Operating | 20772 | 8675 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Not Started | Ben Bedock |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | no | yes | no | 03/24/2023 Summer 2024 project. Bidding process will start closer to summer 2023 to allow 6 months for slate production. Project will more than likely take longer than summer break and will need to start during school.
32 | Capital | 20792 |  | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 400000 | 483440 | 0 | 0 | 0 | 0 | 483440 | 483440 | 0 | 0 | yes | no | no | 05/22/2023 Project has been approved. PO process has officially started.
[11 empty] | 28172492.76 | 13356626.76 | 8229133.31 | 10645591.31 | 4201742.52 | 8937180.26 | 483440 | 9420620.26 | 7295000 | 0
FALSE
Projects to be added
[8 empty] | Godchaux - replace roof [Ben] - wait until after HVAC project completed, FY25 |  |  | Collections |  |  |  |  | 9364499 |  | Collections | 11029283.29
MRB III - roof repairs?
[8 empty] | SC-7 roof work in conjunction with CUI? |  |  | Transferred |  |  |  |  | 8937180.26 |  | Transferred | 0
[11 empty] | To be moved |  |  |  |  | 483440 |  | To be moved | 7295000
[16 empty] | 9420620.26 |  |  | 7295000
[8 empty] | Projects to be discussed |  |  | Remaining |  |  |  |  | -56121.26 |  | Remaining | 3734283.29
Chris to provide next priority projects to add to list (elevators, roofs, etc.)
Add tab about general guidance for shared projects (Bryan Building example) and opex project FAQs
Sam to email group in late July to announce (1) website (2) guidance and (3) FY24 collections
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will potentially include roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordinating with EHS, may change direction.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection
| 1 | 10085 | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Financial Closeout | Sean Rewers | 22000 | 0 | 22000 | 9364499
| 2 | 10098 | MRB III BIO/SCI | MRB III 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy | 1216485.5 | 0 | 1216485.5
| 3 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 4900 | 0 | 4900
| 4 | 20179 | Law School | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon | 722694.5 | 0 | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 | 0 | 327890
| 6 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 69862.5 | 0 | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 81100 | 0 | 81100
| 8 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500 | 0 | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 79415.5 | 0 | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 | 0 | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791 | 0 | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 | 0 | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 | 0 | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 0 | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000 | 0 | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 | 0 | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875 | 0 | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500 | 0 | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500 | 0 | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250 | 0 | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623 | 0 | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093 | 0 | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341 | 0 | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000 | 0 | 715000
| 25 | 20723 | MRB III BIO/SCI | MRB III 4,5,8,9th Floor - Replace Controls (Phase 3) | Programming / Planning | Hans Mooy | 160500 | 0 | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 23400 | 0 | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 | 0 | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997 | 0 | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 0 | 483440 | 483440
[7 empty] | 8937180.26 | 483440 | 9420620.26
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 11029283.29
| 2 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy |  | 4000000 | 4000000
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett |  | 1028900 | 1028900
| 4 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | TBD | TBD
| 5 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | TBD | TBD
| 6 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | TBD | TBD
| 7 | 20723 | MRB III BIO/SCI | MRB III 4,5,8,9th Floor - Replace Controls (Phase 3) | Planning | Hans Mooy |  | 1339500 | 1339500
| 8 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy |  | 926600 | 926600
| 9 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Sean Rewers |  | TBD | TBD
| 10 | 20772 | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Not Started | Ben Bedock |  | TBD | TBD
[7 empty] | 0 | 7295000 | 7295000
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 0
| 2 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy |  | TBD | TBD
| 3 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  | TBD | TBD
| 4 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy |  | TBD | TBD
[7 empty] | 0 | 0 | 0

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget | FY23 FRP Forecast
12000 - Arts and Science: Office of the Dean | 5166995 | 2376208 | 1717974
BENSON OLD CENTRAL | 125875 | 125875 | 125875
SC CHEMISTRY | 886870 | 886490 | 886490
WILSON HALL | 29250 | 29250 | 29250
SC SCIENCE & ENGINEERING | 500000 | 499093 | 499093
BRYAN BLDG | 2910000 | 120500 | 81100
BUTTRICK HALL | 715000 | 715000 | 96166
13000 - Blair: Office of the Dean | 5777890 | 574290 | 574290
BLAIR SCHOOL OF MUSIC | 5777890 | 574290 | 574290
14000 - Divinity: Office of the Dean | 8101000 | 166140 | 96362.5
DIVINITY | 8101000 | 166140 | 96362.5
15000 - Engineering: Office of the Dean | 739000 | 353000 | 353000
1025 16TH AVE S | 146500 | 146500 | 146500
KECK FREE ELECTRON LASER CTR | 592500 | 206500 | 206500
17100 - Law: Business Affairs | 1845389 | 1928829 | 1206134.5
Law School | 1845389 | 1928829 | 1206134.5
18200 - Basic Sciences: Office of the Dean | 2934687.5 | 1595187.5 | 1595187.5
MRB III BIO/SCI | 2934687.5 | 1595187.5 | 1595187.5
21000 - Peabody College: Office of the Dean | 3307531.26 | 3331372.26 | 2953937.76
JESUP PSYCHOLOGY | 456850 | 456850 | 79415.5
One Magnolia Circle | 17500 | 22000 | 22000
PEABODY ADMINISTRATION | 630554 | 630554 | 630554
WYATT CENTER | 2202627.26 | 2221968.26 | 2221968.26
SIX MAGNOLIA CIRCLE |  | 0 | 0
19100 - Nursing: Business Affairs |  | 62100 | 4900
Godchaux Hall |  | 62100 | 4900
20000 - Owen: Office of the Dean | 300000 | 300000 | 300000
OWEN GRAD MGMT | 300000 | 300000 | 300000
Grand Total | 28172492.76 | 10687126.76 | 8801786.26
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## 10085
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Financial Closeout | Sean Rewers | 22000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | Total transfers from FRP cash |  |  | 22000
|  |  |  | Balance |  |  | 0

## 10098
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III 4th Floor - Replace Controls (Phase 2) | Closeout | Hans Mooy | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | Total transfers from FRP cash |  |  | 1216485.5
|  |  |  | Balance |  |  | 0

## 10146
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 62100
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | Total transfers from FRP cash |  |  | 4900
|  |  |  | Balance |  |  | 0

## 20179
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Closeout | Bob Grummon | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
|  |  |  | Total transfers from FRP cash |  |  | 722694.5
|  |  |  | Balance |  |  | 0

## 20336
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | Total transfers from FRP cash |  |  | 327890
|  |  |  | Balance |  |  | 0

## 20431
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 139640
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
139640
|  |  |  | Total transfers from FRP cash |  |  | 69862.5
|  |  |  | Balance |  |  | 0

## 20478
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 2790000
[8 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | TBD | BAC-3 |  | 1028900 | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
2790000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Construction | Ben Bedock | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
456850
|  |  |  | Total transfers from FRP cash |  |  | 79415.5
|  |  |  | Balance |  |  | 0

## 20506
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | Total transfers from FRP cash |  |  | 344155.26
|  |  |  | Balance |  |  | 0

## 20562
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | Total transfers from FRP cash |  |  | 405791
|  |  |  | Balance |  |  | 0

## 20566
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | Total transfers from FRP cash |  |  | 781870
|  |  |  | Balance |  |  | 0

## 20573
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | Total transfers from FRP cash |  |  | 1232681
|  |  |  | Balance |  |  | 0

## 20574
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | Total transfers from FRP cash |  |  | 218202
|  |  |  | Balance |  |  | 0

## 20577
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | Total transfers from FRP cash |  |  | 223000
|  |  |  | Balance |  |  | 0

## 20644
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | Total transfers from FRP cash |  |  | 630554
|  |  |  | Balance |  |  | 0

## 20645
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | Total transfers from FRP cash |  |  | 125875
|  |  |  | Balance |  |  | 0

## 20667
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 206500
|  |  |  | Balance |  |  | 0

## 20698
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | Total transfers from FRP cash |  |  | 29250
|  |  |  | Balance |  |  | 0

## 20700
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | Total transfers from FRP cash |  |  | 79623
|  |  |  | Balance |  |  | 0

## 20701
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | Total transfers from FRP cash |  |  | 239341
|  |  |  | Balance |  |  | 0

## 20718
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
|  |  |  | Total transfers from FRP cash |  |  | 715000
|  |  |  | Balance |  |  | 0

## 20723
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III 4,5,8,9th Floor - Replace Controls (Phase 3) | Planning | Hans Mooy | 160500
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | Total transfers from FRP cash |  |  | 160500
|  |  |  | Balance |  |  | 0

## 20724
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line | Design | Hans Mooy | 23400
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | Total transfers from FRP cash |  |  | 23400
|  |  |  | Balance |  |  | 0

## 20735
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | Total transfers from FRP cash |  |  | 300000
|  |  |  | Balance |  |  | 0

## 20771
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | Total transfers from FRP cash |  |  | 24997
|  |  |  | Balance |  |  | 0

## 20792
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20792 | 0 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 483440
Funding transfers
|  |  |  | TBD | BAC-1 |  | 483440
|  |  |  | Total transfers from FRP cash |  |  | 483440
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
| Sources |  |  | Journal entries to be processed
| crowhus_07262022_FRP | 9364499 |  | tbd | 1512340
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| Total Uses | 8318346.26 | 88.83%
| (less) tbd | 1512340
| Balance | -466187.26 | -4.978%

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.