## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2023-07-06
Total program - FY23 |  |  | (1)
School | GSF | Contribution | Estimated FRP | Contribution vs. Estimated
Arts & Science | 1075461.7321 | 3663826 | 2895123.625 | 768702.375
Blair | 121421.4269 | 413652 | 574290 | -160638
Divinity | 57814.7309 | 196960 | 96362.5 | 100597.5
Engineering | 537962.3327 | 1832701 | 353000 | 1479701
Law | 120155.4846 | 409339 | 1206134.5 | -796795.5
SOM Basic Sciences | 280022.3999 | 953965 | 1036871.875 | -82906.875
Nursing | 106166.7 | 361683 | 4900 | 356783
Owen | 59008.3617 | 201027 | 300000 | -98973
Peabody | 390796.8848 | 1331346 | 2953937.76 | -1622591.76
| 2748810.0535 | 9364499 | 9420620.26 | -56121.26
Total program - FY24 |  |  | (1)
School | GSF | Contribution | Estimated FRP | Contribution vs. Estimated
Arts & Science | 1059147 | 4204813.59 | 1497725 | 2707088.59
Blair | 121421 | 482041.37 | 1376600 | -894558.63
Divinity | 58263 | 231304.11 | 3730137.5 | -3498833.39
Engineering | 552478 | 2193337.66 | 0 | 2193337.66
Law | 120155 | 477015.35 | 0 | 477015.35
SOM Basic Sciences | 265674 | 1054725.78 | 870675 | 184050.78
Nursing | 105746 | 419811.62 | 0 | 419811.62
Owen | 99140 | 393585.8 | 0 | 393585.8
Peabody | 396133 | 1572648.01 | 0 | 1572648.01
| 2748810.0535 | 11029283.29 | 7475137.5 | 3554145.79

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2023-07-06
| Projects |  |  |  | (1) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | Estimated FY23 FRP | Estimated FY24 FRP
1 | Financial Closeout | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000 | 0
2 | Warranty or Construction Closeout | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | 0
3 | Design | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 0 | 4900 | TBD
4 | Warranty or Construction Closeout | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0
5 | Construction | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | 0
6 | Construction | 20431 | Divinity | Divinity - AHU 5N (5 & 6) Replacement | 3800000 | 69862.5 | 3730137.5
7 | Construction | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2910000 | 81100 | 1028900
8 | Design | 20489 | Divinity | Divinity - AHU 1N (1&3) Replacement with Benton | 3726000 | 26500 | 0
9 | Construction | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | 0
10 | Construction | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | 0
11 | Construction | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | 0
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0
13 | Construction | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | 0
14 | Construction | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | 0
15 | Construction | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | 0
16 | Design | 20577 | Blair | Blair School of Music - Air Handling Unit Replacement | 4500000 | 223000 | 0
17 | Construction | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | 0
18 | Construction | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | 0
19 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 0 | 146500 | TBD
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | TBD
21 | Design | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 0 | 29250 | TBD
22 | Construction | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 0
23 | Award | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0
24 | Construction | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | 0
25 | Construction | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 715000 | 0
26 | Bidding | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1500000 | 160500 | 1339500
27 | Bidding | 20724 | Blair | Blair School of Music - Steam Line | 1400000 | 23400 | 1376600
28 | Construction | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | 0
29 | Design | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 0 | 0 | 0
30 | Construction | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | 0
31 | Not Started | 20772 | Owen | Owen - Roof Replacement (Slate Portion) | 0 | 0 | TBD
32 | Construction | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | 0
[5 empty] | 27665242.76 | 9420620.26 | 7475137.5

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 estimated FRP funding for Projects | MRB III Adj | FY23 revised estimated FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 estimated FRP funding for Projects | MRB III Adj | FY24 revised estimated FRP | Contribution vs. FY24 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 2.3368 | 0.55832 | 2.8951 | 0.7687 | 4.2048 | 1.0289 | 0.46882 | 1.4977 | 2.7071
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.3766 |  | 1.3766 | -0.89456
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.7301 |  | 3.7301 | -3.4988
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0 |  | 0 | 2.1933
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0 |  | 0 | 0.47702
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | 1.3395 | -0.46882 | 0.87067 | 0.18405
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0 |  | 0 | 0.41981
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 0 |  | 0 | 0.39359
Peabody | 390796.8848 | 1.3313 | 2.9539 |  | 2.9539 | -1.6226 | 1.5726 | 0 |  | 0 | 1.5726
| 2748810.0535 | 9.3645 | 9.4206 |  | 9.4206 | -0.056121 | 11.0293 | 7.4751 |  | 7.4751 | 3.5541
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | Estimated Budget |  |  |  |  | Estimated Budget
|  | MRB III BIO/SCI | 1595187.5 |  |  |  |  | 1339500
|  | A&S | 558315.625 |  |  |  |  | 468825
|  | SOM | 1036871.875 |  |  |  |  | 870675
|  |  | 1595187.5 |  |  |  |  | 1339500

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24
|  | 3.41 |  |  | 3.97
School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29
Contribution |  | 9364499 | Contribution |  | 11029283.29
Anticipated spend |  | 9420620.26 | Anticipated spend |  | 7475137.5
Remaining funds |  | -56121.26 | Remaining funds |  | 3554145.79

## Project Status
Facility Renewal Program: Projects
JE LOG_FY23'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | FY23 FRP Cash Transferred | FY23 FRP Estimated | FY23 FRP Total Contribution | FY24 FRP Estimated | FY25 FRP Estimated | FY23-x | FY24-x | FY25-x | Project status update
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Financial Closeout | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 22000 | 0 | 22000 | 0 | 0 | yes | no | no | 03/22/2023 Project is in closeout.
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty or Construction Closeout | Hans Mooy | 1216485.5 | 1216485.5 | 1212059.54 | 1212059.54 | 1212059.54 | 1216485.5 | 0 | 1216485.5 | 0 | 0 | yes | no | no | 06/26/2023 Project Complete
3 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 62100 | 62100 | 62100 | 62100 | 4900 | 0 | 4900 | TBD | TBD | yes | yes | yes | 06/23/2023 Project will go out to bid soon. I have contacted SSR to mark up drawings into phases so we can attach them to the bidding portal.
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | Law School | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 | 722694.5 | 0 | 722694.5 | 0 | 0 | yes | no | no | 06/26/2023 Work is complete
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 168775 | 327890 | 0 | 327890 | 0 | 0 | yes | no | no | 06/23/2023 Construction to resume on 06/26 intermittently. Starting July 10, the elevator will be down for a week or two mechanical modernization. Elevator is planned to be up and running by the first week of August.
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 3800000 | 139640 | 126225 | 126225 | 84031.22 | 69862.5 | 0 | 69862.5 | 3730137.5 | 0 | yes | yes | no | 06/26/2023 Equipment shop drawings being prepared.
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2910000 | 2790000 | 1825148 | 1856648 | 79900 | 81100 | 0 | 81100 | 1028900 | 0 | yes | yes | no | 06/23/2023 DPR has mobilized and began construction in June. The interior renovation will be completed in August for A&S to use as swing space during the Garland Hall renovation. Additional items included in the project scope of work that will be completed after August include replacement of the roof mechanical units and roof repairs.
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 3726000 | 26500 | 15895 | 15895 | 8017.5 | 26500 | 0 | 26500 | 0 | TBD | yes | no | yes | 06/26/2023 Drawings to Nashville Machine for Pre-con budget estimate on 06/26/23. Project is slated for FY 25 funding.
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 407000 | 79415.5 | 0 | 79415.5 | 0 | 0 | yes | no | no | 06/23/2023 Final item of window installation is nearing completion. A few touch up items remain until we have hit 100% completion.
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 105654.62 | 344155.26 | 0 | 344155.26 | 0 | 0 | yes | no | no | 06/23/2023 Window repair and painting is nearing completion. Fourth floor window installation will begin on 07/10/2023.
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 267159.7 | 405791 | 0 | 405791 | 0 | 0 | yes | no | no | 06/23/2023 All VAVs have been installed and we will start connecting water lines this week. We still need to coordinate with roofing project to install the filter racks in rooftop AHUs.
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | no | no | yes | 03/24/2023 Working with appropriate parties to determine scope of work.
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 | 781870 | 722579.11 | 722579.11 | 545950 | 781870 | 0 | 781870 | 0 | 0 | yes | no | no | 06/23/2023 Penthouse elevator has passed state inspection ahead of schedule. The elevator will be operating starting Monday 06/26/2023. 06/26 will be the starting day of the other elevator for modernization. This elevator will be completed during normal business hours.
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 0 | 1232681 | 0 | 1232681 | 0 | 0 | yes | no | no | 06/23/2023 Metal roof has been installed. Roof over the old side has been installed as well. 1990's addition to being next week. Weather has not delayed the installation to much.
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 166360 | 218202 | 0 | 218202 | 0 | 0 | yes | no | no | 06/23/2023 Coils and piping has been installed. We are awaiting pumps to complete the project. Anderson piping has given me an estimate of August for delivery and completion of the project.
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 4500000 | 223000 | 220566.21 | 220566.21 | 179066.21 | 223000 | 0 | 223000 | 0 | TBD | yes | no | yes | 05/22/2023 On hold
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 | 630554 | 570996 | 570996 | 175193.4 | 630554 | 0 | 630554 | 0 | 0 | yes | no | no | 06/23/2023 Windows are complete. Roof is nearing completion. Only a few more weeks.
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875 | 125875 | 112250 | 112250 | 85500 | 125875 | 0 | 125875 | 0 | 0 | yes | no | no | 06/23/2023 Soffit work is complete. Door is scheduled to be delivered in 9-11 weeks.
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 146500 | 146500 | 146500 | 0 | 146500 | 0 | 146500 | TBD | 0 | yes | yes | no | 06/28/2023 OPR notes have been completed and sent to Envision. We still have not received a design draft.
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 206500 | 206500 | 206500 | 9525 | 206500 | 0 | 206500 | TBD | 0 | yes | yes | no | 06/28/2023 First draft of chilled water and steam has been completed. Design engineer is still working with AHU supplier to get first draft of HVAC design
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | 29250 | 29250 | 29250 | 21207.5 | 29250 | 0 | 29250 | TBD | 0 | yes | yes | no | 06/23/2023 We are awaiting the design changes for the lower level lab. We have had 1 meeting to discuss with the occupants and they have sent our design team notes on changes that are required. We will have a second meeting to review. We have received a PO for a radio survey install which will be done this summer, and act as the last thing before a drawing set can be released. Expect to put this project out to bid in early FY 24
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 80000 | 79623 | 69954 | 72458.77 | 55117 | 79623 | 0 | 79623 | 0 | 0 | yes | no | no | 06/23/2023 Steam Generator has been removed and shut off valve has been installed. All other lines surrounding the old steam generator have been capped. We are awaiting insulation install and installation of the valves at the AHUs.
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 500000 | 499093 | 0 | 0 | 0 | 499093 | 0 | 499093 | 0 | 0 | yes | no | no | 06/23/2023 Steam generator has been removed and a new shut off valve installed. All other connections around the old steam generator replacement have been capped. We still need to insulate the steam lines and install valves at the AHUs.
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 149599.07 | 239341 | 0 | 239341 | 0 | 0 | yes | no | no | 06/23/2023 Met with state inspector on a few items of concern and have received solutions. Project is on schedule and moving forward.
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000 | 715000 | 616510 | 616510 | 174378.65 | 715000 | 0 | 715000 | 0 | 0 | yes | no | no | 06/30/2023 Drywall finishing will be complete the week of 7/3. New door and window frames are installed. Electrical inspectors have been a delay. Project was scheduled to be complete on 7/21, but the current schedule shows 8/24 as the COO date.
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Bidding | Hans Mooy | 1500000 | 160500 | 155232.52 | 155232.52 | 133807.52 | 160500 | 0 | 160500 | 1339500 | 0 | yes | yes | no | 06/26/2023 RFP sent out t potential bidders. Pre-bid walkthrough is scheduled for 06/30/23.
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Bidding | Hans Mooy | 1400000 | 23400 | 21480 | 21480 | 12000 | 23400 | 0 | 23400 | 1376600 | 0 | yes | yes | no | 06/23/2023 Cost came in from FM Sylvan & Brasfield.... Asking whether we could use Divinity budget savings for the Blair steam shortfall.
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 0 | 300000 | 0 | 300000 | 0 | 0 | yes | no | no | 06/23/2023 Construction started the week of 06/19. Goal is to be completed within a month.
29 | Operating | 20767 | 8673 |  | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Sean Rewers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | no | no | no | 06/23/2023 We have received quotes to trench the front of the building, replace landscaping and seal the foundation. Project is slated for FY 24 start.
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 | 24997 | 0 | 24997 | 0 | 0 | yes | no | no | 06/23/2023 FM Sylvan has completed their work and we are awaiting the plant to install controls.
31 | Capital | 20772 | 8675 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Not Started | Ben Bedock |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | no | yes | no | 03/24/2023 Summer 2024 project. Bidding process will start closer to summer 2023 to allow 6 months for slate production. Project will more than likely take longer than summer break and will need to start during school.
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 400000 | 483440 | 437340 | 437340 | 0 | 0 | 483440 | 483440 | 0 | 0 | yes | no | no | 06/23/2023 Pre-Construction meeting happened on 06/22. Construction is scheduled to start on 06/29.
[11 empty] | 27665242.76 | 13356626.76 | 11096460.42 | 11130465.19 | 5490297.07 | 8937180.26 | 483440 | 9420620.26 | 7475137.5 | 0
FALSE
Projects to be added
[8 empty] | Godchaux - replace roof [Ben] - wait until after HVAC project completed, FY25 |  |  | Collections |  |  |  |  | 9364499 |  | Collections | 11029283.29
[11 empty] | Transferred |  |  |  |  | 8937180.26 |  | Transferred | 0
[11 empty] | To be moved |  |  |  |  | 483440 |  | To be moved | 7475137.5
[8 empty] | Projects to be discussed | [7 empty] | 9420620.26 |  |  | 7475137.5
Chris to provide next priority projects to add to list (elevators, roofs, etc.)
[8 empty] | One Magnolia - elevator modernization (2024)? |  |  | Remaining |  |  |  |  | -56121.26 |  | Remaining | 3554145.79
Bryan Building (20789) - roof?
Vaughn (20807) - roof?
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will potentially include roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordinating with EHS, may change direction.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10085 | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Financial Closeout | Sean Rewers | 22000 | 0 | 22000 | 9364499
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy | 1216485.5 | 0 | 1216485.5
| 3 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 4900 | 0 | 4900
| 4 | 20179 | Law School | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon | 722694.5 | 0 | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 | 0 | 327890
| 6 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 69862.5 | 0 | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 81100 | 0 | 81100
| 8 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500 | 0 | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 79415.5 | 0 | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 | 0 | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791 | 0 | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 | 0 | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 | 0 | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 0 | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000 | 0 | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 | 0 | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875 | 0 | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500 | 0 | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500 | 0 | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250 | 0 | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623 | 0 | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093 | 0 | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341 | 0 | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000 | 0 | 715000
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Hans Mooy | 160500 | 0 | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 23400 | 0 | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 | 0 | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997 | 0 | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 0 | 483440 | 483440
[7 empty] | 8937180.26 | 483440 | 9420620.26 |  | -56121.26
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 11029283.29
| 2 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy |  | 3730137.5 | 3730137.5
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett |  | 1028900 | 1028900
| 4 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | TBD | TBD
| 5 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | TBD | TBD
| 6 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | TBD | TBD
| 7 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Bidding | Hans Mooy |  | 1339500 | 1339500
| 8 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Bidding | Hans Mooy |  | 1376600 | 1376600
| 9 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Sean Rewers |  | 0 | 0
| 10 | 20772 | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Not Started | Ben Bedock |  | TBD | TBD
[7 empty] | 0 | 7475137.5 | 7475137.5 |  | 3554145.79
FY 2025 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 0
| 2 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy |  | TBD | TBD
| 3 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  | TBD | TBD
| 4 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy |  | TBD | TBD
[7 empty] | 0 | 0 | 0 |  | 0

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget | FY23 FRP Forecast
12000 - Arts and Science: Office of the Dean | 5166995 | 2376208 | 1717974
BENSON OLD CENTRAL | 125875 | 125875 | 125875
SC CHEMISTRY | 886870 | 886490 | 886490
WILSON HALL | 29250 | 29250 | 29250
SC SCIENCE & ENGINEERING | 500000 | 499093 | 499093
BRYAN BLDG | 2910000 | 120500 | 81100
BUTTRICK HALL | 715000 | 715000 | 96166
13000 - Blair: Office of the Dean | 5777890 | 574290 | 574290
BLAIR SCHOOL OF MUSIC | 5777890 | 574290 | 574290
14000 - Divinity: Office of the Dean | 8101000 | 166140 | 96362.5
DIVINITY | 8101000 | 166140 | 96362.5
15000 - Engineering: Office of the Dean | 739000 | 353000 | 353000
1025 16TH AVE S | 146500 | 146500 | 146500
KECK FREE ELECTRON LASER CTR | 592500 | 206500 | 206500
17100 - Law: Business Affairs | 1845389 | 1928829 | 1206134.5
Law School | 1845389 | 1928829 | 1206134.5
18200 - Basic Sciences: Office of the Dean | 2934687.5 | 1595187.5 | 1595187.5
MRB III BIO/SCI | 2934687.5 | 1595187.5 | 1595187.5
21000 - Peabody College: Office of the Dean | 3307531.26 | 3331372.26 | 2953937.76
JESUP PSYCHOLOGY | 456850 | 456850 | 79415.5
One Magnolia Circle | 17500 | 22000 | 22000
PEABODY ADMINISTRATION | 630554 | 630554 | 630554
WYATT CENTER | 2202627.26 | 2221968.26 | 2221968.26
SIX MAGNOLIA CIRCLE |  | 0 | 0
19100 - Nursing: Business Affairs |  | 62100 | 4900
Godchaux Hall |  | 62100 | 4900
20000 - Owen: Office of the Dean | 300000 | 300000 | 300000
OWEN GRAD MGMT | 300000 | 300000 | 300000
Grand Total | 28172492.76 | 10687126.76 | 8801786.26
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## 10085
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Financial Closeout | Sean Rewers | 22000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | Total transfers from FRP cash |  |  | 22000
|  |  |  | Balance |  |  | 0

## 10098
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty or Construction Closeout | Hans Mooy | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | Total transfers from FRP cash |  |  | 1216485.5
|  |  |  | Balance |  |  | 0

## 10146
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 62100
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | Total transfers from FRP cash |  |  | 4900
|  |  |  | Balance |  |  | 0

## 20179
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
|  |  |  | Total transfers from FRP cash |  |  | 722694.5
|  |  |  | Balance |  |  | 0

## 20336
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | Total transfers from FRP cash |  |  | 327890
|  |  |  | Balance |  |  | 0

## 20431
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 139640
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
139640
|  |  |  | Total transfers from FRP cash |  |  | 69862.5
|  |  |  | Balance |  |  | 0

## 20478
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2790000
[8 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | TBD | BAC-3 |  | 1028900 | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
2790000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Construction | Ben Bedock | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
456850
|  |  |  | Total transfers from FRP cash |  |  | 79415.5
|  |  |  | Balance |  |  | 0

## 20506
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | Total transfers from FRP cash |  |  | 344155.26
|  |  |  | Balance |  |  | 0

## 20562
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | Total transfers from FRP cash |  |  | 405791
|  |  |  | Balance |  |  | 0

## 20566
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | Total transfers from FRP cash |  |  | 781870
|  |  |  | Balance |  |  | 0

## 20573
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | Total transfers from FRP cash |  |  | 1232681
|  |  |  | Balance |  |  | 0

## 20574
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | Total transfers from FRP cash |  |  | 218202
|  |  |  | Balance |  |  | 0

## 20577
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | Total transfers from FRP cash |  |  | 223000
|  |  |  | Balance |  |  | 0

## 20644
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | Total transfers from FRP cash |  |  | 630554
|  |  |  | Balance |  |  | 0

## 20645
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | Total transfers from FRP cash |  |  | 125875
|  |  |  | Balance |  |  | 0

## 20667
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 206500
|  |  |  | Balance |  |  | 0

## 20698
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | Total transfers from FRP cash |  |  | 29250
|  |  |  | Balance |  |  | 0

## 20700
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | Total transfers from FRP cash |  |  | 79623
|  |  |  | Balance |  |  | 0

## 20701
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | Total transfers from FRP cash |  |  | 239341
|  |  |  | Balance |  |  | 0

## 20718
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
|  |  |  | Total transfers from FRP cash |  |  | 715000
|  |  |  | Balance |  |  | 0

## 20723
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Bidding | Hans Mooy | 160500
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | Total transfers from FRP cash |  |  | 160500
|  |  |  | Balance |  |  | 0

## 20724
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line | Bidding | Hans Mooy | 23400
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | Total transfers from FRP cash |  |  | 23400
|  |  |  | Balance |  |  | 0

## 20735
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | Total transfers from FRP cash |  |  | 300000
|  |  |  | Balance |  |  | 0

## 20771
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | Total transfers from FRP cash |  |  | 24997
|  |  |  | Balance |  |  | 0

## 20792
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 483440
Funding transfers
|  |  |  | TBD | BAC-1 |  | 483440
|  |  |  | Total transfers from FRP cash |  |  | 483440
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
| Sources |  |  | Journal entries to be processed
| crowhus_07262022_FRP | 9364499 |  | tbd | 1512340
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| Total Uses | 8318346.26 | 88.83%
| (less) tbd | 1512340
| Balance | -466187.26 | -4.978%

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.