## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2023-09-06
Total program - FY23 |  |  | (1)
School | GSF | Contribution | Transferred FRP | Contribution vs. Estimated
Arts & Science | 1075461.7321 | 3663826 | 2276289.625 | 1387536.375
Blair | 121421.4269 | 413652 | 574290 | -160638
Divinity | 57814.7309 | 196960 | 96362.5 | 100597.5
Engineering | 537962.3327 | 1832701 | 353000 | 1479701
Law | 120155.4846 | 409339 | 1206134.5 | -796795.5
SOM Basic Sciences | 280022.3999 | 953965 | 1036871.875 | -82906.875
Nursing | 106166.7 | 361683 | 4900 | 356783
Owen | 59008.3617 | 201027 | 300000 | -98973
Peabody | 390796.8848 | 1331346 | 2949437.76 | -1618091.76
| 2748810.0535 | 9364499 | 8797286.26 | 567212.74
Total program - FY24 |  |  | (1)
School | GSF | Contribution | Estimated FRP | Contribution vs. Estimated
Arts & Science | 1059147 | 4204813.59 | 1497725 | 2707088.59
Blair | 121421 | 482041.37 | 1476600 | -994558.63
Divinity | 58263 | 231304.11 | 3730137.5 | -3498833.39
Engineering | 552478 | 2193337.66 | 70000 | 2123337.66
Law | 120155 | 477015.35 | 0 | 477015.35
SOM Basic Sciences | 265674 | 1054725.78 | 870675 | 184050.78
Nursing | 105746 | 419811.62 | 0 | 419811.62
Owen | 99140 | 393585.8 | 0 | 393585.8
Peabody | 396133 | 1572648.01 | 35000 | 1537648.01
| 2748810.0535 | 11029283.29 | 7680137.5 | 3349145.79
(1) - estimated FRP indicates expected funding to be transferred back to the school from FRP program funds. Please note, facility renewal projects may span multiple fiscal years, as such projects may receive funding from multiple fiscal years.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2023-09-06
| Projects |  |  |  | (1) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP | Estimated FY24 FRP
1 | Finalized | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
2 | Financial Closeout | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | 0
3 | Design | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 0 | 4900 | 0
4 | Warranty or Construction Closeout | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0
5 | Warranty or Construction Closeout | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | 0
6 | Construction | 20431 | Divinity | Divinity - AHU 5N (5 & 6) Replacement | 3800000 | 69862.5 | 3730137.5
7 | Construction | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2900000 | 81100 | 1028900
8 | Design | 20489 | Divinity | Divinity - AHU 1N (1&3) Replacement with Benton | 4650000 | 26500 | 0
9 | Warranty or Construction Closeout | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | 0
10 | Warranty or Construction Closeout | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | 0
11 | Construction | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | 0
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0
13 | Warranty or Construction Closeout | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | 0
14 | Construction | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | 0
15 | Construction | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | 0
16 | Design | 20577 | Blair | Blair School of Music - Air Handling Unit Replacement | 4500000 | 223000 | 0
17 | Warranty or Construction Closeout | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | 0
18 | Construction | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | 0
19 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 0 | 146500 | 35000
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | 35000
21 | Design | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 0 | 29250 | 0
22 | Construction | 20700 | Arts & Science | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 0
23 | Design | 20701 | Arts & Science | SC5 - Chemical Discharge Replacement | 500000 | 499093 | 0
24 | Warranty or Construction Closeout | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | 0
25 | Construction | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0
26 | Construction | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1500000 | 160500 | 1339500
27 | Design | 20724 | Blair | Blair School of Music - Steam Line | 1500000 | 23400 | 1476600
28 | Construction | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | 0
29 | Design | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 0 | 0 | 35000
30 | Finalized | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | 0
31 | Programming or Planning | 20772 | Owen | Owen - Roof Replacement (Slate Portion) | 0 | 0 | 0
32 | Construction | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | 0
33 | Design | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 0 | 0 | 0
34 | Not Started | 20833 | Arts & Science | SC5 - HVAC Replacement | 0 | 0 | 0
[5 empty] | 28679242.76 | 8797286.26 | 7680137.5
(1) - estimated total budget represents the best rough order of magnitude for total project costs.
(2) - estimated FYxx FRP indicates expected funding to be transferred back to the school from FRP program funds collected during FYxx.

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
12000 - Arts and Science: Office of the Dean | 5127745 | 5045708
BENSON OLD CENTRAL | 125875 | 125875
SC CHEMISTRY | 886870 | 886490
WILSON HALL |  | 29250
SC SCIENCE & ENGINEERING | 500000 | 499093
BRYAN BLDG | 2900000 | 2790000
BUTTRICK HALL | 715000 | 715000
SC PHYSICS & ASTRONOMY |  | 0
Grand Total | 5127745 | 5045708
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 estimated FRP funding | MRB III Adj | FY24 revised estimated FRP | Contribution vs. FY24 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 1.0289 | 0.46882 | 1.4977 | 2.7071
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.4766 |  | 1.4766 | -0.99456
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.7301 |  | 3.7301 | -3.4988
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0.07 |  | 0.07 | 2.1233
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0 |  | 0 | 0.47702
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | 1.3395 | -0.46882 | 0.87067 | 0.18405
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0 |  | 0 | 0.41981
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 0 |  | 0 | 0.39359
Peabody | 390796.8848 | 1.3313 | 2.9494 |  | 2.9494 | -1.6181 | 1.5726 | 0.035 |  | 0.035 | 1.5376
| 2748810.0535 | 9.3645 | 8.7973 |  | 8.7973 | 0.56721 | 11.0293 | 7.6801 |  | 7.6801 | 3.3491
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24
|  | MRB III BIO/SCI | 1595187.5 |  |  |  |  | 1339500
|  | A&S | 558315.625 |  |  |  |  | 468825
|  | SOM | 1036871.875 |  |  |  |  | 870675
|  |  | 1595187.5 |  |  |  |  | 1339500

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24
|  | 3.41 |  |  | 3.97
School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29
Contribution |  | 9364499 | Contribution |  | 11029283.29
Anticipated spend |  | 7680137.5 | Anticipated spend |  | 6651237.5
Remaining funds |  | 1684361.5 | Remaining funds |  | 4378045.79

## Project Status
Facility Renewal Program: Projects | [15 empty] | JE LOG_FY23'!A1 |  |  | JE LOG_FY24'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY24 FRP Estimated | FY24 FRP Total Contribution | FY25 FRP Estimated | Project status update
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout.
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Financial Closeout | Hans Mooy | 1216485.5 | 1216485.5 | 1212059.54 | 1212059.54 | 1212059.54 | 1216485.5 | 0 | 0 | 0 | 0 | 08/22/2023 project complete
3 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 62100 | 62100 | 62100 | 62100 | 4900 | 0 | TBD | 0 | TBD | 08/29/2023 Po has been started for SSR to complete phase 1 drawings and sign on as commissioning agent. We will put this out to bid after receiving drawings back
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | Law School | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 | 722694.5 | 0 | 0 | 0 | 0 | 08/27/2023 work complete
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Warranty or Construction Closeout | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 274975 | 327890 | 0 | 0 | 0 | 0 | 08/22/2023 Construction is complete. Working on punch list items.
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 3800000 | 139640 | 126225 | 126225 | 100186.22 | 69862.5 | 0 | 3730137.5 | 3730137.5 | 0 | 08/22/2023 Staff move out Thanksgiving 2023. Project estimated start December 2023.
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2900000 | 2790000 | 1869346.53 | 1870106.53 | 416873.11 | 81100 | 1028900 | 0 | 1028900 | 0 | 08/22/2023 The interior fitout was completed on August 14th and A&S is actively moving into the building. DPR is addressing items on the punchlist. Mechanical units and partial roof replacement are scheduled to be done in December 2023 and January 2024.
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 4650000 | 26500 | 15895 | 15895 | 12712.5 | 26500 | 0 | 0 | 0 | TBD | 08/22/2023 Project budget updated with completion of CD's. Construction to wait until FY 25 to start...
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Warranty or Construction Closeout | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 | 79415.5 | 0 | 0 | 0 | 0 | 08/22/2023 Construction complete
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Warranty or Construction Closeout | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 | 344155.26 | 0 | 0 | 0 | 0 | 08/22/2023 Construction complete
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 | 405791 | 0 | 0 | 0 | 0 | 08/22/2023 Still awaiting 1 filter rack to install on AHU. We will be balancing and changing set points on VAVs hopefully this week.
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 03/24/2023 Working with appropriate parties to determine scope of work.
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Warranty or Construction Closeout | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 670650.68 | 781870 | 0 | 0 | 0 | 0 | 08/22/2023 Punch list items to be completed.
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 823000 | 1232681 | 0 | 0 | 0 | 0 | 08/22/2023 Primary roof installation is complete. Metal work remains. Metal work will be completed by 08/31.
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 166360 | 218202 | 0 | 0 | 0 | 0 | 08/22/2023 Pumps have been installed. We are awaiting some electrical starters and insulation to wrap up the project.
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 4500000 | 223000 | 220566.21 | 220566.21 | 185191.21 | 223000 | 0 | 0 | 0 | TBD | 05/22/2023 on hold
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Warranty or Construction Closeout | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 175193.4 | 630554 | 0 | 0 | 0 | 0 | 08/22/2023 Construction complete.
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875 | 125875 | 112250 | 112250 | 85500 | 125875 | 0 | 0 | 0 | 0 | 08/22/2023 Main entrance door to be installed in September. Once installed, project will be complete.
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 146500 | 146500 | 146500 | 0 | 146500 | 0 | 35000 | 35000 | 0 | 08/22/2023 Envision is working on getting a detailed analysis of each HVAC option. We will be having a GC price out each option as our final piece of data to select what type of system we will install. Full CDs will begin after that assessment.
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 206500 | 206500 | 206500 | 47010 | 206500 | 0 | 35000 | 35000 | 0 | 09/01/2023 We are awaiting specs from Hobbs/HVAC Supplier before we can secure pre-construction contractor. ICT has been working on getting drawings ready for pre-construction. Should have a contractor working on pre-con before next update.
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | 29250 | 29250 | 29250 | 21207.5 | 29250 | 0 | TBD | 0 | 0 | 08/29/2023 We have received an updated design set which we will be reviewing over the next few weeks. We have not secured another company to do the radio survey for the building. If the drawing set is approved by the department and Fire/Life Safety we may proceed with bidding to get some cost estimates.
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 80000 | 79623 | 73823.77 | 73823.77 | 73823.77 | 79623 | 0 | 0 | 0 | 0 | 08/22/2023 Project is mostly complete. We turned the steam on, which has not been run to AHUs in 6 years. No leaks but steam traps need to be replaced. Sylvan is working on a quote to have these replaced.
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - Chemical Discharge Replacement | Design | Sean Rewers | 500000 | 499093 | 0 | 18000 | 0 | 499093 | 0 | 0 | 0 | 0 | 08/22/2023 Project is mostly complete. We turned the steam on, which has not been run to AHUs in 6 years. No leaks but steam traps need to be replaced. Sylvan is working on a quote to have these replaced.
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Warranty or Construction Closeout | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 205444 | 239341 | 0 | 0 | 0 | 0 | 08/22/2023 Construction complete
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000 | 715000 | 617745.2 | 622431.2 | 482034.33 | 96166 | 0 | 0 | 0 | 0 | 08/28/2023 Construction complete. Change order 1 in process. Signage and sound masking need to be installed.
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Hans Mooy | 1500000 | 160500 | 155232.52 | 155232.52 | 138257.52 | 160500 | 0 | 1339500 | 1339500 | 0 | 08/22/2023 Project kick-off meeting to occur on 09/05/23
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 1500000 | 23400 | 21480 | 21480 | 12000 | 23400 | 0 | 1476600 | 1476600 | 0 | 08/22/2023 Final footer structural design pending
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 24150 | 300000 | 0 | 0 | 0 | 0 | 08/22/2023 Contractor has been delayed. Working on weekends only. Will finished by 08/27.
29 | Operating | 20767 | 8673 |  | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Jay Surprenant |  | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35000 | 0 | 08/22/2023 Project will start construction in winter 2023.
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 | 24997 | 0 | 0 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space.
31 | Capital | 20772 | 8675 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Programming or Planning | Ben Bedock |  | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | 0 | 08/22/2023 Scope is currently being designed. Once complete, bidding process will begin.
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 400000 | 483440 | 441580 | 441580 | 404017 | 483440 | 0 | 0 | 0 | 0 | 08/22/2023 First stage of roof installation is complete. Roof rock installation will be completed over Thanksgiving break.
33 | Operating | 20811 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Programming or Planning | Ben Bedock | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 09/06/2023: Structural engineer has been contacted and working on scheduling meeting to discuss the proposed scope and the needs of the project.
34 | Operating | 20831 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Not Started | Sean Rewers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New project for engineering study.
35 | Operating | 20832 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Design | Sean Rewers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New project for engineering study.
36 | Operating | 20833 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Not Started | Sean Rewers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New project for engineering study.
37 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Design | Sean Rewers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | New project for engineering study.
[11 empty] | 28754242.76 | 13356626.76 | 11150804.49 | 11174250.49 | 8062976.82 | 8797286.26 | 1028900 | 6651237.5 | 7680137.5 | 0
[16 empty] | TRUE | TRUE
Projects to be added
[8 empty] | Godchaux - replace roof [Ben] - wait until after HVAC project completed, FY25 |  |  | Collections |  |  |  |  | 9364499 |  | Carryforward | 567212.74
[8 empty] | SC7 - Roof replacement (CUI / Stevenson), FY25 | [9 empty] | Collections | 11029283.29
[8 empty] | Frist - replace roof (small section over stairwell) - waiting for eB # |  |  | Transferred |  |  |  |  | 8797286.26 |  |  | 11596496.03
[8 empty] | Projects to be discussed |  |  | Remaining |  |  |  |  | 567212.74 |  | Transferred | 1028900
[8 empty] | One Magnolia - elevator modernization (2024)? | [9 empty] | To be moved | 6651237.5
[8 empty] | Vaughn - roof, (phase 2) - summer 2024? | [10 empty] | 7680137.5
[18 empty] | Remaining | 3916358.53
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will potentially include roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordinating with EHS, may change direction.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10085 | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 |  | 17500 | 9364499
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy | 1216485.5 |  | 1216485.5
| 3 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 4900 |  | 4900
| 4 | 20179 | Law School | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Hans Mooy | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 483440 |  | 483440
[7 empty] | 8797286.26 | 0 | 8797286.26 |  | 567212.74
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 0 | TBD | TBD | 11029283.29
| 2 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 0 | 3730137.5 | 3730137.5
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 1028900 | 0 | 1028900
| 4 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 0 | 35000 | 35000
| 5 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 0 | 35000 | 35000
| 6 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 0 | TBD | TBD
| 7 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Hans Mooy | 0 | 1339500 | 1339500
| 8 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 0 | 1476600 | 1476600
| 9 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Jay Surprenant | 0 | 35000 | 35000
| 10 | 20772 | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Programming or Planning | Ben Bedock | 0 | TBD | TBD
| 11 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Not Started | Sean Rewers | 0 | 0 | 0
| 12 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Design | Sean Rewers | 0 | 0 | 0
| 13 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Not Started | Sean Rewers | 0 | 0 | 0
| 14 | 20834 | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Design | Sean Rewers | 0 | 0 | 0
Prior Year Carryforward
567212.74
Available Funds
[7 empty] | 1028900 | 6651237.5 | 7680137.5 | 11596496.03 | 3916358.53
FY 2025 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 0
| 2 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy |  | TBD | TBD
| 3 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  | TBD | TBD
| 4 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy |  | TBD | TBD
Prior Year Carryforward
0
Available Funds
[7 empty] | 0 | 0 | 0 |  | 0

## Summary_by Phase
Facility Renewal Program: Summary by Project Phase
Row Labels | Actual Costs | FY23 FRP Cash | FY24 FRP Cash
Construction | 3076761.59 | 3253240.5 | 1028900
Benson Old Central - Replace Soffit and Doors | 85500 | 125875 | 0
Bryan Building - Swing Space Renovation - A&S Planning | 416873.11 | 81100 | 1028900
Buttrick Hall - 3rd Floor Inequality Renovations | 482034.33 | 96166 | 0
Divinity - AHU 5N (5 & 6) Replacement | 100186.22 | 69862.5 | 0
Law School - Sections 1, 2, & 3 Roof Replacement | 404017 | 483440 | 0
MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 138257.52 | 160500 | 0
MRB III - Steam Coil Replacement | 166360 | 218202 | 0
Owen - Roof Replacement (Third Level) | 24150 | 300000 | 0
SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 73823.77 | 79623 | 0
Wyatt Center - Roof Replacement | 823000 | 1232681 | 0
Wyatt Center - VAV Replacement | 362559.64 | 405791 | 0
Design | 340221.21 | 1159143 | 0
1025 16th Avenue - Mechanical and Electrical Upgrades | 0 | 146500 | 0
Blair School of Music - Air Handling Unit Replacement | 185191.21 | 223000 | 0
Blair School of Music - Steam Line | 12000 | 23400 | 0
Divinity - AHU 1N (1&3) Replacement with Benton | 12712.5 | 26500 | 0
Godchaux Hall - HVAC Upgrade | 62100 | 4900 | 0
Keck FEL - Mechanical Upgrades | 47010 | 206500 | 0
SC5 - Chemical Discharge Replacement | 0 | 499093 | 0
Six Magnolia Circle - Foundation Repairs | 0 | 0 | 0
Wilson Hall - Fire Alarm Replacement | 21207.5 | 29250 | 0
Wilson Hall - HVAC Replacement | 0 | 0 | 0
Wyatt Center - HVAC Upgrades - Engineering Study | 0 | 0 | 0
Finalized | 35472 | 42497 | 0
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
SC4 - Interstitial Space HVAC Modifications | 17972 | 24997 | 0
Financial Closeout | 1212059.54 | 1216485.5 | 0
MRB III - 4th Floor - Replace Controls (Phase 2) | 1212059.54 | 1216485.5 | 0
Not Started | 0 | 0 | 0
Keck FEL - Roof Replacement | 0 | 0 | 0
SC5 - HVAC Replacement | 0 | 0 | 0
SC6 - HVAC Upgrades - Feasibility Study | 0 | 0 | 0
Programming or Planning | 0 | 0 | 0
One Magnolia Circle - Retaining Wall Repair | 0 | 0 | 0
Owen - Roof Replacement (Slate Portion) | 0 | 0 | 0
Warranty or Construction Closeout | 3398462.48 | 3125920.26 | 0
Blair School of Music - Elevator #3 Modernization | 274975 | 327890 | 0
Jesup - Roof Replacement | 412000 | 79415.5 | 0
Law School - Fire Alarm System Replacement | 1352423.14 | 722694.5 | 0
Peabody Administration - Envelope Repairs | 175193.4 | 630554 | 0
SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 670650.68 | 781870 | 0
Wyatt Center - Elevator #2 Modernization | 205444 | 239341 | 0
Wyatt Center - Window Replacement | 307776.26 | 344155.26 | 0
Grand Total | 8062976.82 | 8797286.26 | 1028900

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 22000 | 17500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 0

## 10098
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Financial Closeout | Hans Mooy | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | Total transfers from FRP cash |  |  | 1216485.5
|  |  |  | Balance |  |  | 0

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 62100
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | Total transfers from FRP cash |  |  | 4900
|  |  |  | Balance |  |  | 0

## 20179
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
|  |  |  | Total transfers from FRP cash |  |  | 722694.5
|  |  |  | Balance |  |  | 0

## 20336
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Warranty or Construction Closeout | Ben Bedock | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | Total transfers from FRP cash |  |  | 327890
|  |  |  | Balance |  |  | 0

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 139640
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
139640
|  |  |  | Total transfers from FRP cash |  |  | 69862.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2790000
[8 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
2790000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Warranty or Construction Closeout | Ben Bedock | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
456850
|  |  |  | Total transfers from FRP cash |  |  | 79415.5
|  |  |  | Balance |  |  | 0

## 20506
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Warranty or Construction Closeout | Ben Bedock | 344155.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | Total transfers from FRP cash |  |  | 344155.26
|  |  |  | Balance |  |  | 0

## 20562
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | Total transfers from FRP cash |  |  | 405791
|  |  |  | Balance |  |  | 0

## 20566
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Warranty or Construction Closeout | Ben Bedock | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | Total transfers from FRP cash |  |  | 781870
|  |  |  | Balance |  |  | 0

## 20573
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | Total transfers from FRP cash |  |  | 1232681
|  |  |  | Balance |  |  | 0

## 20574
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | Total transfers from FRP cash |  |  | 218202
|  |  |  | Balance |  |  | 0

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | Total transfers from FRP cash |  |  | 223000
|  |  |  | Balance |  |  | 0

## 20644
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Warranty or Construction Closeout | Ben Bedock | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | Total transfers from FRP cash |  |  | 630554
|  |  |  | Balance |  |  | 0

## 20645
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | Total transfers from FRP cash |  |  | 125875
|  |  |  | Balance |  |  | 0

## 20667
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 206500
|  |  |  | Balance |  |  | 0

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | Total transfers from FRP cash |  |  | 29250
|  |  |  | Balance |  |  | 0

## 20700
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | Total transfers from FRP cash |  |  | 79623
|  |  |  | Balance |  |  | 0

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC5 - Chemical Discharge Replacement | Design | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Warranty or Construction Closeout | Ben Bedock | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | Total transfers from FRP cash |  |  | 239341
|  |  |  | Balance |  |  | 0

## 20718
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Hans Mooy | 160500
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | Total transfers from FRP cash |  |  | 160500
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line | Design | Hans Mooy | 23400
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | Total transfers from FRP cash |  |  | 23400
|  |  |  | Balance |  |  | 0

## 20735
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | Total transfers from FRP cash |  |  | 300000
|  |  |  | Balance |  |  | 0

## 20771
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 24997
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | Total transfers from FRP cash |  |  | 24997
|  |  |  | Balance |  |  | 0

## 20792
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 483440
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | Total transfers from FRP cash |  |  | 483440
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 11029283.29 | tbd | 0
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| Total Uses | 1028900
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 10567596.03

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.