## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2023-10-03
Total program - FY23 |  |  | (1)
School | GSF | Contribution | Transferred FRP | Contribution vs. Estimated
Arts & Science | 1075461.7321 | 3663826 | 2276289.625 | 1387536.375
Blair | 121421.4269 | 413652 | 574290 | -160638
Divinity | 57814.7309 | 196960 | 96362.5 | 100597.5
Engineering | 537962.3327 | 1832701 | 353000 | 1479701
Law | 120155.4846 | 409339 | 1206134.5 | -796795.5
SOM Basic Sciences | 280022.3999 | 953965 | 1036871.875 | -82906.875
Nursing | 106166.7 | 361683 | 4900 | 356783
Owen | 59008.3617 | 201027 | 300000 | -98973
Peabody | 390796.8848 | 1331346 | 2949437.76 | -1618091.76
| 2748810.0535 | 9364499 | 8797286.26 | 567212.74
Total program - FY24 |  |  | (1)
School | GSF | Contribution | Estimated FRP | Contribution vs. Estimated
Arts & Science | 1059147 | 4204813.59 | 1575679 | 2629134.59
Blair | 121421 | 482041.37 | 1476600 | -994558.63
Divinity | 58263 | 231304.11 | 3660360 | -3429055.89
Engineering | 552478 | 2193337.66 | 0 | 2193337.66
Law | 120155 | 477015.35 | 0 | 477015.35
SOM Basic Sciences | 265674 | 1054725.78 | 870675 | 184050.78
Nursing | 105746 | 419811.62 | 11500 | 408311.62
Owen | 99140 | 393585.8 | 0 | 393585.8
Peabody | 396133 | 1572648.01 | 0 | 1572648.01
| 2748810.0535 | 11029283.29 | 7594814 | 3434469.29
(1) - estimated FRP indicates expected funding to be transferred back to the school from FRP program funds. Please note, facility renewal projects may span multiple fiscal years, as such projects may receive funding from multiple fiscal years.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2023-10-03
| Projects |  |  |  | (1) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP | Estimated FY24 FRP
1 | Finalized | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
2 | Financial Closeout | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | 0
3 | Design | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 0 | 4900 | 11500
4 | Warranty or Construction Closeout | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0
5 | Warranty or Construction Closeout | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | 0
6 | Construction | 20431 | Divinity | Divinity - AHU 5N (5 & 6) Replacement | 3800000 | 69862.5 | 3660360
7 | Construction | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2900000 | 81100 | 1028900
8 | Design | 20489 | Divinity | Divinity - AHU 1N (1&3) Replacement with Benton | 4650000 | 26500 | 0
9 | Financial Closeout | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | 0
10 | Financial Closeout | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | 0
11 | Construction | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | 0
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0
13 | Warranty or Construction Closeout | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | 0
14 | Construction | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | 0
15 | Construction | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | 0
16 | Design | 20577 | Blair | Blair School of Music - Air Handling Unit Replacement | 4500000 | 223000 | 0
17 | Warranty or Construction Closeout | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | 0
18 | Construction | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | 0
19 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 0 | 146500 | 0
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | 0
21 | Design | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 0 | 29250 | 0
22 | Construction | 20700 | Arts & Science | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 5954
23 | Design | 20701 | Arts & Science | SC5 - Chemical Discharge Replacement | 500000 | 499093 | 0
24 | Warranty or Construction Closeout | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | 0
25 | Warranty or Construction Closeout | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0
26 | Construction | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1500000 | 160500 | 1339500
27 | Bidding | 20724 | Blair | Blair School of Music - Steam Line | 1500000 | 23400 | 1476600
28 | Construction | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | 0
29 | Design | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 0 | 0 | 0
30 | Finalized | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | 0
31 | Bidding | 20772 | Owen | Owen - Roof Replacement (Slate Portion) | 0 | 0 | 0
32 | Construction | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | 0
33 | Design | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 24000
34 | Design | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 0 | 0 | 24000
35 | Design | 20833 | Arts & Science | SC5 - HVAC Replacement | 24000 | 0 | 24000
36 | Design | 20834 | Peabody | Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0 | 0
[5 empty] | 28732242.76 | 8797286.26 | 7594814
(1) - estimated total budget represents the best rough order of magnitude for total project costs.
(2) - estimated FYxx FRP indicates expected funding to be transferred back to the school from FRP program funds collected during FYxx.

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
12000 - Arts and Science: Office of the Dean | 229875 | 229498
Construction | 205875 | 205498
Benson Old Central - Replace Soffit and Doors | 125875 | 125875
SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623
Design | 24000 | 24000
Wilson Hall - HVAC Replacement | 24000 | 24000
Not Started |  | 0
SC5 - HVAC Replacement |  | 0
SC6 - HVAC Upgrades - Feasibility Study |  | 0
21000 - Peabody College: Office of the Dean |  | 0
Design |  | 0
Six Magnolia Circle - Foundation Repairs |  | 0
Wyatt Center - HVAC Upgrades - Engineering Study |  | 0
20000 - Owen: Office of the Dean | 300000 | 300000
Construction | 300000 | 300000
Owen - Roof Replacement (Third Level) | 300000 | 300000
Grand Total | 529875 | 529498
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 estimated FRP funding | MRB III Adj | FY24 revised estimated FRP | Contribution vs. FY24 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 1.1069 | 0.46882 | 1.5757 | 2.6291
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.4766 |  | 1.4766 | -0.99456
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.6604 |  | 3.6604 | -3.4291
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0 |  | 0 | 2.1933
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0 |  | 0 | 0.47702
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | 1.3395 | -0.46882 | 0.87067 | 0.18405
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0.0115 |  | 0.0115 | 0.40831
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 0 |  | 0 | 0.39359
Peabody | 390796.8848 | 1.3313 | 2.9494 |  | 2.9494 | -1.6181 | 1.5726 | 0 |  | 0 | 1.5726
| 2748810.0535 | 9.3645 | 8.7973 |  | 8.7973 | 0.56721 | 11.0293 | 7.5948 |  | 7.5948 | 3.4345
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24
|  | MRB III BIO/SCI | 1595187.5 |  |  |  |  | 1339500
|  | A&S | 558315.625 |  |  |  |  | 468825
|  | SOM | 1036871.875 |  |  |  |  | 870675
|  |  | 1595187.5 |  |  |  |  | 1339500

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25
|  | 3.41 |  |  | 3.97 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78 | SOM Basic Sciences | 315635.413 | 1432984.7751
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62 | Nursing | 105746.41 | 480088.7014
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623
Anticipated spend |  | 7594814 | Anticipated spend |  | 2816100 | Anticipated spend |  | 0
Remaining funds |  | 1769685 | Remaining funds |  | 8213183.29 | Remaining funds |  | 12857284.4623

## Project Status
Facility Renewal Program: Projects | [15 empty] | JE LOG_FY23'!A1 |  |  | JE LOG_FY24'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY24 FRP Estimated | FY24 FRP Total Contribution | FY25 FRP Estimated | Project status update
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 17500 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout.
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Financial Closeout | Hans Mooy | 1216485.5 | 1216485.5 | 1212059.54 | 1212059.54 | 1212059.54 | 1216485.5 | 0 | 0 | 0 | 0 | 08/22/2023 project complete
3 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 73600 | 62100 | 73600 | 62100 | 4900 | 11500 | TBD | 11500 | TBD | 09/27/2023 We are awaiting a PO for design engineers drawing set and commissioning. There was a lot of back and forth on the contract end date which had caused delays.
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | Law School | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 | 722694.5 | 0 | 0 | 0 | 0 | 09/22/2023 work complete
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Warranty or Construction Closeout | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 276775 | 327890 | 0 | 0 | 0 | 0 | 09/22/2023 Primary construction is complete. Punchlist items are 95% complete. Appropriate door handle for the new mechanical room is ordered and will be installed upon arrival.
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 3800000 | 3800000 | 126225 | 126225 | 101113.72 | 69862.5 | 3660360 | 0 | 3660360 | 0 | 09/27/2023 Construction Scheduled to Start 11/15/23
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2900000 | 2790000 | 1870106.53 | 1870106.53 | 971198.11 | 81100 | 1028900 | 0 | 1028900 | 0 | 08/22/2023 The interior fitout was completed on August 14th and A&S is actively moving into the building. DPR is addressing items on the punchlist. Mechanical units and partial roof replacement are scheduled to be done in December 2023 and January 2024.
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 4650000 | 26500 | 15895 | 15895 | 14407.5 | 26500 | 0 | 0 | 0 | TBD | 09/27/2023 Reviewed and revised project budget. Facility renewal has posted the budget....for FY 25 work.
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Financial Closeout | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 | 79415.5 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared.
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Financial Closeout | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 | 344155.26 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared.
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 | 405791 | 0 | 0 | 0 | 0 | 09/27/2023 All equipment has been installed and we are awaiting scheduling of HVAC testing and balancing. After that project will be complete.
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 03/24/2023 Working with appropriate parties to determine scope of work.
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Warranty or Construction Closeout | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 707150.68 | 781870 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared.
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 823000 | 1232681 | 0 | 0 | 0 | 0 | 09/22/2023 Final crane lift is scheduled for 09/23/2023. This is to install the final metal panels. Once finished, project will be punched out and marked complete.
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 166360 | 218202 | 0 | 0 | 0 | 0 | 09/27/2023 We are awaiting starters for the pumps and some JCI controls install. Controls and starters will be installed at the same time, Anderson will have insulation installed and project will be wrapped up.
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 4500000 | 223000 | 220566.21 | 220566.21 | 185191.21 | 223000 | 0 | 0 | 0 | TBD | 05/22/2023 on hold
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Warranty or Construction Closeout | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 175193.4 | 630554 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared.
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875 | 125875 | 112250 | 112250 | 85500 | 125875 | 0 | 0 | 0 | 0 | 09/22/2023 Door installation is scheduled for 10/19/2023. Once door is complete, project will be finished and ready to be closed.
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 146500 | 146500 | 146500 | 0 | 146500 | 0 | TBD | 0 | 0 | 09/27/2023 We are expecting our study back from Envision in early October, which will give us an analysis of the different types of systems we can install in the building. After review we will make a selection and begin design work.
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 206500 | 206500 | 206500 | 47010 | 206500 | 0 | TBD | 0 | 0 | 10/02/2023 Design drawings have been completed to a point where pre-construction can start. We will be getting Sylvan involved to start this effort.
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | 29250 | 29250 | 29250 | 21207.5 | 29250 | 0 | TBD | 0 | 0 | 09/27/2023 We have a final CD review at the end of September and will put this out to bid in October.
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 73823.77 | 79623 | 5954 | 0 | 5954 | 0 | 09/27/2023 Awaiting a CO for steam traps. Once the steam traps are installed we will have a final test of the lines and install insulation. This is the final piece of this project.
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - Chemical Discharge Replacement | Design | Sean Rewers | 500000 | 499093 | 18000 | 18000 | 0 | 499093 | 0 | 0 | 0 | 0 | 09/27/2023 Design engineers have almost completed their study of the needs of the building. We expect this study back in early October for review. This study will give us the size and scope of work for the project, and we will work with our awarded bidder to price out the project.
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Warranty or Construction Closeout | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 207769 | 239341 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared.
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Warranty or Construction Closeout | Erin Fry | 715000 | 715000 | 622431.2 | 625201.2 | 482034.33 | 96166 | 0 | 0 | 0 | 0 | 09/26/2023 Construction complete. CA for building signage started. Once signage is installed and all invoices have been paid, the financial closeout process will be started.
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Hans Mooy | 1500000 | 160500 | 155232.52 | 155232.52 | 138257.52 | 160500 | 0 | 1339500 | 1339500 | 0 | 09/27/2023 On Hold
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Bidding | Hans Mooy | 1500000 | 23400 | 21480 | 21480 | 12000 | 23400 | 0 | 1476600 | 1476600 | 0 | 09/27/2023 Waiting for final budget from FM Sylvan and Chancellor memo. Interior work to begin 05/2024.
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 260350 | 300000 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared.
29 | Operating | 20767 | 8673 |  | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Jay Surprenant |  | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | 0 | 08/22/2023 Project will start construction in winter 2023.
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 | 24997 | 0 | 0 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space.
31 | Capital | 20772 | 8675 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Bidding | Ben Bedock |  | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | 0 | 09/22/2023 Project currently out to bid. Bids are due in early October.
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 400000 | 483440 | 441580 | 441580 | 404017 | 483440 | 0 | 0 | 0 | 0 | 09/22/2023 Primary roof installation has been completed. Roof is currently curing until the Thanksgiving break to where we will flood the roof and apply the stone in areas that are needed. Drain lines to be cleared or replaced, currently being evaluated as to which route to go. Drains work, but are very slow.
33 | Operating | 20831 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Design | Sean Rewers | 24000 | 24000 | 0 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0 | 10/02/2023 Study has started
34 | Operating | 20832 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Design | Sean Rewers |  | 24000 | 24000 | 24000 | 0 | 0 | 24000 | 0 | 24000 | 0 | 10/02/2023 We have minor changes to make to the drawing set, but will be putting this out to bid in October.
35 | Operating | 20833 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Design | Sean Rewers | 24000 | 24000 | 0 | 0 | 0 | 0 | 24000 | 0 | 24000 | 0 | 10/02/2023 Study has started
36 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Design | Sean Rewers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 09/27/2023 This project is on hold until October. We are awaiting approval from the CBO for initial funding which will be repaid by the FRP.
[11 empty] | 28732242.76 | 17106440.76 | 11210003.49 | 11248273.49 | 8896749.32 | 8797286.26 | 4778714 | 2816100 | 7594814 | 0
[16 empty] | TRUE | TRUE
Projects to be added
[8 empty] | Godchaux - replace roof [Ben] - wait until after HVAC project completed, FY25 |  |  | Collections |  |  |  |  | 9364499 |  | Carryforward | 567212.74
[8 empty] | SC7 - Roof replacement (CUI / Stevenson), FY25 | [9 empty] | Collections | 11029283.29
[8 empty] | Frist - replace roof (small section over stairwell) - waiting for eB # |  |  | Transferred |  |  |  |  | 8797286.26 |  |  | 11596496.03
[8 empty] | Projects to be discussed |  |  | Remaining |  |  |  |  | 567212.74 |  | Transferred | 4778714
[8 empty] | One Magnolia - elevator modernization (2024)? | [9 empty] | To be moved | 2816100
[8 empty] | Vaughn - roof, (phase 2) - summer 2024? | [10 empty] | 7594814
[18 empty] | Remaining | 4001682.03
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will potentially include roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordinating with EHS, may change direction.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10085 | One Magnolia Circle | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 |  | 17500 | 9364499
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy | 1216485.5 |  | 1216485.5
| 3 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 4900 |  | 4900
| 4 | 20179 | Law School | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Hans Mooy | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 483440 |  | 483440
[7 empty] | 8797286.26 | 0 | 8797286.26 |  | 567212.74
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 11500 | TBD | TBD | 11029283.29
| 2 | 20431 | DIVINITY | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 3660360 | 0 | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 1028900 | 0 | 1028900
| 4 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 0 | TBD | TBD
| 5 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 0 | TBD | TBD
| 6 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 0 | TBD | TBD
| 7 | 20700 | SC CHEMISTRY | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 5954 | 0 | 5954
| 8 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Hans Mooy | 0 | 1339500 | 1339500
| 9 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Bidding | Hans Mooy | 0 | 1476600 | 1476600
| 10 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Jay Surprenant | 0 | TBD | TBD
| 11 | 20772 | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Bidding | Ben Bedock | 0 | TBD | TBD
| 12 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Design | Sean Rewers | 24000 | 0 | 24000
| 13 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Design | Sean Rewers | 24000 | 0 | 24000
| 14 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Design | Sean Rewers | 24000 | 0 | 24000
| 15 | 20834 | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Design | Sean Rewers | 0 | 0 | 0
Prior Year Carryforward
567212.74
Available Funds
[7 empty] | 4778714 | 2816100 | 7583314 | 11596496.03 | 4013182.03
FY 2025 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | Godchaux Hall | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 12857284.4623
| 2 | 20489 | DIVINITY | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy |  | TBD | TBD
| 3 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  | TBD | TBD
| 4 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy |  | TBD | TBD
Prior Year Carryforward
0
Available Funds
[7 empty] | 0 | 0 | 0 |  | 12857284.4623

## Summary_by Phase
Facility Renewal Program: Summary by Project Phase
Row Labels | Actual Costs | FY23 FRP Cash | FY24 FRP Cash
Construction | 3076761.59 | 3259194.5 | 1028900
Benson Old Central - Replace Soffit and Doors | 85500 | 125875 | 0
Bryan Building - Swing Space Renovation - A&S Planning | 416873.11 | 81100 | 1028900
Buttrick Hall - 3rd Floor Inequality Renovations | 482034.33 | 96166 | 0
Divinity - AHU 5N (5 & 6) Replacement | 100186.22 | 69862.5 | 0
Law School - Sections 1, 2, & 3 Roof Replacement | 404017 | 483440 | 0
MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 138257.52 | 160500 | 0
MRB III - Steam Coil Replacement | 166360 | 218202 | 0
Owen - Roof Replacement (Third Level) | 24150 | 300000 | 0
SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 73823.77 | 85577 | 0
Wyatt Center - Roof Replacement | 823000 | 1232681 | 0
Wyatt Center - VAV Replacement | 362559.64 | 405791 | 0
Design | 340221.21 | 1159143 | 0
1025 16th Avenue - Mechanical and Electrical Upgrades | 0 | 146500 | 0
Blair School of Music - Air Handling Unit Replacement | 185191.21 | 223000 | 0
Blair School of Music - Steam Line | 12000 | 23400 | 0
Divinity - AHU 1N (1&3) Replacement with Benton | 12712.5 | 26500 | 0
Godchaux Hall - HVAC Upgrade | 62100 | 4900 | 0
Keck FEL - Mechanical Upgrades | 47010 | 206500 | 0
SC5 - Chemical Discharge Replacement | 0 | 499093 | 0
Six Magnolia Circle - Foundation Repairs | 0 | 0 | 0
Wilson Hall - Fire Alarm Replacement | 21207.5 | 29250 | 0
Wilson Hall - HVAC Replacement | 0 | 0 | 0
Wyatt Center - HVAC Upgrades - Engineering Study | 0 | 0 | 0
Finalized | 35472 | 42497 | 0
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
SC4 - Interstitial Space HVAC Modifications | 17972 | 24997 | 0
Financial Closeout | 1212059.54 | 1216485.5 | 0
MRB III - 4th Floor - Replace Controls (Phase 2) | 1212059.54 | 1216485.5 | 0
Not Started | 0 | 0 | 0
Keck FEL - Roof Replacement | 0 | 0 | 0
SC5 - HVAC Replacement | 0 | 0 | 0
SC6 - HVAC Upgrades - Feasibility Study | 0 | 0 | 0
Programming or Planning | 0 | 0 | 0
Owen - Roof Replacement (Slate Portion) | 0 | 0 | 0
Warranty or Construction Closeout | 3398462.48 | 3125920.26 | 0
Blair School of Music - Elevator #3 Modernization | 274975 | 327890 | 0
Jesup - Roof Replacement | 412000 | 79415.5 | 0
Law School - Fire Alarm System Replacement | 1352423.14 | 722694.5 | 0
Peabody Administration - Envelope Repairs | 175193.4 | 630554 | 0
SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 670650.68 | 781870 | 0
Wyatt Center - Elevator #2 Modernization | 205444 | 239341 | 0
Wyatt Center - Window Replacement | 307776.26 | 344155.26 | 0
Grand Total | 8062976.82 | 8803240.26 | 1028900

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 22000 | 17500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 0

## 10098
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Financial Closeout | Hans Mooy | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | Total transfers from FRP cash |  |  | 1216485.5
|  |  |  | Balance |  |  | 0

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 73600
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 4900
|  |  |  | Balance |  |  | 11500

## 20179
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
|  |  |  | Total transfers from FRP cash |  |  | 722694.5
|  |  |  | Balance |  |  | 0

## 20336
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Warranty or Construction Closeout | Ben Bedock | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | Total transfers from FRP cash |  |  | 327890
|  |  |  | Balance |  |  | 0

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity - AHU 5N (5 & 6) Replacement | Construction | Hans Mooy | 3800000
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360 | All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
139640
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 3660360

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2790000
[8 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
2790000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity - AHU 1N (1&3) Replacement with Benton | Design | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Financial Closeout | Ben Bedock | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
456850
|  |  |  | Total transfers from FRP cash |  |  | 79415.5
|  |  |  | Balance |  |  | 0

## 20506
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Financial Closeout | Ben Bedock | 344155.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | Total transfers from FRP cash |  |  | 344155.26
|  |  |  | Balance |  |  | 0

## 20562
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | Total transfers from FRP cash |  |  | 405791
|  |  |  | Balance |  |  | 0

## 20566
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Warranty or Construction Closeout | Ben Bedock | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | Total transfers from FRP cash |  |  | 781870
|  |  |  | Balance |  |  | 0

## 20573
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | Total transfers from FRP cash |  |  | 1232681
|  |  |  | Balance |  |  | 0

## 20574
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | Total transfers from FRP cash |  |  | 218202
|  |  |  | Balance |  |  | 0

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | Total transfers from FRP cash |  |  | 223000
|  |  |  | Balance |  |  | 0

## 20644
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Warranty or Construction Closeout | Ben Bedock | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | Total transfers from FRP cash |  |  | 630554
|  |  |  | Balance |  |  | 0

## 20645
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | Total transfers from FRP cash |  |  | 125875
|  |  |  | Balance |  |  | 0

## 20667
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 206500
|  |  |  | Balance |  |  | 0

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | Total transfers from FRP cash |  |  | 29250
|  |  |  | Balance |  |  | 0

## 20700
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 85577
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | 0

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC5 - Chemical Discharge Replacement | Design | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Warranty or Construction Closeout | Ben Bedock | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | Total transfers from FRP cash |  |  | 239341
|  |  |  | Balance |  |  | 0

## 20718
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Warranty or Construction Closeout | Erin Fry | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Hans Mooy | 160500
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | Total transfers from FRP cash |  |  | 160500
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line | Bidding | Hans Mooy | 23400
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | Total transfers from FRP cash |  |  | 23400
|  |  |  | Balance |  |  | 0

## 20735
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | Total transfers from FRP cash |  |  | 300000
|  |  |  | Balance |  |  | 0

## 20771
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 24997
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | Total transfers from FRP cash |  |  | 24997
|  |  |  | Balance |  |  | 0

## 20792
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 483440
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | Total transfers from FRP cash |  |  | 483440
|  |  |  | Balance |  |  | 0

## 20831
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20831 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Design | Sean Rewers | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20832 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Design | Sean Rewers | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20833 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement | Design | Sean Rewers | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 11029283.29 | tbd | 0
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| Total Uses | 4778714
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 6817782.03

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.