## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2023-11-02
Total program - FY23
School | GSF | Contribution to FRP | Funded Projects | Funded Projects vs. Contribution
Arts & Science | 1075461.7321 | 3663826 | 2276289.625 | -1387536.375
Blair | 121421.4269 | 413652 | 574290 | 160638
Divinity | 57814.7309 | 196960 | 96362.5 | -100597.5
Engineering | 537962.3327 | 1832701 | 353000 | -1479701
Law | 120155.4846 | 409339 | 1206134.5 | 796795.5
SOM Basic Sciences | 280022.3999 | 953965 | 1036871.875 | 82906.875
Nursing | 106166.7 | 361683 | 4900 | -356783
Owen | 59008.3617 | 201027 | 300000 | 98973
Peabody | 390796.8848 | 1331346 | 2949437.76 | 1618091.76
| 2748810.0535 | 9364499 | 8797286.26 | -567212.74
Total program - FY24 |  |  | (1)
School | GSF | Contribution to FRP | Estimed Funded Projects | Est. Funded Projects vs. Cont.
Arts & Science | 1059147 | 4204813.59 | 1607154 | -2597659.59
Blair | 121421 | 482041.37 | 1964100 | 1482058.63
Divinity | 58263 | 231304.11 | 3660360 | 3429055.89
Engineering | 552478 | 2193337.66 | 24933 | -2168404.66
Law | 120155 | 477015.35 | 0 | -477015.35
SOM Basic Sciences | 265674 | 1054725.78 | 942175 | -112550.78
Nursing | 105746 | 419811.62 | 611500 | 191688.38
Owen | 99140 | 393585.8 | 0 | -393585.8
Peabody | 396133 | 1572648.01 | -33629 | -1606277.01
| 2748810.0535 | 11029283.29 | 8776593 | -2252690.29
(1) - estimated funded projects is anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2023-11-02
| Projects |  |  |  | (1) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP Funding | Estimated Funding FY24 FRP
1 | Finalized | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
2 | Financial Closeout | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | 0
3 | Design | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 0 | 4900 | 600000
4 | Warranty or Construction Closeout | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0
5 | Warranty or Construction Closeout | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | 0
6 | Construction | 20431 | Divinity | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 69862.5 | 0
7 | Construction | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2900000 | 81100 | 0
8 | Not Started | 20489 | Divinity | Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | 4650000 | 26500 | 0
9 | Finalized | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | 0
10 | Finalized | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | 0
11 | Construction | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | 0
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0
13 | Warranty or Construction Closeout | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | 0
14 | Warranty or Construction Closeout | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | 0
15 | Construction | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | 0
16 | Design | 20577 | Blair | Blair School of Music - Air Handling Unit Replacement | 4500000 | 223000 | 0
17 | Financial Closeout | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | 0
18 | Construction | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | 0
19 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 0 | 146500 | TBD
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | TBD
21 | Design | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 0 | 29250 | TBD
22 | Construction | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 0
23 | Design | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0
24 | Warranty or Construction Closeout | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | 0
25 | Warranty or Construction Closeout | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0
26 | Construction | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500 | 1449500
27 | Construction | 20724 | Blair | Blair School of Music - Steam Line | 1987500 | 23400 | 1964100
28 | Warranty or Construction Closeout | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | 0
29 | Design | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 0 | 0 | 30000
30 | Finalized | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | 0
31 | Award | 20772 | Owen | Owen - Roof Replacement (Slate Portion) | 0 | 0 | 0
32 | Construction | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | 0
33 | Design | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 0
34 | Design | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 0 | 0 | 0
35 | Design | 20833 | Arts & Science | SC5 - HVAC Replacement | 24000 | 0 | 0
36 | Finalized | 20834 | Peabody | Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0 | 0
37 | Programming or Planning | 20857 | Peabody | One Magnolia Circle - Elevator Modernization | 0 | 0 | TBD
[5 empty] | 29329742.76 | 8797286.26 | 4043600
(1) - estimated total budget represents the best rough order of magnitude for total project costs.
(2) - FYxx FRP funding indicates anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
12000 - Arts and Science: Office of the Dean | 5175745 | 5123662
Construction | 3105875 | 3001452
Benson Old Central - Replace Soffit and Doors | 125875 | 125875
Bryan Building - Swing Space Renovation - A&S Planning | 2900000 | 2790000
SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 85577
Design | 548000 | 600343
SC5 - HVAC Replacement | 24000 | 24000
SC6 - HVAC Upgrades - Feasibility Study | 24000 | 24000
Wilson Hall - Fire Alarm Replacement |  | 29250
Wilson Hall - HVAC Replacement |  | 24000
SC-5 - Chemical Discharge Replacement | 500000 | 499093
Finalized | 25000 | 24997
SC4 - Interstitial Space HVAC Modifications | 25000 | 24997
Warranty or Construction Closeout | 1496870 | 1496870
Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 715000
SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870
13000 - Blair: Office of the Dean | 6815390 | 574290
Construction | 1987500 | 23400
Blair School of Music - Steam Line | 1987500 | 23400
Design | 4500000 | 223000
Blair School of Music - Air Handling Unit Replacement | 4500000 | 223000
Warranty or Construction Closeout | 327890 | 327890
Blair School of Music - Elevator #3 Modernization | 327890 | 327890
14000 - Divinity: Office of the Dean | 8450000 | 3826500
Construction | 3800000 | 3800000
Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 3800000
Not Started | 4650000 | 26500
Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | 4650000 | 26500
15000 - Engineering: Office of the Dean | 386000 | 377933
Design |  | 377933
1025 16th Avenue - Mechanical and Electrical Upgrades |  | 146500
Keck FEL - Mechanical Upgrades |  | 231433
Not Started | 386000 | 0
Keck FEL - Roof Replacement | 386000 | 0
17100 - Law: Business Affairs | 1845389 | 1928829
Construction | 400000 | 483440
Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440
Warranty or Construction Closeout | 1445389 | 1445389
Law School - Fire Alarm System Replacement | 1445389 | 1445389
18200 - Basic Sciences: Office of the Dean | 3044687.5 | 1595187.5
Construction | 1828202 | 378702
MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500
MRB III - Steam Coil Replacement | 218202 | 218202
Financial Closeout | 1216485.5 | 1216485.5
MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5
21000 - Peabody College: Office of the Dean | 3312531.26 | 3348972.26
Construction | 400000 | 405791
Wyatt Center - VAV Replacement | 400000 | 405791
Design |  | 0
Six Magnolia Circle - Foundation Repairs |  | 0
Finalized | 823505.26 | 823005.26
Jesup - Roof Replacement | 456850 | 456850
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000
Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0
Wyatt Center - Window Replacement | 344155.26 | 344155.26
Financial Closeout | 630554 | 630554
Peabody Administration - Envelope Repairs | 630554 | 630554
Programming or Planning |  | 17600
One Magnolia Circle - Elevator Modernization |  | 17600
Warranty or Construction Closeout | 1458472 | 1472022
Wyatt Center - Elevator #2 Modernization | 225791 | 239341
Wyatt Center - Roof Replacement | 1232681 | 1232681
19100 - Nursing: Business Affairs |  | 73600
Design |  | 73600
Godchaux Hall - HVAC Upgrade |  | 73600
20000 - Owen: Office of the Dean | 300000 | 300000
Warranty or Construction Closeout | 300000 | 300000
Owen - Roof Replacement (Third Level) | 300000 | 300000
Award |  | 0
Owen - Roof Replacement (Slate Portion) |  | 0
Grand Total | 29329742.76 | 17148973.76
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 estimated FRP funding | MRB III Adj | FY24 revised estimated FRP | Contribution vs. FY24 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 1.0998 | 0.50732 | 1.6072 | 2.5977
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.9641 |  | 1.9641 | -1.4821
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.6604 |  | 3.6604 | -3.4291
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0.024933 |  | 0.024933 | 2.1684
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0 |  | 0 | 0.47702
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | 1.4495 | -0.50732 | 0.94218 | 0.11255
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0.6115 |  | 0.6115 | -0.19169
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 0 |  | 0 | 0.39359
Peabody | 390796.8848 | 1.3313 | 2.9494 |  | 2.9494 | -1.6181 | 1.5726 | -0.033629 |  | -0.033629 | 1.6063
| 2748810.0535 | 9.3645 | 8.7973 |  | 8.7973 | 0.56721 | 11.0293 | 8.7766 |  | 8.7766 | 2.2527
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24
|  | MRB III BIO/SCI | 1595187.5 |  |  |  |  | 1449500
|  | A&S | 558315.625 |  |  |  |  | 507325
|  | SOM | 1036871.875 |  |  |  |  | 942175
|  |  | 1595187.5 |  |  |  |  | 1449500

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25
|  | 3.41 |  |  | 3.97 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78 | SOM Basic Sciences | 315635.413 | 1432984.7751
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62 | Nursing | 105746.41 | 480088.7014
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623
Anticipated spend |  | 8776593 | Anticipated spend |  | 4043600 | Anticipated spend |  | 0
Remaining funds |  | 587906 | Remaining funds |  | 6985683.29 | Remaining funds |  | 12857284.4623

## Project Status
Facility Renewal Program: Projects | [16 empty] | JE LOG_FY23'!A1 |  |  | JE LOG_FY24'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Current Contingency | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY24 FRP Estimated | FY24 FRP Total Contribution | FY25 FRP Estimated | FY26 FRP Estimated | Project status update | Check
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout. | 10085
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Financial Closeout | Hans Mooy | 1216485.5 | 1216485.5 | 1212059.54 | 1212059.54 | 1212059.54 | 0 | 1216485.5 | 0 | 0 | 0 | 0 | 0 | 08/22/2023 project complete | 10098
3 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 73600 | 73600 | 73600 | 62100 | 0 | 4900 | 11500 | 600000 | 611500 | TBD | 0 | 10/22/2023 We are still awaiting a phased drawing set. Engineer has gotten their PO for drawings and for commissioning. We will have a site walk with the building stakeholders in early November to get some scope of work info and decide of a bidding and construction schedule. | 10146
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 | 4425.96 | 722694.5 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 work is complete | 20179
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Warranty or Construction Closeout | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 276775 | 47290 | 327890 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20336
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy | 3800000 | 3800000 | 3400975 | 3314297.72 | 101803.72 | 126060 | 69862.5 | 3660360 | 0 | 3660360 | 0 | 0 | 10/23/2023 Work to commence late November 2023. | 20431
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2900000 | 2790000 | 1870177.96 | 1870177.96 | 1157068.54 | 604000 | 81100 | 1028900 | 0 | 1028900 | 0 | 0 | 11/01/2023 The interior fit out was completed in August and A&S is actively occupying the building. Mechanical units and partial roof replacement are scheduled to be done in December 2023 and January 2024. | 20478
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | Not Started | Hans Mooy | 4650000 | 26500 | 15895 | 15895 | 14407.5 | 3000 | 26500 | 0 | 0 | 0 | 0 | 3170000 | 10/23/2023 On Hold till FY26 | 20489
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 | 0 | 79415.5 | -44850 | 0 | -44850 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20497
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 | 0 | 344155.26 | -36379 | 0 | -36379 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20506
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 | 36256 | 405791 | 0 | 0 | 0 | 0 | 0 | 10/22/2023 Testing and balancing should be completed. We are awaiting a punch list from plant operations and the zone. We will walk the building at the end of October for punch list items. | 20562
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TBD | 0 | 03/24/2023 Working with appropriate parties to determine scope of work. | 20563
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Warranty or Construction Closeout | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 720686.68 | 55670 | 781870 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Card reader issue has been resolved. Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20566
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Warranty or Construction Closeout | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 1002114 | 111346 | 1232681 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Meeting with contractor on 10/23 to punch walk the roof. | 20573
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 166360 | 19837 | 218202 | 0 | 0 | 0 | 0 | 0 | 10/22/2023 Still awaiting starters for the pumps, then project will wrap up. | 20574
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 4500000 | 223000 | 220566.21 | 220566.21 | 185191.21 | 81 | 223000 | 0 | 0 | 0 | TBD | 0 | 05/22/2023 on hold | 20577
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Financial Closeout | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 569739 | 51915 | 630554 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20644
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875 | 125875 | 112250 | 112250 | 85500 | 11225 | 125875 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Front door installation completed over 10/19-10/20. Project is now complete. | 20645
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 146500 | 146500 | 146500 | 11500 | 0 | 146500 | 0 | TBD | 0 | TBD | 0 | 10/22/2023 We have our study completed and are awaiting pricing from Nashville Machine and IN2 electric. We will use those number and the study to determine which system we should install in the building. Depending on financing we should be able to get design completed and possibly award the project this fiscal year. If funding allows we can work on ordering equipment. | 20667
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 231433 | 231433 | 231433 | 49485 | 0 | 206500 | 24933 | TBD | 24933 | 0 | 0 | 10/22/2023 Pre-construction has begun and drawings are still in review. Some small items still need to be changed in the drawing set. Hope to have pricing in November and then we can start planning out construction schedule. | 20668
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | 29250 | 29250 | 29250 | 21207.5 | 0 | 29250 | 0 | TBD | 0 | 0 | 0 | 10/22/2023 Final drawing review has been completed and we are awaiting the final drawing set. Project will go out to bid in November. | 20698
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 73823.77 | 0 | 79623 | 5954 | 0 | 5954 | 0 | 0 | 10/22/2023 Steam traps have been received by FM Sylvan. They are completing installation, testing and insulation during the end of October. Hope to closeout the project in early November. | 20700
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Design | Sean Rewers | 500000 | 499093 | 18000 | 18000 | 0 | 20500 | 499093 | 0 | 0 | 0 | 0 | 0 | 10/22/2023 Study of the building has begun, we are awaiting a recommendation for the discharge system size from the study. | 20701
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Warranty or Construction Closeout | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 207769 | 27422 | 239341 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20702
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Warranty or Construction Closeout | Erin Fry | 715000 | 715000 | 625201.2 | 651554.6 | 482034.33 | 0 | 96166 | 0 | 0 | 0 | 0 | 0 | 10/30/2023 Construction complete. Once final invoice has been paid, the Financial Closeout process will be started. | 20718
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Andy Maddox | 1610000 | 160500 | 155232.52 | 155232.52 | 138257.52 | 4767 | 160500 | 0 | 1449500 | 1449500 | 0 | 0 | 10/23/2023 restart meeting to occur November 1, 2023 | 20723
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Construction | Hans Mooy | 1987500 | 23400 | 21480 | 21480 | 12000 | 0 | 23400 | 0 | 1964100 | 1964100 | 0 | 0 | 10/23/2023 Funding BAC being processed. | 20724
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Warranty or Construction Closeout | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 260350 | 18000 | 300000 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Project is complete. Contractor is working on punch list items. Once items complete, project is ready to close. | 20735
29 | Operating | 20767 | 8673 |  | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Jay Surprenant |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 10/30/2023 Still in design phase. | 20767
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 | 0 | 24997 | -7025 | 0 | -7025 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space. | 20771
31 | Capital | 20772 | 8675 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Award | Ben Bedock |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000000 | 0 | 10/23/2023 Bids have been received. Reviewing with appropriate parties to determine the next step. | 20772
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 400000 | 483440 | 442680 | 442680 | 405117 | 35760 | 483440 | 0 | 0 | 0 | 0 | 0 | 10/23/2023 Met with the contractor to discuss final stage of the project. Awaiting safety protocol from contractor to submit at FRC. | 20792
33 | Operating | 20831 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Design | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 0 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | 10/22/2023 Project study is currently underway. | 20831
34 | Operating | 20832 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Design | Sean Rewers |  | 24000 | 24000 | 24000 | 0 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | 10/22/2023 Project study is currently underway. | 20832
35 | Operating | 20833 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Design | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 0 | 0 | 0 | 24000 | 0 | 24000 | 0 | 0 | 10/22/2023 Project study is currently underway. | 20833
36 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Finalized | Sean Rewers | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 09/27/2023 This project is deferred indefinitely. | #N/A
37 | Capital | 20857 |  | CP_400227 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Programming or Planning | Ben Bedock |  | 17600 | 0 | 17600 | 0 | 0 | 0 | 17600 | TBD | 17600 | 0 | 0 | 10/23/2023 Pricing submitted for Lerch Bates to develop the scope of work. | 20857
[11 empty] | 29329742.76 | 17148973.76 | 14573127.92 | 14530404.04 | 9685580.35 | 1177554.96 | 8797286.26 | 4732993 | 4043600 | 8776593 | 3000000 | 3170000
[17 empty] | TRUE | TRUE
Projects to be added
[8 empty] | SC7 - Roof replacement (CUI / Stevenson), FY25 | [7 empty] | Collections | 9364499 |  | Carryforward | 567212.74
[8 empty] | Law School - Exterior Window Painting ~$250k --> Chris to do project intake | [10 empty] | Collections | 11029283.29
[8 empty] | SOM-NMR- Air compressors ~$80K, holding until FY25, if needed sooner SOM will fund - Chris to report back | [7 empty] | Transferred | 8797286.26 |  |  | 11596496.03
[8 empty] | Projects to be discussed | [7 empty] | Remaining | 567212.74 |  | Transferred | 4732993
[8 empty] | Vaughn - roof, (phase 2) - summer 2024 | [10 empty] | To be moved | 4043600
[8 empty] | Frist - replace roof (small section over stairwell) | [11 empty] | 8776593
Godchaux - replace roof [Ben] - wait until after HVAC project completed, FY25
[19 empty] | Remaining | 2819903.03
[10 empty] | Closeout contingency | [5 empty] | 316068.96
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Will potentially include roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on W11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project will be joint funded, FPR / Divinity + Dean of Students.
Note on I26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Coordinating with EHS, may change direction.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10085 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 |  | 17500 | 9364499
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy | 1216485.5 |  | 1216485.5
| 3 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 4900 |  | 4900
| 4 | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | Design | Hans Mooy | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Andy Maddox | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Design | Hans Mooy | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock | 483440 |  | 483440
[7 empty] | 8797286.26 | 0 | 8797286.26 |  | 567212.74
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 11500 | 600000 | 611500 | 11029283.29 |  | mid-Nov for cost estimates
| 2 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy | 3660360 | 0 | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 1028900 | 0 | 1028900
| 4 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 0 | TBD | TBD |  |  | early-Nov for cost estimates
| 5 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 24933 | TBD | TBD |  |  | early-Dec for cost estimates
| 6 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 0 | TBD | TBD |  |  | late-Nov for cost estimates
| 7 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 5954 | 0 | 5954
| 8 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Andy Maddox | 0 | 1449500 | 1449500 |  |  | waiting for SOM leadership to weigh in on timing
| 9 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line | Construction | Hans Mooy | 0 | 1964100 | 1964100 |  |  | memo in process
| 10 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Design | Jay Surprenant | 0 | 30000 | 30000
| 11 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Design | Sean Rewers | 24000 | 0 | 24000
| 12 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Design | Sean Rewers | 24000 | 0 | 24000
| 13 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Design | Sean Rewers | 24000 | 0 | 24000
| 14 | 20857 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Programming or Planning | Ben Bedock | 17600 | TBD | TBD |  |  | early-Jan for cost estimates
Prior Year Carryforward
567212.74
Available Funds
[7 empty] | 4821247 | 4043600 | 8822314 | 11596496.03 | 2774182.03
FY 2025 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | TBD | TBD | 12857284.4623
| 2 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  | TBD | TBD
| 3 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy |  | TBD | TBD
| 4 | 20772 | OWEN GRAD MGMT | Owen - Roof Replacement (Slate Portion) | Award | Ben Bedock |  | 3000000 | 3000000
Prior Year Carryforward
0
Available Funds
[7 empty] | 0 | 3000000 | 3000000 |  | 9857284.4623
FY 2026 |  | eBuilder | Building | Project | Phase | Manager | Transferred | Estimated | FRP Funding | FRP Collection | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | Not Started | Hans Mooy |  | 3170000 | 3170000 | 0
Prior Year Carryforward
0
Available Funds
[7 empty] | 0 | 3170000 | 3170000 |  | -3170000

## Summary_by Phase
Facility Renewal Program: Summary by Project Phase
Row Labels | Actual Costs | FY23 FRP Cash | FY24 FRP Cash
Construction | 2502490.19 | 1647793.5 | 4695214
Benson Old Central - Replace Soffit and Doors | 85500 | 125875 | 0
Blair School of Music - Steam Line | 12000 | 23400 | 0
Bryan Building - Swing Space Renovation - A&S Planning | 1157068.54 | 81100 | 1028900
Law School - Sections 1, 2, & 3 Roof Replacement | 405117 | 483440 | 0
MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 138257.52 | 160500 | 0
MRB III - Steam Coil Replacement | 166360 | 218202 | 0
Wyatt Center - VAV Replacement | 362559.64 | 405791 | 0
Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 101803.72 | 69862.5 | 3660360
SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 73823.77 | 79623 | 5954
Design | 329483.71 | 1109243 | 83500
1025 16th Avenue - Mechanical and Electrical Upgrades | 11500 | 146500 | 0
Blair School of Music - Air Handling Unit Replacement | 185191.21 | 223000 | 0
Godchaux Hall - HVAC Upgrade | 62100 | 4900 | 11500
Keck FEL - Mechanical Upgrades | 49485 | 206500 | 0
SC5 - HVAC Replacement | 0 | 0 | 24000
SC6 - HVAC Upgrades - Feasibility Study | 0 | 0 | 24000
Six Magnolia Circle - Foundation Repairs | 0 | 0 | 0
Wilson Hall - Fire Alarm Replacement | 21207.5 | 29250 | 0
Wilson Hall - HVAC Replacement | 0 | 0 | 24000
SC-5 - Chemical Discharge Replacement | 0 | 499093 | 0
Finalized | 755248.26 | 466067.76 | 0
Jesup - Roof Replacement | 412000 | 79415.5 | 0
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
SC4 - Interstitial Space HVAC Modifications | 17972 | 24997 | 0
Wyatt Center - HVAC Upgrades - Engineering Study | 0 | 0 | 0
Wyatt Center - Window Replacement | 307776.26 | 344155.26 | 0
Financial Closeout | 1781798.54 | 1847039.5 | 0
MRB III - 4th Floor - Replace Controls (Phase 2) | 1212059.54 | 1216485.5 | 0
Peabody Administration - Envelope Repairs | 569739 | 630554 | 0
Not Started | 14407.5 | 26500 | 0
Keck FEL - Roof Replacement | 0 | 0 | 0
Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | 14407.5 | 26500 | 0
Programming or Planning | 0 | 0
One Magnolia Circle - Elevator Modernization | 0 | 0
Warranty or Construction Closeout | 4302152.15 | 3700642.5 | 0
Blair School of Music - Elevator #3 Modernization | 276775 | 327890 | 0
Buttrick Hall - 3rd Floor Inequality Renovations | 482034.33 | 96166 | 0
Law School - Fire Alarm System Replacement | 1352423.14 | 722694.5 | 0
Owen - Roof Replacement (Third Level) | 260350 | 300000 | 0
SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 720686.68 | 781870 | 0
Wyatt Center - Elevator #2 Modernization | 207769 | 239341 | 0
Wyatt Center - Roof Replacement | 1002114 | 1232681 | 0
Award | 0 | 0 | 0
Owen - Roof Replacement (Slate Portion) | 0 | 0 | 0
Grand Total | 9685580.35 | 8797286.26 | 4778714

## 10085
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 22000 | 17500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 0

## 10098
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Financial Closeout | Hans Mooy | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | Total transfers from FRP cash |  |  | 1216485.5
|  |  |  | Balance |  |  | 0

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers | 73600
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 73600
|  |  |  | Balance |  |  | 0

## 20179
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
|  |  |  | Total transfers from FRP cash |  |  | 722694.5
|  |  |  | Balance |  |  | 0

## 20336
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Warranty or Construction Closeout | Ben Bedock | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | Total transfers from FRP cash |  |  | 327890
|  |  |  | Balance |  |  | 0

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy | 3800000
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360
All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
3800000
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Construction | Cathy Bartlett | 2790000
[8 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
2790000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (1/3) - Phase 2 with Benton | Not Started | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Finalized | Ben Bedock | 456850 | 412000
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -44850
|  |  |  | Total transfers from FRP cash |  |  | 412000
|  |  |  | Balance |  |  | 0

## 20506
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Finalized | Ben Bedock | 344155.26 | 307776.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -36379
|  |  |  | Total transfers from FRP cash |  |  | 307776.26
|  |  |  | Balance |  |  | 0

## 20562
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Construction | Sean Rewers | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | Total transfers from FRP cash |  |  | 405791
|  |  |  | Balance |  |  | 0

## 20566
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Warranty or Construction Closeout | Ben Bedock | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | Total transfers from FRP cash |  |  | 781870
|  |  |  | Balance |  |  | 0

## 20573
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Warranty or Construction Closeout | Ben Bedock | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | Total transfers from FRP cash |  |  | 1232681
|  |  |  | Balance |  |  | 0

## 20574
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Construction | Sean Rewers | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | Total transfers from FRP cash |  |  | 218202
|  |  |  | Balance |  |  | 0

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - Air Handling Unit Replacement | Design | Hans Mooy | 223000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | Total transfers from FRP cash |  |  | 223000
|  |  |  | Balance |  |  | 0

## 20644
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Financial Closeout | Ben Bedock | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | Total transfers from FRP cash |  |  | 630554
|  |  |  | Balance |  |  | 0

## 20645
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Construction | Ben Bedock | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | Total transfers from FRP cash |  |  | 125875
|  |  |  | Balance |  |  | 0

## 20667
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 231433
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_10312023_FRP | BAC-4 |  | 24933
|  |  |  | Total transfers from FRP cash |  |  | 231433
|  |  |  | Balance |  |  | 0

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers | 29250
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | Total transfers from FRP cash |  |  | 29250
|  |  |  | Balance |  |  | 0

## 20700
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers | 85577
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | 0

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Design | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Warranty or Construction Closeout | Ben Bedock | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | Total transfers from FRP cash |  |  | 239341
|  |  |  | Balance |  |  | 0

## 20718
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Warranty or Construction Closeout | Erin Fry | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Andy Maddox | 160500
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | Total transfers from FRP cash |  |  | 160500
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line | Construction | Hans Mooy | 23400
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | Total transfers from FRP cash |  |  | 23400
|  |  |  | Balance |  |  | 0

## 20735
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Warranty or Construction Closeout | Ben Bedock | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | Total transfers from FRP cash |  |  | 300000
|  |  |  | Balance |  |  | 0

## 20771
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 24997 | 17972
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -7025
|  |  |  | Total transfers from FRP cash |  |  | 17972
|  |  |  | Balance |  |  | 0

## 20792
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Construction | Ben Bedock | 483440
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | Total transfers from FRP cash |  |  | 483440
|  |  |  | Balance |  |  | 0

## 20831
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20831 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Design | Sean Rewers | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20832 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Design | Sean Rewers | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20833 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement | Design | Sean Rewers | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20857
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20857 | 0 | CP_400227 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Elevator Modernization | Programming or Planning | Ben Bedock | 17600
Funding transfers
|  |  |  | crowhus_10312023_FRP | BAC-1 |  | 17600
|  |  |  | Total transfers from FRP cash |  |  | 17600
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 11029283.29 | tbd | 0
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| crowhus_10312023_FRP | -45721
| Total Uses | 4732993
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 6863503.03

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.