## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2024-04-17
Total program - FY23
School | GSF | Contribution to FRP | Funded Projects | Contribution vs. Funded
Arts & Science | 1075461.7321 | 3663826 | 2276289.625 | 1387536.375
Blair | 121421.4269 | 413652 | 574290 | -160638
Divinity | 57814.7309 | 196960 | 96362.5 | 100597.5
Engineering | 537962.3327 | 1832701 | 353000 | 1479701
Law | 120155.4846 | 409339 | 1206134.5 | -796795.5
SOM Basic Sciences | 280022.3999 | 953965 | 1036871.875 | -82906.875
Nursing | 106166.7 | 361683 | 4900 | 356783
Owen | 59008.3617 | 201027 | 300000 | -98973
Peabody | 390796.8848 | 1331346 | 2949437.76 | -1618091.76
| 2748810.0535 | 9364499 | 8797286.26 | 567212.74
Total program - FY24 |  |  | (1)
School | GSF | Contribution to FRP | Estimed Funded Projects | Contribution vs. Funded
Arts & Science | 1059147 | 4204813.59 | 2389351.394 | 1815462.196
Blair | 121421 | 482041.37 | 1916810 | -1434768.63
Divinity | 58263 | 231304.11 | 3660360 | -3429055.89
Engineering | 552478 | 2193337.66 | 2024933 | 168404.66
Law | 120155 | 477015.35 | 642985 | -165969.65
SOM Basic Sciences | 265674 | 1054725.78 | -17509.674 | 1072235.454
Nursing | 105746 | 419811.62 | 286527 | 133284.62
Owen | 99140 | 393585.8 | 0 | 393585.8
Peabody | 396133 | 1572648.01 | 600349.64 | 972298.37
| 2748810.0535 | 11029283.29 | 11503806.36 | -474523.07
(1) - estimated funded projects is anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2024-04-17
| Projects |  |  |  | (1) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP Funding | Estimated Funding FY24 FRP
1 | Finalized | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0
2 | Finalized | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | -4400.96
3 | Award | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 318000 | 4900 | 255957
4 | Warranty or Construction Closeout | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0
5 | Financial Closeout | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | -47290
6 | Construction | 20431 | Divinity | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 69862.5 | 3660360
7 | Warranty or Construction Closeout | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2790000 | 81100 | 1028900
8 | Not Started | 20489 | Divinity | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | 4650000 | 26500 | 0
9 | Finalized | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | -44850
10 | Finalized | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | -36379
11 | Financial Closeout | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | -43231.36
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0
13 | Finalized | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | -59283.32
14 | Financial Closeout | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | -119221
15 | Financial Closeout | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | -22537
16 | Bidding | 20577 | Blair | Blair School of Music - AHU - 1 Replacement -Phase 1 - FY25 | 1500000 | 223000 | 0
17 | Financial Closeout | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | -58765
18 | Financial Closeout | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | 0
19 | Design | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 2000000 | 146500 | 2000000
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | 24933
21 | Award | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 680000 | 29250 | 649263
22 | Finalized | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 5954
23 | Bidding | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0
24 | Finalized | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | -29922
25 | Financial Closeout | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0
26 | Award | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500 | 0
27 | Construction | 20724 | Blair | Blair School of Music - Steam Line - FY 23 | 1987500 | 23400 | 1964100
28 | Warranty or Construction Closeout | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | 0
29 | Award | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 149000 | 0 | 148299
30 | Finalized | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | -7025
31 | Construction | 20772 | Owen | OGSM Old Mechanical- Slate Roof & Window Replacement | 3200000 | 0 | 0
32 | Finalized | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | -32665
33 | Award | 20811 | Peabody | One Magnolia Circle - Retaining Wall Repair | 75000 | 0 | 285235
34 | Finalized | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 24000
35 | Finalized | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 24000 | 0 | 24000
36 | Warranty or Construction Closeout | 20833 | Arts & Science | SC5 - HVAC Replacement | 24000 | 0 | 24000
37 | Finalized | 20834 | Peabody | Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0 | 0
38 | Construction | 20857 | Peabody | One Magnolia Circle - Elevator Modernization | 499184 | 0 | 499184
39 | Award | 20884 | Law | Law School - Exterior Window Painting | 0 | 0 | 675650
40 | Award | 20885 | Arts & Science | NMR - Replace Air Compressors | 99000 | 0 | 123341
41 | Construction | 20911 | Arts & Science | Buttrick Hall - Elevator Upgrades | 75000 | 0 | 61045
42 | Construction | 20912 | Arts & Science | Benson Hall - Elevator Upgrades | 75000 | 0 | 59798
43 | Construction | 20913 | Arts & Science | Wilson Hall - Elevator Upgrades | 75000 | 0 | 96612
44 | Award | 20924 | Nursing | Frist Hall - Stairwell Roof Replacement | 0 | 0 | 30570
45 | Design | 20925 | Blair | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | 2750000 | 0 | 0
46 | Not Started | 20934 | Arts & Science | Neely Auditorium - MEP Feasibility Study | 0 | 0 | 0
47 | Award | 20936 | Arts & Science | Wilson Hall - Lighting Retrofit for 103 and 126 | 0 | 0 | 0
48 | Programming or Planning | 20940 | Engineering | 1025 16th Avenue - Security System Replacement | 0 | 0 | 0
49 | Award | 20945 | Other | Seigenthaler Building - HVAC Improvements | 99000 | 0 | 99000
50 | Programming or Planning | 20957 | Arts & Science | SC6 - Roof Replacement | 500000 | 0 | 350000
51 | Programming or Planning | 20958 | Arts & Science | Furman Hall - Elevator Modernization | 290000 | 0 | 18175
[5 empty] | 37127926.76 | 8797286.26 | 11602806.36
(1) - estimated total budget represents the best rough order of magnitude for total project costs.
(2) - FYxx FRP funding indicates anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25
|  | 3.41 |  |  | 3.97 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78 | SOM Basic Sciences | 315635.413 | 1432984.7751
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62 | Nursing | 105746.41 | 480088.7014
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623
Anticipated spend |  | 11602806.36 | Anticipated spend |  | 3384630 | Anticipated spend |  | 0
Remaining funds |  | -2238307.36 | Remaining funds |  | 7644653.29 | Remaining funds |  | 12857284.4623

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 estimated FRP funding | MRB III Adj | FY24 revised estimated FRP | Contribution vs. FY24 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 2.3988 | -0.0094283 | 2.3894 | 1.8155
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.9168 |  | 1.9168 | -1.4348
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.6604 |  | 3.6604 | -3.4291
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 2.0249 |  | 2.0249 | 0.1684
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0.64299 |  | 0.64299 | -0.16597
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | -0.026938 | 0.0094283 | -0.01751 | 1.0722
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0.28653 |  | 0.28653 | 0.13328
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 0 |  | 0 | 0.39359
Peabody | 390796.8848 | 1.3313 | 2.9494 |  | 2.9494 | -1.6181 | 1.5726 | 0.60035 |  | 0.60035 | 0.9723
| 2748810.0535 | 9.3645 | 8.7973 |  | 8.7973 | 0.56721 | 11.0293 | 11.5038 |  | 11.5038 | -0.47452
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24
|  | MRB III BIO/SCI | 1595187.5 |  |  |  |  | -26937.96
|  | A&S | 558315.625 |  |  |  |  | -9428.286
|  | SOM | 1036871.875 |  |  |  |  | -17509.674
|  |  | 1595187.5 |  |  |  |  | -26937.96

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
17100 - Law: Business Affairs | 1845389 | 1928829
Finalized | 400000 | 483440
Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440
Warranty or Construction Closeout | 1445389 | 1445389
Law School - Fire Alarm System Replacement | 1445389 | 1445389
Award | 0 | 0
Law School - Exterior Window Painting | 0 | 0
Grand Total | 1845389 | 1928829
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Summary_by Phase
Facility Renewal Program: Summary by Project Phase
Row Labels | Actual Costs | FY23 FRP Cash | FY24 FRP Cash | Count of eBuilder
Construction | 1956984.3 | 93262.5 | 6341099 | 7
Design | 124210 | 353000 | 24933 | 3
Finalized | 3483690.25 | 3266827.26 | -160571.28 | 12
Financial Closeout | 3295000.23 | 3037159 | -291044.36 | 7
Not Started | 14407.5 | 26500 | 0 | 3
Warranty or Construction Closeout | 3501188.13 | 1103794.5 | 1052900 | 4
Award | 226097.52 | 194650 | 1250860 | 10
Bidding | 199591.21 | 722093 | 0 | 2
Programming or Planning | 0 | 0 | 0 | 3
Grand Total | 12801169.14 | 8797286.26 | 8218176.36 | 51

## Project Status
Facility Renewal Program: Projects | [16 empty] | JE LOG_FY23'!A1 |  |  | JE LOG_FY24'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Unallocated Reserve | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY24 FRP Estimated | FY24 FRP Total Contribution | FY25 FRP Estimated | FY26 FRP Estimated | Project status update | Check
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout. | 10085
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy | 1216485.5 | 1216485.5 | 1212084.54 | 1212084.54 | 1212084.54 | 0 | 1216485.5 | -4400.96 | 0 | -4400.96 | 0 | 0 | 08/22/2023 project complete | 10098
3 | Capital | 10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Award | Sean Rewers | 318000 | 318057 | 228355.7 | 228355.7 | 64975 |  | 4900 | 255957 | 0 | 255957 | 0 | 0 | 03/22/2024 Project has been awarded, PO as been sent to Beech. We will be working on schedule in April for summer install. | 10146
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 | 92965.86 | 722694.5 | 0 | 0 | 0 | 0 | 0 | 03/26/2024 work is complete | 20179
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Financial Closeout | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 280600 |  | 327890 | -47290 | 0 | -47290 | 0 | 0 | 01/22/2024 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20336
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy | 3800000 | 3800000 | 3540067.72 | 3544817.72 | 1653351.9 |  | 69862.5 | 3660360 | 0 | 3660360 | 0 | 0 | 03/22/2024 02/22/2024 01/24/2024 Project on schedule and under budget. | 20431
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2790000 | 2467989.41 | 2467989.41 | 1864414.99 | TBD | 81100 | 1028900 | 0 | 1028900 | 0 | 0 | 03/29/2024 The interior fitout was completed in August and A&S is actively occupying the building. Mechanical rooftop units and partial roof replacement began in December and is substantially complete. Issues with winter construction (roof, RTU's) are being addressed with DPR. | 20478
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Not Started | Hans Mooy | 4650000 | 26500 | 15895 | 15895 | 14407.5 |  | 26500 | 0 | 0 | 0 | 0 | 3170000 | 10/23/2023 On Hold till FY26 | 20489
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 |  | 79415.5 | -44850 | 0 | -44850 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20497
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 |  | 344155.26 | -36379 | 0 | -36379 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20506
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Financial Closeout | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 |  | 405791 | -43231.36 | 0 | -43231.36 | 0 | 0 | 01/22/2024 Project is in closeout | 20562
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 03/24/2023 Working with appropriate parties to determine scope of work. | 20563
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 722586.68 |  | 781870 | -59283.32 | 0 | -59283.32 | 0 | 0 | 11/22/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20566
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Financial Closeout | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 1113460 |  | 1232681 | -119221 | 0 | -119221 | 0 | 0 | 01/22/2024 Project is complete. Waiting on final invoice to clear to begin the closeout process. | 20573
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Financial Closeout | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 195665 |  | 218202 | -22537 | 0 | -22537 | 0 | 0 | 01/22/2024 Project is in closeout | 20574
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement -Phase 1 - FY25 | Bidding | Hans Mooy | 1500000 | 223000 | 220566.21 | 220566.21 | 185191.21 |  | 223000 | 0 | 0 | 0 | 1500000 | 2510000 | 03/22/2024 Pre Bid walk tentatively set for 04/19/24 | 20577
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Financial Closeout | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 571789 |  | 630554 | -58765 | 0 | -58765 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20644
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Financial Closeout | Ben Bedock | 125875 | 125875 | 114350 | 114350 | 114350 | 11225 | 125875 | 0 | 0 | 0 | 0 | 0 | 02/26/2024 Punchlist items have been discussed with the contractor. Once items are completed, project is ready to closeout. | 20645
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 2000000 | 146500 | 146500 | 146500 | 34500 |  | 146500 | 0 | 2000000 | 2000000 | 0 | 0 | 03/22/2024 02/27/2024 We expect DD set to be ready at the end of March and we will start the review process in April. | 20667
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 0 | 231433 | 231433 | 231433 | 89710 |  | 206500 | 24933 | 0 | 24933 | TBD | 0 | 03/22/2024 FM Sylvan is closing in on pricing for the second utility run, leading to Stevenson Center. We are coordinating with NES to see what costs would be for transformer power set up. | 20668
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Award | Sean Rewers | 680000 | 678513 | 583771 | 583771 | 21207.5 |  | 29250 | 649263 | 0 | 649263 | 0 | 0 | 03/28/2024 We will begin scheduling in April, put in front of FRC in April, with construction slated to start summer 2024. | 20698
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 85576.77 |  | 79623 | 5954 | 0 | 5954 | 0 | 0 | 11/27/2023 Project is in closeout | 20700
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Bidding | Sean Rewers | 500000 | 499093 | 18000 | 18000 | 14400 |  | 499093 | 0 | 0 | 0 | 0 | 0 | 03/22/2024 Pre-bid walkthrough is scheduled for the end of March. We will determine schedule once lead times are known. Project needs to be completed during the summer when students are less likely to be using the building. | 20701
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 209419 |  | 239341 | -29922 | 0 | -29922 | 0 | 0 | 12/18/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20702
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Financial Closeout | Erin Fry | 715000 | 715000 | 656784.6 | 656784.6 | 656576.59 | TBD | 96166 | 0 | 0 | 0 | 0 | 0 | 02/23/2024 Construction complete. Library Closeout process complete. The Financial closeout process has been started. | 20718
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Andy Maddox | 1610000 | 160500 | 155232.52 | 155232.52 | 138595.02 |  | 160500 | 0 | 0 | 0 | TBD | 0 | 03/27/2024 Per meeting with Anthony Tharp, this is an FY25 project. There are several projects on 9th floor at MRB III, that will roll into one large project - controls project, nitrogen generators project, and Micro Spectrometer Research Center (MSRC) project. | 20723
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Construction | Hans Mooy | 1987500 | 1987500 | 1784625 | 1784625 | 259375.9 |  | 23400 | 1964100 | 0 | 1964100 | 0 | 0 | 03/22/2024 02/22/2024 01/22/2024 11/22/2023 10/23/2023 Outside work is underway; Inside work is scheduled for May 2024 | 20724
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Warranty or Construction Closeout | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 260350 | 23500 | 300000 | 0 | 0 | 0 | 0 | 0 | 03/26/2024 02/26/2024 Project is complete. Contractor is working on punch list items. Once items complete, project is ready to close. | 20735
29 | Capital | 20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Award | Jay Surprenant | 149000 | 148299 | 0 | 125699 | 0 |  | 0 | 148299 | 0 | 148299 | 0 | 0 | 03/29/2024 02/28/2024 01/26/2024 12/18/2023 Waiting budget approval. 2/28 Scope modified, waiting on additional bid, will modify BAC and resubmit. 3/29, New budget submitted. waiting approval before scheduling contractor. Set for summer '24 work. | 20767
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 |  | 24997 | -7025 | 0 | -7025 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space. | 20771
31 | Capital | 20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock | 3200000 | 3200000 | 2789045 | 2789045 | 0 |  | 0 | 0 | 0 | 0 | 3200000 | 0 | 03/26/2024 02/26/2024 Currently working through the PO process. | 20772
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock | 400000 | 483440 | 450775 | 450775 | 450775 |  | 483440 | -32665 | 0 | -32665 | 0 | 0 | 12/18/2023 Construction complete. Waiting on final invoices to clear to begin the closeout process. | 20792
33 | Capital | 20811 |  | CP_400224 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Award | Ben Bedock | 75000 | 2640 | 2640 | 2640 | 1320 |  | 0 | 0 | 285235 | 285235 |  |  | 03/26/2024 Project currently out to bid. Bids are due 03/29 | 20811
34 | Operating | 20831 | 8230 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 24000 | 0 | 0 | 01/30/2024 Project is in closeout. Study was completed and findings were shared with Provost and A&S. Due to the large scale renovations needed to the building this project will require further planning and cannot be priced our accurately. A&S will present the findings to their dean for further guidance on how to tackle the buildings issues. | 20831
35 | Operating | 20832 | 8220 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 24000 | 0 | 0 | 01/22/2024 Project study and estimated pricing is complete. Project in closeout. | 20832
36 | Operating | 20833 | 8215 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Warranty or Construction Closeout | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 24000 | 0 | 0 | 03/22/2024 Project is in closeout | 20833
37 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Finalized | Sean Rewers | 5000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/27/2023 This project is on hold until October. We are awaiting approval from the CBO for initial funding which will be repaid by the FRP. | #N/A
38 | Capital | 20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock | 499184 | 499184 | 461612 | 461612 | 13000 |  | 0 | 499184 | 0 | 499184 | 0 | 0 | 03/26/2024 Working through the PO process | 20857
39 |  | 20884 |  |  | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Exterior Window Painting | Award | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 675650 | 675650 |  |  | 03/26/2024 VUMO is managing this project. CPC is helping with the PO process. | 20884
40 | Operating | 20885 | 8676 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Award | Sean Rewers | 99000 | 98341 | 83231 | 83231 | 0 |  | 0 | 98341 | 25000 | 123341 |  |  | 03/22/2024 We are awaiting contract signature by Nashville Machine. We hope to have equipment in around May and will do summer install. | 20885
41 | Capital | 20911 | 8819 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Construction | Ben Bedock | 75000 | 61045 | 54613 | 54613 | 27256.5 |  | 0 | 61045 | 0 | 61045 |  |  | 03/26/2024 Working through the PO process. | 20911
42 | Capital | 20912 | 8822 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Construction | Ben Bedock | 75000 | 59798 | 53366 | 53366 | 2000 |  | 0 | 59798 | 0 | 59798 |  |  | 03/26/2024 Working through the PO process. | 20912
43 | Capital | 20913 | 8818 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Elevator Upgrades | Construction | Ben Bedock | 75000 | 96612 | 86900 | 86900 | 2000 |  | 0 | 96612 | 0 | 96612 |  |  | 03/26/2024 Working through the PO process. | 20913
44 | TBD | 20924 |  |  | 19000 - Nursing: Office of the Dean | Nursing | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Award | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 30570 | 30570 |  |  | 03/26/2024 Working with the appropriate parties to determine the scope of work. | 20924
45 | Capital | 20925 |  |  | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Design | Hans Mooy | 2750000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 2750000 | 03/22/2024 waiting for FY 26 funding | 20925
46 | TBD | 20934 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | NEELY AUDITORIUM | Neely Auditorium - MEP Feasibility Study | Not Started | Sean Rewers |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | New project | 20934
47 | TBD | 20936 | 8814 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Award | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | 03/29/2024 Bids due 3/29. Will award in April if budget is approved. | 20936
48 | TBD | 20940 |  |  | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Programming or Planning | Sean Rewers |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  | New project | 20940
49 | Operating | 20945 |  |  | 10000 - Chancellor | Other | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Award | Sean Rewers | 99000 | 99000 | 75900 | 75900 | 0 |  | 0 | 99000 | 0 | 99000 | TBD |  | 03/22/2024 We are awaiting PO for Nashville Machine. They will start work as soon as PO is received. | 20945
50 | TBD | 20957 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - Roof Replacement | Programming or Planning | Hans Mooy | 500000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 350000 | 350000 |  |  | New project | 20957
51 | TBD | 20958 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - Elevator Modernization | Programming or Planning | Ben Bedock | 290000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 18175 | 18175 | TBD |  | New project | 20958
[11 empty] | 37127926.76 | 24254112.76 | 21431564.19 | 21562013.19 | 12801169.14 | 127690.86 | 8797286.26 | 8218176.36 | 3384630 | 11602806.36 | 4700000 | 8430000
[17 empty] | TRUE | TRUE
Projects to be added
[8 empty] | MRB III - air compressor engineering /design (Chris to complete project intake) | [7 empty] | Collections | 9364499 |  | Carryforward | 567212.74
[8 empty] | Godchaux - replace roof [Ben] - wait until after HVAC project completed, FY26 (includes small stairwell section in Frist) | [10 empty] | Collections | 11029283.29
[16 empty] | Transferred | 8797286.26 |  |  | 11596496.03
Projects to be discussed
[8 empty] | Vaughn - roof, (phase 2) - summer 2024 | [7 empty] | Remaining | 567212.74 |  | Transferred | 8218176.36
[19 empty] | To be moved | 3384630
11602806.36
[16 empty] | Unalloc reserve | 127690.86 |  | Remaining | -6310.33
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on W11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project will be joint funded, FPR / Divinity + Dean of Students.
Note on W19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase 2 estimate. May be a separate project ID.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10085 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 9364499 | 17500 |  | 17500
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy |  | 1216485.5 |  | 1216485.5
| 3 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 4900 |  | 4900
| 4 | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon |  | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock |  | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy |  | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett |  | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Design | Hans Mooy |  | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock |  | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock |  | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers |  | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock |  | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock |  | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers |  | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement -Phase 1 - FY25 | Design | Hans Mooy |  | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock |  | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock |  | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers |  | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers |  | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock |  | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry |  | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Andy Maddox |  | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Design | Hans Mooy |  | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock |  | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers |  | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock |  | 483440 |  | 483440
[8 empty] | 8797286.26 | 0 | 8797286.26 | 567212.74
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Award | Sean Rewers | 11029283.29 | 255957 | 0 | 255957 |  | phase 1
| 2 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy |  | 3660360 | 0 | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett |  | 1028900 | 0 | 1028900
| 4 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 0 | 2000000 | 2000000
| 5 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 24933 | 0 | 24933
| 6 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Award | Sean Rewers |  | 649263 | 0 | 649263
| 7 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers |  | 5954 | 0 | 5954
| 8 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Construction | Hans Mooy |  | 1964100 | 0 | 1964100
| 9 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Award | Jay Surprenant |  | 148299 | 0 | 148299
| 10 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers |  | 24000 | 0 | 24000
| 11 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers |  | 24000 | 0 | 24000
| 12 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement | Warranty or Construction Closeout | Sean Rewers |  | 24000 | 0 | 24000
| 13 | 20857 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock |  | 499184 | 0 | 499184
| 14 | 20811 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Award | Ben Bedock |  | 0 | 285235 | 285235
| 15 | 20884 | LAW SCHOOL | Law School - Exterior Window Painting | Award | Ben Bedock |  | 0 | 675650 | 675650
| 16 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Award | Sean Rewers |  | 98341 | 25000 | 123341
| 17 | 20911 | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Construction | Ben Bedock |  | 61045 | 0 | 61045
| 18 | 20912 | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Construction | Ben Bedock |  | 59798 | 0 | 59798
| 19 | 20913 | WILSON HALL | Wilson Hall - Elevator Upgrades | Construction | Ben Bedock |  | 96612 | 0 | 96612
| 20 | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Award | Ben Bedock |  | 0 | 30570 | 30570
| 21 | 20945 | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Award | Sean Rewers |  | 99000 | 0 | 99000
| 22 | 20957 | SC PHYSICS & ASTRONOMY | SC6 - Roof Replacement | Programming or Planning | Hans Mooy |  | 0 | 350000 | 350000
| 23 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Programming or Planning | Ben Bedock |  | 0 | 18175 | 18175
|  | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy |  | -4400.96 | 0 | -4400.96
|  | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock |  | -44850 | 0 | -44850
|  | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock |  | -36379 | 0 | -36379
|  | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock |  | -59283.32 | 0 | -59283.32
|  | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers |  | -7025 | 0 | -7025
|  | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock |  | -29922 | 0 | -29922
|  | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock |  | -32665 | 0 | -32665
|  | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Financial Closeout | Ben Bedock |  | -47290 | 0 | -47290
|  | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Financial Closeout | Sean Rewers |  | -43231.36 | 0 | -43231.36
|  | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Financial Closeout | Ben Bedock |  | -119221 | 0 | -119221 | prior year
|  | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Financial Closeout | Sean Rewers |  | -22537 | 0 | -22537 | carryforward
|  | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Financial Closeout | Ben Bedock |  | -58765 | 0 | -58765 | 567212.74
[8 empty] | 8218176.36 | 3384630 | 11602806.36 | -6310.33
FY 2025 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock | 12857284.4623 |  | 3200000 | 3200000
| 2 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement -Phase 1 - FY25 | Bidding | Hans Mooy |  |  | 1500000 | 1500000 |  | phase 1
| 3 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Andy Maddox |  |  | TBD | TBD
| 4 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  |  | TBD | TBD
| 5 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Award | Jay Surprenant |  |  | 0 | 0
| 6 | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Award | Ben Bedock |  |  | 0 | 0
| 8 | 20934 | NEELY AUDITORIUM | Neely Auditorium - MEP Feasibility Study | Not Started | Sean Rewers |  |  | 0 | 0
| 9 | 20936 | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Award | Jay Surprenant |  |  | 0 | 0
| 10 | 20940 | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Programming or Planning | Sean Rewers |  |  | 0 | 0
| 11 | 20945 | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Award | Sean Rewers |  |  | TBD | TBD
| 12 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Programming or Planning | Ben Bedock |  |  | TBD | TBD
[8 empty] | 0 | 4700000 | 4700000 | 8157284.4623
FY 2026 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Not Started | Hans Mooy | 0 |  | 3170000 | 3170000 |  | phase 2
| 2 | 20925 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Design | Hans Mooy |  |  | 2750000 | 2750000 |  | phase 2
| 3 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  |  | TBD | TBD
[8 empty] | 0 | 5920000 | 5920000 | -5920000
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Preliminary cost estimates presented in three options. $4M - $5M range.

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 22000 | 17500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 0

## 10098 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy | 1216485.5 | 1212084.54
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | crowhus_01302024_FRP | FX2-1 |  | -4400.96
|  |  |  | Total transfers from FRP cash |  |  | 1212084.54
|  |  |  | Balance |  |  | 0

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 4418 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Award | Sean Rewers | 318057
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | crowhus_01302024_FRP | BAC-5 |  | 244457
|  |  |  | FY24 subtotal |  |  | 255957
|  |  |  | Balance |  |  | 0

## 20179
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Warranty or Construction Closeout | Bob Grummon | 1445389 | 1352423.14
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
1445389
|  |  |  | Total transfers from FRP cash |  |  | 722694.5
|  |  |  | Balance |  |  | 0

## 20336 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Financial Closeout | Ben Bedock | 327890 | 280600
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -47290
|  |  |  | Total transfers from FRP cash |  |  | 280600
|  |  |  | Balance |  |  | 0

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy | 3800000
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360
All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
3800000
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2467989.41
[9 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 |  | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 |  | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 |  | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
[7 empty] | 2790000 |  | 1110000 | 1680000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Not Started | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Finalized | Ben Bedock | 456850 | 412000
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -44850
|  |  |  | Total transfers from FRP cash |  |  | 412000
|  |  |  | Balance |  |  | 0

## 20506 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Finalized | Ben Bedock | 344155.26 | 307776.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -36379
|  |  |  | Total transfers from FRP cash |  |  | 307776.26
|  |  |  | Balance |  |  | 0

## 20562 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Financial Closeout | Sean Rewers | 405791 | 362559.64
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -43231.36
|  |  |  | Total transfers from FRP cash |  |  | 362559.64
|  |  |  | Balance |  |  | 0

## 20566 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock | 781870 | 722586.68
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | crowhus_02292024_FRP | FX |  | -59283.32
|  |  |  | Total transfers from FRP cash |  |  | 722586.68
|  |  |  | Balance |  |  | 0

## 20573 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Financial Closeout | Ben Bedock | 1232681 | 1113460
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -119221
|  |  |  | Total transfers from FRP cash |  |  | 1113460
|  |  |  | Balance |  |  | 0

## 20574 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Financial Closeout | Sean Rewers | 218202 | 195665
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -22537
|  |  |  | Total transfers from FRP cash |  |  | 195665
|  |  |  | Balance |  |  | 0

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - AHU - 1 Replacement -Phase 1 - FY25 | Bidding | Hans Mooy | 223000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | Total transfers from FRP cash |  |  | 223000
|  |  |  | Balance |  |  | 0

## 20644 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Financial Closeout | Ben Bedock | 630554 | 571789
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -58765
|  |  |  | Total transfers from FRP cash |  |  | 571789
|  |  |  | Balance |  |  | 0

## 20645
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Financial Closeout | Ben Bedock | 125875 | 114350
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | Total transfers from FRP cash |  |  | 125875
|  |  |  | Balance |  |  | 0

## 20667
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 231433
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_10312023_FRP | BAC-4 |  | 24933
|  |  |  | Total transfers from FRP cash |  |  | 231433
|  |  |  | Balance |  |  | 0

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Award | Sean Rewers | 678513
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | crowhus_01302024_FRP | BAC-4 | ` | 649263
|  |  |  | Total transfers from FRP cash |  |  | 678513
|  |  |  | Balance |  |  | 0

## 20700 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers | 85577 | 85576.77
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | 0

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Bidding | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock | 239341 | 209419
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | crowhus_02292024_FRP | FX |  | -29922
|  |  |  | Total transfers from FRP cash |  |  | 209419
|  |  |  | Balance |  |  | 0

## 20718
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Financial Closeout | Erin Fry | 715000 | 656784.6
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Andy Maddox | 160500
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | Total transfers from FRP cash |  |  | 160500
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line - FY 23 | Construction | Hans Mooy | 1987500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | crowhus_12192023_FRP | BAC-2 |  | 1964100
|  |  |  | Total transfers from FRP cash |  |  | 1987500
|  |  |  | Balance |  |  | 0

## 20735
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Warranty or Construction Closeout | Ben Bedock | 300000 | 276500
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | Total transfers from FRP cash |  |  | 300000
|  |  |  | Balance |  |  | 0

## 20767
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Six Magnolia Circle - Foundation Repairs | Award | Jay Surprenant | 148299 | 0
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 148299
|  |  |  | Total transfers from FRP cash |  |  | 148299
|  |  |  | Balance |  |  | 0

## 20771 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 24997 | 17972
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -7025
|  |  |  | Total transfers from FRP cash |  |  | 17972
|  |  |  | Balance |  |  | 0

## 20792 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock | 483440 | 450775
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | crowhus_02292024_FRP | FX |  | -32665
|  |  |  | Total transfers from FRP cash |  |  | 450775
|  |  |  | Balance |  |  | 0

## 20831 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20831 | 8230 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20832 | 8220 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20833 | 8215 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement | Warranty or Construction Closeout | Sean Rewers | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20857
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock | 499184
Funding transfers
|  |  |  | crowhus_10312023_FRP | BAC-1 |  | 17600
|  |  |  | crowhus_01302024_FRP | BAC-2 |  | 4000
|  |  |  | crowhus_03312024_FRP | BAC-3 |  | 477584
|  |  |  | Total transfers from FRP cash |  |  | 499184
|  |  |  | Balance |  |  | 0

## 20885
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20885 | 8676 | 0 | 12000 - Arts and Science: Office of the Dean | NMR - Replace Air Compressors | Award | Sean Rewers | 98341
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-2 |  | 98341
|  |  |  | Total transfers from FRP cash |  |  | 98341
|  |  |  | Balance |  |  | 0

## 20911
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20911 | 8819 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Elevator Upgrades | Construction | Ben Bedock | 61045
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 56945
|  |  |  | Total transfers from FRP cash |  |  | 61045
|  |  |  | Balance |  |  | 0

## 20912
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20912 | 8822 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Hall - Elevator Upgrades | Construction | Ben Bedock | 59798
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 55698
|  |  |  | Total transfers from FRP cash |  |  | 59798
|  |  |  | Balance |  |  | 0

## 20913
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20913 | 8818 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Elevator Upgrades | Construction | Ben Bedock | 96612
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 92512
|  |  |  | Total transfers from FRP cash |  |  | 96612
|  |  |  | Balance |  |  | 0

## 20936
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20936 | 8814 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Lighting Retrofit for 103 and 126 | Award | Jay Surprenant | 0
Funding transfers
|  |  |  | TBD | BAC-1 |  | 404655.91
|  |  |  | Total transfers from FRP cash |  |  | 404655.91
|  |  |  | Balance |  |  | -404655.91

## 20945
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20945 | 0 | 0 | 10000 - Chancellor | Seigenthaler Building - HVAC Improvements | Award | Sean Rewers | 99000
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 99000
|  |  |  | Total transfers from FRP cash |  |  | 99000
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 11029283.29 | tbd | 0
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| crowhus_10312023_FRP | -45721
| crowhus_12192023_FRP | 1964100
| crowhus_01302024_FRP | 893319.04
| crowhus_02292024_FRP | -11229.32
| crowhus_03312024_FRP | 638993.64
| Total Uses | 8218176.36
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 3378319.67 |  |  | DB: | CR:
[5 empty] | 7025 | 24933
[5 empty] | 36379 | 17600
44850
[5 empty] | 88254 | 42533 | 130787
-45721
[5 empty] | DB: | CR:
[5 empty] | 1964100 | 1964100
[5 empty] | 1964100 | 1964100
[5 empty] | 3928200 | 3928200
0
[5 empty] | DB: | CR:
649263
244457
4000
4400.96
[5 empty] | 4400.96 | 897720 | 902120.96
893319.04
[5 empty] | DB: | CR:
12300
98341
59283.32
29922
32665
[5 empty] | 121870.32 | 110641 | 232511.32
-11229.32
[5 empty] | DB: | CR:
148299
[5 empty] | 47290 | 477584
[5 empty] | 43231.36 | 56945
[5 empty] | 119221 | 55698
[5 empty] | 22537 | 92512
[5 empty] | 58765 | 99000
[5 empty] | 291044.36 | 930038 | 1221082.36
638993.64

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody
19000 - Nursing: Office of the Dean | Nursing

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.