## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.
Notes about upcoming planning

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2024-12-03
School | GSF | FY23 - FY25 Cumulative Contribution | FY23 Funded Projects | FY24 Funded Projects | FY25 Estimated Projects | Contribution vs. Funded
Arts & Science | 1075461.7321 | 12747868.731 | 2276289.625 | 2619344.704 | 1038779 | 6813455.402
Blair | 121421.4269 | 1496829.2818 | 574290 | 1916810 | 1077000 | -2071270.7182
Divinity | 57814.7309 | 692779.0038 | 96362.5 | 3660360 | 0 | -3063943.4962
Engineering | 537962.3327 | 6515613.1943 | 353000 | 24933 | 2344789 | 3792891.1943
Law | 120155.4846 | 1427819.0631 | 1206134.5 | 661160 | 160859.14 | -600334.5769
SOM Basic Sciences | 280022.3999 | 3441675.5551 | 1036871.875 | -17509.674 | 1111175 | 1311138.3541
Nursing | 106166.7 | 1261583.3214 | 4900 | 286527 | 0 | 970156.3214
Owen | 59008.3617 | 1046789.5035 | 300000 | 1576500 | 1600000 | -2429710.4965
Peabody | 390796.8848 | 4620109.0983 | 2949437.76 | 600347.91 | 0 | 1070323.4283
| 2748810.0535 | 33251066.7523 | 8797286.26 | 11328472.94 | 7332602.14 | 5792705.4123
Estimated funded projects is anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2024-12-03
| Projects |  |  |  | (1) | (2) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP Funding | FY24 FRP Funding | FY25 FRP Funding
1 | Finalized | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0 | 0
2 | Finalized | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | -4400.96 | 0
3 | Financial Closeout | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 318000 | 4900 | 255957 | 0
4 | Finalized | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0 | -92965.86
5 | Finalized | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | -47290 | 0
6 | Warranty or Construction Closeout | 20431 | Divinity | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 69862.5 | 3660360 | 0
7 | Warranty or Construction Closeout | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2790000 | 81100 | 1028900 | 0
8 | Programming or Planning | 20489 | Divinity | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | 4650000 | 26500 | 0 | 0
9 | Finalized | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | -44850 | 0
10 | Finalized | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | -36379 | 0
11 | Finalized | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | -43231.36 | 0
12 | Not Started | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0 | 0
13 | Finalized | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | -59283.32 | 0
14 | Finalized | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | -119221 | 0
15 | Finalized | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | -22537 | 0
16 | Construction | 20577 | Blair | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | 1300000 | 223000 | 0 | 1077000
17 | Finalized | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | -58765 | 0
18 | Finalized | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | -11525 | 0
19 | Award | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 1550000 | 146500 | 0 | 1650000
20 | Design | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | 24933 | 0
21 | Financial Closeout | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 680000 | 29250 | 649263 | 0
22 | Finalized | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 5954 | 0
23 | Award | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0 | 0
24 | Finalized | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | -29922 | 0
25 | Finalized | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0 | 0
26 | Award | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500 | 0 | 1709500
27 | Warranty or Construction Closeout | 20724 | Blair | Blair School of Music - Steam Line - FY 23 | 1987500 | 23400 | 1964100 | 0
28 | Finalized | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | -23500 | 0
29 | Warranty or Construction Closeout | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 149000 | 0 | 148299 | 0
30 | Finalized | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | -7025 | 0
31 | Construction | 20772 | Owen | OGSM Old Mechanical- Slate Roof & Window Replacement | 3200000 | 0 | 1600000 | 1600000
32 | Finalized | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | -32665 | 0
33 | Construction | 20811 | Peabody | One Magnolia Circle - Retaining Wall Repair | 75000 | 0 | 285233.27 | 0
34 | Design | 20812 | Engineering | 1025 16th Avenue - Patio Repairs | 0 | 0 | 0 | 400000
35 | Finalized | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 24000 | 0
36 | Finalized | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 24000 | 0 | 24000 | 0
37 | Finalized | 20833 | Arts & Science | SC5 - HVAC Replacement (Design Services) | 24000 | 0 | 24000 | 0
38 | Finalized | 20834 | Peabody | Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0 | 0 | 0
39 | Construction | 20857 | Peabody | One Magnolia Circle - Elevator Modernization | 499184 | 0 | 499184 | 0
40 | Financial Closeout | 20884 | Law | Law School - Exterior Window Painting | 675650 | 0 | 675650 | 0
41 | Construction | 20885 | Arts & Science | NMR - Replace Air Compressors | 99000 | 0 | 113053.4 | 30000
42 | Warranty or Construction Closeout | 20911 | Arts & Science | Buttrick Hall - Elevator Upgrades | 61045 | 0 | 61045 | 0
43 | Construction | 20912 | Arts & Science | Benson Hall - Elevator Upgrades | 59798 | 0 | 59798 | 0
44 | Construction | 20913 | Arts & Science | Wilson Hall - Elevator Upgrades | 96612 | 0 | 96612 | 0
45 | Warranty or Construction Closeout | 20922 | Arts & Science | Vaughn Home - Exterior Improvements | 170000 | 0 | 197150 | 0
46 | Warranty or Construction Closeout | 20924 | Nursing | Frist Hall - Stairwell Roof Replacement | 30570 | 0 | 30570 | 0
47 | Programming or Planning | 20925 | Blair | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | 2750000 | 0 | 0 | 0
48 | Not Started | 20934 | Arts & Science | Neely Auditorium - MEP Feasibility Study | 0 | 0 | 0 | TBD
49 | Warranty or Construction Closeout | 20936 | Arts & Science | Wilson Hall - Lighting Retrofit for 103 and 126 | 405000 | 0 | 404655.91 | 0
50 | Construction | 20940 | Engineering | 1025 16th Avenue - Security System Replacement | 310000 | 0 | 0 | 294789
51 | Financial Closeout | 20945 | Other | Seigenthaler Building - HVAC Improvements | 99000 | 0 | 99000 | 0
52 | Finalized | 20957 | Arts & Science | SC6 - Roof Replacement | 500000 | 0 | 0 | 0
53 | Construction | 20958 | Arts & Science | Furman Hall - Elevator Modernization | 290000 | 0 | 18175 | 243454
54 | Programming or Planning | 20962 | Arts & Science | Vaughn Home - Roof Replacement | 1750000 | 0 | 0 | TBD
55 | Programming or Planning | 20979 | Engineering | 1025 16th Avenue - Roof Replacement | 270000 | 0 | 0 | 0
56 | Construction | 20982 | Law | Law School - Elevator 1 Modernization | 272000 | 0 | 18175 | 253825
57 | Construction | 20984 | Arts & Science | Wilson Hall - 1st Floor Urinal Replacement | 167000 | 0 | 0 | 167000
58 | Programming or Planning | 21004 | Arts & Science | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | 0 | 0 | 0 | TBD
59 | Programming or Planning | 21005 | Arts & Science | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | 0 | 0 | 0 | TBD
60 | Programming or Planning | 21006 | Engineering | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | 0 | 0 | 0 | 0
61 | Programming or Planning | 21007 | Engineering | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | 0 | 0 | 0 | 0
62 | Not Started | 21010 | Engineering | Featheringill-Jacobs Hall - Domestic Water Heat Exchanger Replacement | 0 | 0 | 0 | 0
63 | Programming or Planning | 21051 | SOM Basic Sciences | MRBIII - 5th Floor Controls | 0 | 0 | 0 | 0
[5 empty] | 40520601.76 | 8797286.26 | 11427472.94 | 7332602.14
Estimated total budget represents the best rough order of magnitude for total project costs.
FYxx FRP funding indicates anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25 |  |  | Facility Renewal Program: Contributions - FY26
|  | 3.41 |  |  | 3.97 |  |  | 4.54 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141 | Arts & Science | 1168519.772 | 5305079.765
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118 | Blair | 121417.211 | 551234.1379
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938 | College of Connected Computing | 42638.0889 | 193576.9234
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343 | Divinity | 58286.9615 | 264622.8051
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131 | Engineering | 490439.8851 | 2226597.0781
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78 | SOM Basic Sciences | 315635.413 | 1432984.7751 | Law | 119265.3553 | 541464.7131
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62 | Nursing | 105746.41 | 480088.7014 | Nursing | 105746.45 | 480088.883
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035 | Owen | 99610.0673 | 452229.7056
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883 | Peabody | 381580.0251 | 1732373.3138
[9 empty] | SOM Basic Sciences | 334042.3631 | 1516552.3283
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623 |  | 2921546.1792 | 13263819.6534
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623 | Contribution |  | 13263819.6534
Anticipated spend |  | 8797286.26 | Anticipated spend |  | 11427472.94 | Anticipated spend |  | 7332602.14 | Anticipated spend |  | 0
Remaining funds |  | 567212.74 | Remaining funds |  | -398189.65 | Remaining funds |  | 5524682.3223 | Remaining funds |  | 13263819.6534
TRUE

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 FRP funding | MRB III Adj | FY24 FRP | Contribution vs. FY24 FRP funding | FY25 Contribution | FY25 estimated FRP funding | MRB III Adj | FY25 FRP | Contribution vs. FY25 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 2.6288 | -0.0094283 | 2.6193 | 1.5855 | 4.8792 | 0.44045 | 0.59832 | 1.0388 | 3.8405
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.9168 |  | 1.9168 | -1.4348 | 0.60114 | 1.077 |  | 1.077 | -0.47586
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.6604 |  | 3.6604 | -3.4291 | 0.26451 | 0 |  | 0 | 0.26451
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0.024933 |  | 0.024933 | 2.1684 | 2.4896 | 2.3448 |  | 2.3448 | 0.14479
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0.66116 |  | 0.66116 | -0.18414 | 0.54146 | 0.16086 |  | 0.16086 | 0.38061
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | -0.026938 | 0.0094283 | -0.01751 | 1.0722 | 1.433 | 1.7095 | -0.59832 | 1.1112 | 0.32181
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0.28653 |  | 0.28653 | 0.13328 | 0.48009 | 0 |  | 0 | 0.48009
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 1.5765 |  | 1.5765 | -1.1829 | 0.45218 | 1.6 |  | 1.6 | -1.1478
Peabody | 390796.8848 | 1.3313 | 2.9494 |  | 2.9494 | -1.6181 | 1.5726 | 0.60035 |  | 0.60035 | 0.9723 | 1.7161 | 0 |  | 0 | 1.7161
| 2748810.0535 | 9.3645 | 8.7973 |  | 8.7973 | 0.56721 | 11.0293 | 11.3285 |  | 11.3285 | -0.29919 | 12.8573 | 7.3326 |  | 7.3326 | 5.5247
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24 |  |  |  |  | FY25
MRB III BIO/SCI |  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1709500
A&S |  |  | 558315.625 |  |  |  |  | -9428.286 |  |  |  |  | 598325
SOM |  |  | 1036871.875 |  |  |  |  | -17509.674 |  |  |  |  | 1111175
|  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1709500

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
21000 - Peabody College: Office of the Dean | 4035715.26 | 4264088.53
Construction | 723184 | 932716.27
Six Magnolia Circle - Foundation Repairs | 149000 | 148299
One Magnolia Circle - Elevator Modernization | 499184 | 499184
One Magnolia Circle - Retaining Wall Repair | 75000 | 285233.27
Finalized | 3312531.26 | 3331372.26
Jesup - Roof Replacement | 456850 | 456850
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000
Peabody Administration - Envelope Repairs | 630554 | 630554
Wyatt Center - Elevator #2 Modernization | 225791 | 239341
Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0
Wyatt Center - Roof Replacement | 1232681 | 1232681
Wyatt Center - VAV Replacement | 400000 | 405791
Wyatt Center - Window Replacement | 344155.26 | 344155.26
Grand Total | 4035715.26 | 4264088.53
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Status
Facility Renewal Program: Projects | [16 empty] | JE LOG_FY23'!A1 | JE LOG_FY24'!A1 |  |  | JE LOG_FY25'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Unallocated Reserve | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY25 FRP Transferred | FY25 FRP Estimated | FY25 FRP Total Contribution | FY26 FRP Estimated | Project status update | Check
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout. | 10085
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy | 1216485.5 | 1216485.5 | 1212084.54 | 1212084.54 | 1212084.54 | 0 | 1216485.5 | -4400.96 | 0 | 0 | 0 | 0 | 08/22/2023 project complete | 10098
3 | Capital | 10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Financial Closeout | Sean Rewers | 318000 | 318057 | 253826.81 | 253826.81 | 241690.38 | 64230.19 | 4900 | 255957 | 0 | 0 | 0 | 0 | 09/26/2024 Project is in library closeout. Will complete financial closeout after. | 10146
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Fire Alarm System Replacement | Finalized | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 |  | 722694.5 | 0 | -92965.86 | 0 | -92965.86 | 0 | 07/29/2024 work is complete | 20179
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Finalized | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 280600 |  | 327890 | -47290 | 0 | 0 | 0 | 0 | 01/22/2024 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20336
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy | 3800000 | 3800000 | 3608989.67 | 3608989.67 | 3452428.36 | 191010.33 | 69862.5 | 3660360 | 0 | 0 | 0 | 0 | 11/25/2024 Project Complete | 20431
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2790000 | 2652824.48 | 2652824.48 | 2652824.48 | 0 | 81100 | 1028900 | 0 | 0 | 0 | 0 | 12/02/2024 Door hardware will be replaced early 2025 then the project will be closed out. | 20478
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Programming or Planning | Hans Mooy | 4650000 | 26500 | 15895 | 15895 | 14407.5 |  | 26500 | 0 | 0 | 0 | 0 | 3170000 | 10/23/2023 On Hold till FY26 | 20489
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 |  | 79415.5 | -44850 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20497
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 |  | 344155.26 | -36379 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20506
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Finalized | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 |  | 405791 | -43231.36 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20562
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | On hold per FRP 07/24/2024 until summer of 2026 | 20563
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 722586.68 |  | 781870 | -59283.32 | 0 | 0 | 0 | 0 | 11/22/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20566
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Finalized | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 1113460 |  | 1232681 | -119221 | 0 | 0 | 0 | 0 | 01/22/2024 Project is complete. Waiting on final invoice to clear to begin the closeout process. | 20573
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Finalized | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 195665 |  | 218202 | -22537 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20574
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Hans Mooy | 1300000 | 1300000 | 1092354.21 | 1092354.21 | 185191.21 |  | 223000 | 0 | 1077000 | 0 | 1077000 | 2510000 | 11/25/2024 AHU in production, delivery is 24 weeks out (May 2025). Meetings will pick back up in late January. | 20577
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Finalized | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 571789 |  | 630554 | -58765 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20644
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Finalized | Ben Bedock | 125875 | 125875 | 114350 | 114350 | 114350 |  | 125875 | -11525 | 0 | 0 | 0 | 0 | 02/26/2024 Punchlist items have been discussed with the contractor. Once items are completed, project is ready to closeout. | 20645
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Award | Sean Rewers | 1550000 | 146500 | 146500 | 146500 | 119500 |  | 146500 | 0 | 0 | 1650000 | 1650000 | 0 | 11/25/2024 PO process has been started. Awaiting PO to order equipment for a spring start to project. | 20667
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 0 | 231433 | 231433 | 231433 | 116143 |  | 206500 | 24933 | 0 | 0 | 0 | TBD | 11/25/2024 We are awaiting definitive plans from the CUI project to determine where our chilled water connection will be. If hot water goes past the building as part of CUI we will rework the design to include hot water connection. | 20668
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Financial Closeout | Sean Rewers | 680000 | 678513 | 586776.36 | 586776.36 | 586776.36 | 91736.64 | 29250 | 649263 | 0 | 0 | 0 | 0 | 11/25/2024 Project in FX | 20698
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 85576.77 |  | 79623 | 5954 | 0 | 0 | 0 | 0 | 11/27/2023 Project is in closeout | 20700
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 500000 | 499093 | 400593 | 400593 | 15300 |  | 499093 | 0 | 0 | 0 | 0 | 0 | 11/25/2024 Project is scheduled for Winter 2024. | 20701
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 209419 |  | 239341 | -29922 | 0 | 0 | 0 | 0 | 12/18/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20702
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Finalized | Erin Fry | 715000 | 715000 | 656784.6 | 656784.6 | 656576.59 |  | 96166 | 0 | 0 | 0 | 0 | 0 | 02/23/2024 Construction complete. Library Closeout process complete. The Financial closeout process has been started. | 20718
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Jay Surprenant | 1610000 | 1700000 | 155232.52 | 155232.52 | 138595.02 |  | 160500 | 0 | 1539500 | 170000 | 1709500 | 0 | 10/23/2024 Heat loads on the 9th floor have changed since original design. Therefore Phoenix Controls is checking the design to see if VAV box sizes need to change. This needs to be figured out before Burns Services orders materials/equipment. Once this is determined, VU will issue the PO to Burns. | 20723
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Warranty or Construction Closeout | Hans Mooy | 1987500 | 1987500 | 1802431.9 | 1802431.9 | 1690674.65 | 185068.1 | 23400 | 1964100 | 0 | 0 | 0 | 0 | 11/25/2024 Project substantially complete. | 20724
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Finalized | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 276500 | 0 | 300000 | -23500 | 0 | 0 | 0 | 0 | 04/23/2024 Project is complete. | 20735
29 | Capital | 20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Warranty or Construction Closeout | Jay Surprenant | 149000 | 148299 | 125699 | 125699 | 125699 | 22600 | 0 | 148299 | 0 | 0 | 0 | 0 | 12/02/2024 Moving through LC process. no change from last month. | 20767
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 |  | 24997 | -7025 | 0 | 0 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space. | 20771
31 | Capital | 20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock | 3200000 | 3200000 | 2936840.14 | 2936840.14 | 1813601 |  | 0 | 1600000 | 1600000 | 0 | 1600000 | 0 | 11/26/2024 Copper work is continuing. Slate installation has started on the vertical surfaces and sloped surfaces. Window installation is completed. Front door is installation is complete. | 20772
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock | 400000 | 483440 | 450775 | 450775 | 450775 |  | 483440 | -32665 | 0 | 0 | 0 | 0 | 12/18/2023 Construction complete. Waiting on final invoices to clear to begin the closeout process. | 20792
33 | Capital | 20811 |  | CP_400224 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Construction | Ben Bedock | 75000 | 285233.27 | 243124.27 | 253063.19 | 52640 |  | 0 | 285233.27 | 0 | 0 | 0 | 0 | 11/26/2024 Funding for the landscape work has been approved and working through contracts to issue the PO. Once landscape work is complete, project is complete. | 20811
34 | Capital | 20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Design | Sean Rewers | 0 | 38500 | 38500 | 38500 | 4500 |  |  |  | 38500 | 361500 | 400000 |  | 11/25/2024 THP is editing drawings to include removing planters, and working around an existing exhaust vent. We expect drawings soon and will get THP to put out to bid. Project is scheduled for summer 2025 | 20812
35 | Operating | 20831 | 8230 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/30/2024 Project is in closeout. Study was completed and findings were shared with Provost and A&S. Due to the large scale renovations needed to the building this project will require further planning and cannot be priced our accurately. A&S will present the findings to their dean for further guidance on how to tackle the buildings issues. | 20831
36 | Operating | 20832 | 8220 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/22/2024 Project study and estimated pricing is complete. Project in closeout. | 20832
37 | Operating | 20833 | 8215 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 04/24/2024 Project is in closeout | 20833
38 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Finalized | Sean Rewers | 5000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/27/2023 This project is on hold until October. We are awaiting approval from the CBO for initial funding which will be repaid by the FRP. | #N/A
39 | Capital | 20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock | 499184 | 499184 | 461612 | 461612 | 139403.42 |  | 0 | 499184 | 0 | 0 | 0 | 0 | 11/26/2024 Construction has started on elevator 1. Temporary inspection for elevator 1 is scheduled for 12/6. With a finial inspection and completion of both elevators scheduled for 01/03/2025. | 20857
40 | Capital | 20884 |  | CP_400251 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Exterior Window Painting | Financial Closeout | Ben Bedock | 675650 | 675650 | 551283 | 551283 | 551283 | 124367 | 0 | 675650 | 0 | 0 | 0 | 0 | 08/23/2024 VUMO is managing this project. CPC is helping with the PO/financial process. | 20884
41 | Operating | 20885 | 8676 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Construction | Sean Rewers | 99000 | 143053.4 | 113596.76 | 113596.76 | 0 |  | 0 | 113053.4 | 30000 | 0 | 30000 | 0 | 11/25/2024 VUMO has confirmed that new VAV is keeping the room cool enough to not require a return system. We are awaiting Atlas to make warranty repairs to the compressors and set up sequencing. | 20885
42 | Operating | 20911 | 8819 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Warranty or Construction Closeout | Ben Bedock | 61045 | 61045 | 54613 | 54613 | 53713 | 6432 | 0 | 61045 | 0 | 0 | 0 | 0 | 11/26/2024 Items are complete. Waiting on final invoice to clear to start the closeout process. | 20911
43 | Operating | 20912 | 8822 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Construction | Ben Bedock | 59798 | 59798 | 53366 | 53366 | 26632.55 |  | 0 | 59798 | 0 | 0 | 0 | 0 | 11/26/2024 Hydraulic jack is in hand and installation to happen over the winter holiday. | 20912
44 | Operating | 20913 | 8818 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Elevator Upgrades | Construction | Ben Bedock | 96612 | 96612 | 86900 | 86900 | 43400.05 |  | 0 | 96612 | 0 | 0 | 0 | 0 | 11/26/2024 Hydraulic jack is in hand and installation to happen over the winter holiday. | 20913
45 | Capital | 20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Exterior Improvements | Warranty or Construction Closeout | Jay Surprenant | 170000 | 197150 | 170000 | 170000 | 170000 | 27150 | 0 | 197150 | 0 | 0 | 0 | 0 | 12/02/2024 Moved to library closeout. waiting on closeout documents from contractor. No change from last month. | 20922
46 | Operating | 20924 |  |  | 19000 - Nursing: Office of the Dean | Nursing | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Warranty or Construction Closeout | Ben Bedock | 30570 | 30570 | 24500 | 24500 | 0 | 6070 | 0 | 30570 | 0 | 0 | 0 | 0 | 11/26/2024 Construction is complete. Waiting on the final invoice to begin the closeout process. | 20924
47 | Capital | 20925 | 8260 |  | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Programming or Planning | Hans Mooy | 2750000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2750000 | 05/21/2024 05/21/24 04/22/2024 03/22/2024 waiting for FY 26 funding | 20925
48 | TBD | 20934 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | NEELY AUDITORIUM | Neely Auditorium - MEP Feasibility Study | Not Started | Sean Rewers |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | TBD | TBD | 0 | Project was cancelled per Aaron Covey and Chris Preston. Email in documents folder. | 20934
49 | Operating | 20936 | 8814 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Warranty or Construction Closeout | Jay Surprenant | 405000 | 404655.91 | 357255.91 | 357255.91 | 267941.93 | 47400 | 0 | 404655.91 | 0 | 0 | 0 | 0 | 12/02/2024 Project completed. Moving to Library Closeout. No change from last month. | 20936
50 | Capital | 20940 |  | CP_400291 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Construction | Sean Rewers | 310000 | 294789 | 253729.9 | 270433.9 | 0 |  | 0 | 0 | 294789 | 0 | 294789 | 0 | 11/25/2024 Project set to start 12/2/24 and run through January. Pre-construction meeting has taken place, equipment is on order. | 20940
51 | Operating | 20945 |  |  | 10000 - Chancellor | Other | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Financial Closeout | Sean Rewers | 99000 | 99000 | 82897 | 82897 | 0 | 16103 | 0 | 99000 | 0 | 0 | 0 | 0 | 11/25/2024 We are awaiting TAB and other reports from Nashville Machine, then we will put into FX. | 20945
52 | Capital | 20957 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - Roof Replacement | Finalized | Hans Mooy | 500000 | 0 | 0 | 0 | 0 | [7 empty] | 05/21/2024 04/23/2024 BAC to be submitted for funding x-fer. 05/21 project on hold | #N/A
53 | Capital | 20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - Elevator Modernization | Construction | Ben Bedock | 290000 | 261629 | 235633 | 235633 | 11175 |  | 0 | 18175 | 243454 | 0 | 243454 | 0 | 11/26/2024 PO has been issued to the contractor. Engineering drawings, review and production has started. Construction to start on 05/13/2025. | 20958
54 | Capital | 20962 | 8754 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Roof Replacement | Programming or Planning | Ben Bedock | 1750000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | TBD | TBD | 0 | 11/26/2024 Met with structural engineer and it was determined that we do not have any major structural issues with the walls of the buildings. We have determined that one wall will included in the scope for a full replacement or until we hit undamaged wood. Working on the scope to prepare for the bidding process. | 20962
55 | Capital | 20979 | 9 |  | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Programming or Planning | Ben Bedock | 270000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 11/25/2024 Working with the appropriate parties to determine the scope of work and the time frame of the work. | 20979
56 | Capital | 20982 |  | CP_400270 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Elevator 1 Modernization | Construction | Ben Bedock | 272000 | 272000 | 246321 | 246321 | 5925 |  | 0 | 18175 | 253825 | 0 | 253825 | 0 | 11/26/2024 PO has been issued to the contractor. Engineering drawings, review and production has started. Construction to start on 05/13/2025. | 20982
57 | Operating | 20984 | 8712 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Construction | Hans Mooy | 167000 | 167000 | 143484.6 | 143484.6 | 0 |  | 0 | 0 | 167000 | 0 | 167000 | 0 | 11/25/2024 Work to commence on Thanksgiving day holiday week. And work will complete during the winter break period. | 20984
58 | Capital | 21004 | 1010 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Programming or Planning | Jay Surprenant | 0 | 54000 | 44000 | 44000 | 0 |  | 0 | 0 | 54000 | TBD | TBD | 0 | 12/02/2024 Design budget approved. Envision has started plan generation. | 21004
59 | Capital | 21005 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | TBD | TBD | TBD | 09/24/2024 This is FY 26 project. No updates to provide yet. Project not started. | 21005
60 | Capital | 21006 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/24/2024 Project not started. this is an FY28 project. | 21006
61 | Capital | 21007 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/24/2024 Project not started. This is an FY29 project. | 21007
62 | TBD | 21010 |  |  | 15000 - Engineering: Office of the Dean | Engineering | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Domestic Water Heat Exchanger Replacement | Not Started | Sean Rewers |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | New project | 21010
63 | TBD | 21051 |  |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 12/02/2024 Project Not Started. Need to engage with engineering group.
[11 empty] | 40520601.76 | 29593862.34 | 25602034.16 | 25628677.08 | 20911058.53 | 782167.26 | 8797286.26 | 11427472.94 | 5205102.14 | 2181500 | 7332602.14 | 8430000
[17 empty] | TRUE | TRUE
[8 empty] | Projects to be added | [8 empty] | TRUE | TRUE | TRUE |  | TRUE
Wilson Hall - HVAC upgrades (phased) (PIs submitted)
Godchaux - upgrades (phased) (Pis to be submitted)
Godchaux - replace roof [Ben]
Projects to be discussed
Law School - replace front stairs ($200k - $400k)
How to handle planned projects in out years (SC-5 21006 / 21007)
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes roof repairs in scope.
Note on L10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on W11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project will be joint funded, FPR / Divinity + Dean of Students.
Note on W19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase 2 estimate. May be a separate project ID.
Note on L28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: wait for HVAC project completion (both phases), FY26? (includes small stairwell section in Frist)

## Summary_by FY
FY 2023 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10085 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 9364499 | 17500 |  | 17500
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Hans Mooy |  | 1216485.5 |  | 1216485.5
| 3 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Sean Rewers |  | 4900 |  | 4900
| 4 | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Bob Grummon |  | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Ben Bedock |  | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Hans Mooy |  | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Cathy Bartlett |  | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Design | Hans Mooy |  | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Ben Bedock |  | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Ben Bedock |  | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Sean Rewers |  | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Ben Bedock |  | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Ben Bedock |  | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Sean Rewers |  | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Design | Hans Mooy |  | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Ben Bedock |  | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Ben Bedock |  | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Sean Rewers |  | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Sean Rewers |  | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Sean Rewers |  | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers |  | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Ben Bedock |  | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Erin Fry |  | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Jay Surprenant |  | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Design | Hans Mooy |  | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Ben Bedock |  | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Sean Rewers |  | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Ben Bedock |  | 483440 |  | 483440
[8 empty] | 8797286.26 | 0 | 8797286.26 | 567212.74
TRUE
FY 2024 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Financial Closeout | Sean Rewers | 11029283.29 | 255957 |  | 255957 |  | phase 1
| 2 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy |  | 3660360 |  | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett |  | 1028900 |  | 1028900
| 4 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 24933 |  | 24933
| 5 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Financial Closeout | Sean Rewers |  | 649263 |  | 649263
| 6 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers |  | 5954 |  | 5954
| 7 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Warranty or Construction Closeout | Hans Mooy |  | 1964100 |  | 1964100
| 8 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Warranty or Construction Closeout | Jay Surprenant |  | 148299 |  | 148299
| 9 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock |  | 1600000 |  | 1600000
| 10 | 20811 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Construction | Ben Bedock |  | 285233.27 |  | 285233.27
| 11 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers |  | 24000 |  | 24000
| 12 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers |  | 24000 |  | 24000
| 13 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Finalized | Sean Rewers |  | 24000 |  | 24000
| 14 | 20857 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock |  | 499184 |  | 499184
| 15 | 20884 | LAW SCHOOL | Law School - Exterior Window Painting | Financial Closeout | Ben Bedock |  | 675650 |  | 675650
| 16 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Construction | Sean Rewers |  | 113053.4 |  | 113053.4
| 17 | 20911 | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Warranty or Construction Closeout | Ben Bedock |  | 61045 |  | 61045
| 18 | 20912 | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Construction | Ben Bedock |  | 59798 |  | 59798
| 19 | 20913 | WILSON HALL | Wilson Hall - Elevator Upgrades | Construction | Ben Bedock |  | 96612 |  | 96612
| 20 | 20922 | VAUGHN HOME | Vaughn Home - Exterior Improvements | Warranty or Construction Closeout | Jay Surprenant |  | 197150 |  | 197150
| 21 | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Warranty or Construction Closeout | Ben Bedock |  | 30570 |  | 30570
| 22 | 20936 | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Warranty or Construction Closeout | Jay Surprenant |  | 404655.91 |  | 404655.91
| 23 | 20945 | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Financial Closeout | Sean Rewers |  | 99000 |  | 99000
| 24 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Construction | Ben Bedock |  | 18175 |  | 18175
| 25 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Construction | Ben Bedock |  | 18175 |  | 18175
|  | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy |  | -4400.96 |  | -4400.96
|  | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Finalized | Ben Bedock |  | -47290 |  | -47290
|  | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock |  | -44850 |  | -44850
|  | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock |  | -36379 |  | -36379
|  | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Finalized | Sean Rewers |  | -43231.36 |  | -43231.36
|  | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock |  | -59283.32 |  | -59283.32
|  | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Finalized | Ben Bedock |  | -119221 |  | -119221
|  | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Finalized | Sean Rewers |  | -22537 |  | -22537
|  | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Finalized | Ben Bedock |  | -58765 |  | -58765
|  | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Finalized | Ben Bedock |  | -11525 |  | -11525 | prior year
|  | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock |  | -29922 |  | -29922 | carryforward
|  | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers |  | -7025 |  | -7025
|  | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock |  | -32665 |  | -32665 | 567212.74
|  | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Finalized | Ben Bedock |  | -23500 |  | -23500
[8 empty] | 11427472.94 | 0 | 11427472.94 | 169023.09
FY 2025 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining | Estimated
| 1 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Hans Mooy | 12857284.4623 | 1077000 | 0 | 1077000 |  | 1300000
| 2 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Award | Sean Rewers |  | 0 | 1650000 | 1650000 |  | 1550000
| 3 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Jay Surprenant |  | 1539500 | 170000 | 1709500 |  | 1610000
| 4 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock |  | 1600000 | 0 | 1600000 |  | 3200000
| 5 | 20812 | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Design | Sean Rewers |  | 38500 | 361500 | 400000 |  | 0
| 6 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Construction | Sean Rewers |  | 30000 | 0 | 30000
| 7 | 20934 | NEELY AUDITORIUM | Neely Auditorium - MEP Feasibility Study | Not Started | Sean Rewers |  | 0 | TBD | 0 |  | 0
| 8 | 20940 | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Construction | Sean Rewers |  | 294789 | 0 | 294789 |  | 310000
| 9 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Construction | Ben Bedock |  | 243454 | 0 | 243454 |  | 290000
| 10 | 20962 | VAUGHN HOME | Vaughn Home - Roof Replacement | Programming or Planning | Ben Bedock |  | 0 | TBD | 0 | prior year | 1750000
| 11 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Construction | Ben Bedock |  | 253825 | 0 | 253825 |  | 272000
| 12 | 20984 | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Construction | Hans Mooy |  | 167000 | 0 | 167000 | 169023.09 | 167000
| 13 | 21004 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Programming or Planning | Jay Surprenant |  | 54000 | TBD | 54000 |  | 0
| 14 | 21010 | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Domestic Water Heat Exchanger Replacement | Not Started | Sean Rewers |  | 0 | 0 | 0 |  | 0
|  | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Finalized | Bob Grummon |  | -92965.86 | 0 | -92965.86
[8 empty] | 5205102.14 | 2181500 | 7386602.14 | 5639705.4123 | 10449000
FY 2026 |  | eBuilder | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Programming or Planning | Hans Mooy | 0 |  | 3170000 | 3170000
| 2 | 20925 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Programming or Planning | Hans Mooy |  |  | 2750000 | 2750000
| 3 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  |  | TBD | TBD
| 4 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock |  |  | TBD | TBD
| 5 | 20979 | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Programming or Planning | Ben Bedock |  |  | TBD | TBD
| 6 | 21005 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Programming or Planning | Jay Surprenant |  |  | TBD | TBD
| 7 | 21006 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Programming or Planning | Jay Surprenant |  |  | 0 | 0
| 8 | 21007 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Programming or Planning | Jay Surprenant |  |  | 0 | 0
[8 empty] | 0 | 5920000 | 5920000 | -5920000
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Preliminary cost estimates presented in three options. $4M - $5M range.

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 22000 | 17500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 0

## 10098 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy | 1216485.5 | 1212084.54
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | crowhus_01302024_FRP | FX2-1 |  | -4400.96
|  |  |  | Total transfers from FRP cash |  |  | 1212084.54
|  |  |  | Balance |  |  | 0

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Financial Closeout | Sean Rewers | 318057
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | crowhus_01302024_FRP | BAC-5 |  | 244457
|  |  |  | FY24 subtotal |  |  | 255957
|  |  |  | Balance |  |  | 0

## 20179 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Finalized | Bob Grummon | 1445389 | 1352423.14
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
|  |  |  | crowhus_08312024_FRP |  |  | -92965.86
1352423.14
|  |  |  | Total transfers from FRP cash |  |  | 629728.64
|  |  |  | Balance |  |  | 0

## 20336 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Finalized | Ben Bedock | 327890 | 280600
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -47290
|  |  |  | Total transfers from FRP cash |  |  | 280600
|  |  |  | Balance |  |  | 0

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy | 3800000
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360
All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
3800000
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2652824.48
[9 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 |  | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 |  | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 |  | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
[7 empty] | 2790000 |  | 1110000 | 1680000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Programming or Planning | Hans Mooy | 26500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Finalized | Ben Bedock | 456850 | 412000
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -44850
|  |  |  | Total transfers from FRP cash |  |  | 412000
|  |  |  | Balance |  |  | 0

## 20506 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Finalized | Ben Bedock | 344155.26 | 307776.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -36379
|  |  |  | Total transfers from FRP cash |  |  | 307776.26
|  |  |  | Balance |  |  | 0

## 20562 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Finalized | Sean Rewers | 405791 | 362559.64
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -43231.36
|  |  |  | Total transfers from FRP cash |  |  | 362559.64
|  |  |  | Balance |  |  | 0

## 20566 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock | 781870 | 722586.68
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | crowhus_02292024_FRP | FX |  | -59283.32
|  |  |  | Total transfers from FRP cash |  |  | 722586.68
|  |  |  | Balance |  |  | 0

## 20573 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Finalized | Ben Bedock | 1232681 | 1113460
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -119221
|  |  |  | Total transfers from FRP cash |  |  | 1113460
|  |  |  | Balance |  |  | 0

## 20574 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Finalized | Sean Rewers | 218202 | 195665
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -22537
|  |  |  | Total transfers from FRP cash |  |  | 195665
|  |  |  | Balance |  |  | 0

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Hans Mooy | 1300000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | crowhus_10312024_FRP | BAC-4 |  | 1077000
|  |  |  | Total transfers from FRP cash |  |  | 1300000
|  |  |  | Balance |  |  | 0

## 20644 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Finalized | Ben Bedock | 630554 | 571789
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -58765
|  |  |  | Total transfers from FRP cash |  |  | 571789
|  |  |  | Balance |  |  | 0

## 20645 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Finalized | Ben Bedock | 125875 | 114350
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | crowhus_04302024_FRP | FX2-1 |  | -11525
|  |  |  | Total transfers from FRP cash |  |  | 114350
|  |  |  | Balance |  |  | 0

## 20667
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Award | Sean Rewers | 146500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | Total transfers from FRP cash |  |  | 146500
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 231433
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_10312023_FRP | BAC-4 |  | 24933
|  |  |  | Total transfers from FRP cash |  |  | 231433
|  |  |  | Balance |  |  | 0

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Financial Closeout | Sean Rewers | 678513
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | crowhus_01302024_FRP | BAC-4 | ` | 649263
|  |  |  | Total transfers from FRP cash |  |  | 678513
|  |  |  | Balance |  |  | 0

## 20700 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers | 85577 | 85576.77
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | 0

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Award | Sean Rewers | 499093
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock | 239341 | 209419
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | crowhus_02292024_FRP | FX |  | -29922
|  |  |  | Total transfers from FRP cash |  |  | 209419
|  |  |  | Balance |  |  | 0

## 20718 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Finalized | Erin Fry | 715000 | 656784.6
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Jay Surprenant | 1700000
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | crowhus_10312024_FRP |  |  | 1539500
|  |  |  | Total transfers from FRP cash |  |  | 1700000
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line - FY 23 | Warranty or Construction Closeout | Hans Mooy | 1987500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | crowhus_12192023_FRP | BAC-2 |  | 1964100
|  |  |  | Total transfers from FRP cash |  |  | 1987500
|  |  |  | Balance |  |  | 0

## 20735 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Finalized | Ben Bedock | 300000 | 276500
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | crowhus_06302024_FRP | FX2-1 |  | -23500
|  |  |  | Total transfers from FRP cash |  |  | 276500
|  |  |  | Balance |  |  | 0

## 20767
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Six Magnolia Circle - Foundation Repairs | Warranty or Construction Closeout | Jay Surprenant | 148299 | 125699
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 148299
|  |  |  | Total transfers from FRP cash |  |  | 148299
|  |  |  | Balance |  |  | 0

## 20771 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers | 24997 | 17972
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -7025
|  |  |  | Total transfers from FRP cash |  |  | 17972
|  |  |  | Balance |  |  | 0

## 20792 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock | 483440 | 450775
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | crowhus_02292024_FRP | FX |  | -32665
|  |  |  | Total transfers from FRP cash |  |  | 450775
|  |  |  | Balance |  |  | 0

## 20831 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20831 | 8230 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20832 | 8220 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20833 | 8215 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement (Design Services) | Finalized | Sean Rewers | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20772
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock | 3200000
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 1600000
|  |  |  | crowhus_07312024_FRP | BAC-1 |  | 1600000
|  |  |  | Total transfers from FRP cash |  |  | 3200000
|  |  |  | Balance |  |  | 0

## 20811
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20811 | 0 | CP_400224 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Retaining Wall Repair | Construction | Ben Bedock | 285233.27
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 285233.27
|  |  |  | Total transfers from FRP cash |  |  | 285233.27
|  |  |  | Balance |  |  | 0
Original budget (BAC-1) for $2,640 set up as a Facilities capital project, owning org 37000. It has been determined this is an FRP project and will be assigned to Peabody. Owning org has been updated in Oracle.

## 20812
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Patio Repairs | Design | Sean Rewers | 38500
Funding transfers
|  |  |  | crowhus_08312024_FRP | BAC-1 |  | 4500
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 34000
|  |  |  | Total transfers from FRP cash |  |  | 38500
|  |  |  | Balance |  |  | 0

## 20857
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock | 499184
Funding transfers
|  |  |  | crowhus_10312023_FRP | BAC-1 |  | 17600
|  |  |  | crowhus_01302024_FRP | BAC-2 |  | 4000
|  |  |  | crowhus_03312024_FRP | BAC-3 |  | 477584
|  |  |  | Total transfers from FRP cash |  |  | 499184
|  |  |  | Balance |  |  | 0

## 20884
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20884 | 0 | CP_400251 | 17100 - Law: Business Affairs | Law School - Exterior Window Painting | Financial Closeout | Ben Bedock | 675650
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-3 |  | 675650
|  |  |  | Total transfers from FRP cash |  |  | 675650
|  |  |  | Balance |  |  | 0

## 20885
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20885 | 8676 | 0 | 12000 - Arts and Science: Office of the Dean | NMR - Replace Air Compressors | Construction | Sean Rewers | 143053.4
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-2 |  | 98341
|  |  |  | crowhus_05312024_FRP | BAC-3 |  | 14712.4
|  |  |  | crowhus_09302024_FRP | BAC-4 |  | 30000
|  |  |  | Total transfers from FRP cash |  |  | 143053.4
|  |  |  | Balance |  |  | 0

## 20911
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20911 | 8819 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Elevator Upgrades | Warranty or Construction Closeout | Ben Bedock | 61045
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 56945
|  |  |  | Total transfers from FRP cash |  |  | 61045
|  |  |  | Balance |  |  | 0

## 20912
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20912 | 8822 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Hall - Elevator Upgrades | Construction | Ben Bedock | 59798
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 55698
|  |  |  | Total transfers from FRP cash |  |  | 59798
|  |  |  | Balance |  |  | 0

## 20913
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20913 | 8818 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Elevator Upgrades | Construction | Ben Bedock | 96612
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 92512
|  |  |  | Total transfers from FRP cash |  |  | 96612
|  |  |  | Balance |  |  | 0

## 20922
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Vaughn Home - Exterior Improvements | Warranty or Construction Closeout | Jay Surprenant | 197150
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 197150
|  |  |  | Total transfers from FRP cash |  |  | 197150
|  |  |  | Balance |  |  | 0

## 20924
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20924 | 0 | 0 | 19000 - Nursing: Office of the Dean | Frist Hall - Stairwell Roof Replacement | Warranty or Construction Closeout | Ben Bedock | 30570
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 30570
|  |  |  | Total transfers from FRP cash |  |  | 30570
|  |  |  | Balance |  |  | 0

## 20936
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20936 | 8814 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Lighting Retrofit for 103 and 126 | Warranty or Construction Closeout | Jay Surprenant | 404655.91
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 404655.91
|  |  |  | Total transfers from FRP cash |  |  | 404655.91
|  |  |  | Balance |  |  | 0

## 20940
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20940 | 0 | CP_400291 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Security System Replacement | Bidding | Rewers, Sean | 0
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 294789
|  |  |  | Total transfers from FRP cash |  |  | 294789
|  |  |  | Balance |  |  | -294789

## 20945
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20945 | 0 | 0 | 10000 - Chancellor | Seigenthaler Building - HVAC Improvements | Financial Closeout | Sean Rewers | 99000
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 99000
|  |  |  | Total transfers from FRP cash |  |  | 99000
|  |  |  | Balance |  |  | 0

## 20958
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Furman Hall - Elevator Modernization | Construction | Ben Bedock | 261629
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 243454
|  |  |  | Total transfers from FRP cash |  |  | 261629
|  |  |  | Balance |  |  | 0

## 20982
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20982 | 0 | CP_400270 | 17100 - Law: Business Affairs | Law School - Elevator 1 Modernization | Construction | Ben Bedock | 272000
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_10312024_FRP | BAC-2 |  | 253825
|  |  |  | Total transfers from FRP cash |  |  | 272000
|  |  |  | Balance |  |  | 0

## 20984
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20984 | 8712 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - 1st Floor Urinal Replacement | Construction | Hans Mooy | 167000
Funding transfers
|  |  |  | crowhus_09302024_FRP | BAC-1 |  | 167000
|  |  |  | Total transfers from FRP cash |  |  | 167000
|  |  |  | Balance |  |  | 0

## 21004
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
21004 | 1010 | 0 | 12100 - Arts and Science: Business Affairs | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Programming or Planning | Jay Surprenant | 0
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 54000
|  |  |  | Total transfers from FRP cash |  |  | 54000
|  |  |  | Balance |  |  | -54000

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
Sources
| crowhus_08072023_FRP | 11029283.29
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| crowhus_10312023_FRP | -45721
| crowhus_12192023_FRP | 1964100
| crowhus_01302024_FRP | 893319.04
| crowhus_02292024_FRP | -11229.32
| crowhus_03312024_FRP | 638993.64
| crowhus_04302024_FRP | 1384584.18
| crowhus_05312024_FRP | 230037.4
| crowhus_06302024_FRP | 1594675
| Total Uses | 11427472.94
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 169023.09 | DB: | CR:
|  |  | 7025 | 24933
|  |  | 36379 | 17600
44850
|  |  | 88254 | 42533 | 130787
-45721
|  |  | DB: | CR:
|  |  | 1964100 | 1964100
|  |  | 1964100 | 1964100
|  |  | 3928200 | 3928200
0
|  |  | DB: | CR:
649263
244457
4000
4400.96
|  |  | 4400.96 | 897720 | 902120.96
893319.04
|  |  | DB: | CR:
12300
98341
59283.32
29922
32665
|  |  | 121870.32 | 110641 | 232511.32
-11229.32
|  |  | DB: | CR:
148299
|  |  | 47290 | 477584
|  |  | 43231.36 | 56945
|  |  | 119221 | 55698
|  |  | 22537 | 92512
|  |  | 58765 | 99000
|  |  | 291044.36 | 930038 | 1221082.36
638993.64
|  |  | DB: | CR:
285233.27
675650
30570
404655.91
11525
|  |  | 11525 | 1396109.18 | 1407634.18
1384584.18
|  |  | 460074.8 | 230037.4
|  |  | DB: | CR:
18175
1600000
23500
|  |  | 23500 | 1618175 | 1641675
1594675

## JE LOG_FY25
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 12857284.4623 | tbd | 0
| Total sources | 12857284.4623
Uses
| crowhus_07312024_FRP | 1600000
| crowhus_08312024_FRP | 188988.14
| crowhus_09302024_FRP | 197000
| crowhus_10312024_FRP | 3219114
| Total Uses | 5205102.14
| plus carryforward | 169023.09
| (less) TBD | 0 |  |  | DB: | CR:
38500
| Balance | 7821205.4123 |  |  |  | 243454
92965.86
[5 empty] | 92965.86 | 281954 | 374919.86
188988.14

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody
19000 - Nursing: Office of the Dean | Nursing

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.