## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.
Notes about upcoming planning

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2025-02-06
School | GSF | FY23 - FY25 Cumulative Contribution | FY23 Funded Projects | FY24 Funded Projects | FY25 Estimated Projects | Contribution vs. Funded
Arts & Science | 1075461.7321 | 12747868.731 | 2276289.625 | 2619344.704 | 3035079 | 4817155.402
Blair | 121421.4269 | 1496829.2818 | 574290 | 1916810 | 1077000 | -2071270.7182
Divinity | 57814.7309 | 692779.0038 | 96362.5 | 3660360 | 0 | -3063943.4962
Engineering | 537962.3327 | 6515613.1943 | 353000 | 24933 | 2308408.64 | 3829271.5543
Law | 120155.4846 | 1427819.0631 | 1206134.5 | 661160 | 160859.14 | -600334.5769
SOM Basic Sciences | 280022.3999 | 3441675.5551 | 1036871.875 | -17509.674 | 1000675 | 1421638.3541
Nursing | 106166.7 | 1261583.3214 | 4900 | 286527 | 0 | 970156.3214
Owen | 59008.3617 | 1046789.5035 | 300000 | 1576500 | 1600000 | -2429710.4965
Peabody | 390796.8848 | 4620109.0983 | 2949437.76 | 600347.91 | 0 | 1070323.4283
| 2748810.0535 | 33251066.7523 | 8797286.26 | 11328472.94 | 9182021.78 | 3943285.7723
Estimated funded projects is anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2025-02-06
| Projects |  |  |  | (1) | (2) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP Funding | FY24 FRP Funding | FY25 FRP Funding
1 | Complete | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0 | 0
2 | Complete | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | -4400.96 | 0
3 | Active | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 318000 | 4900 | 255957 | 0
4 | Complete | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0 | -92965.86
5 | Complete | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | -47290 | 0
6 | Active | 20431 | Divinity | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 69862.5 | 3660360 | 0
7 | Active | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2790000 | 81100 | 1028900 | 0
8 | Active | 20489 | Divinity | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | 4750000 | 26500 | 0 | 0
9 | Complete | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | -44850 | 0
10 | Complete | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | -36379 | 0
11 | Complete | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | -43231.36 | 0
12 | Deferred / On Hold | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0 | 0
13 | Complete | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | -59283.32 | 0
14 | Complete | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | -119221 | 0
15 | Complete | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | -22537 | 0
16 | Active | 20577 | Blair | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | 1300000 | 223000 | 0 | 1077000
17 | Complete | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | -58765 | 0
18 | Complete | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | -11525 | 0
19 | Active | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 1550000 | 146500 | 0 | 1398860
20 | Active | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | 24933 | 0
21 | Active | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 680000 | 29250 | 649263 | 0
22 | Complete | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 5954 | 0
23 | Active | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0 | 0
24 | Complete | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | -29922 | 0
25 | Complete | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0 | 0
26 | Active | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500 | 0 | 1539500
27 | Active | 20724 | Blair | Blair School of Music - Steam Line - FY 23 | 1987500 | 23400 | 1964100 | 0
28 | Complete | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | -23500 | 0
29 | Active | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 149000 | 0 | 148299 | 0
30 | Complete | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | -7025 | 0
31 | Active | 20772 | Owen | OGSM Old Mechanical- Slate Roof & Window Replacement | 3200000 | 0 | 1600000 | 1600000
32 | Complete | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | -32665 | 0
33 | Active | 20811 | Peabody | One Magnolia Circle - Retaining Wall Repair | 75000 | 0 | 285233.27 | 0
34 | Active | 20812 | Engineering | 1025 16th Avenue - Patio Repairs | 600000 | 0 | 0 | 600000
35 | Complete | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 24000 | 0
36 | Complete | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 24000 | 0 | 24000 | 0
37 | Complete | 20833 | Arts & Science | SC5 - HVAC Replacement (Design Services) | 24000 | 0 | 24000 | 0
38 | Voided | 20834 | Peabody | Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0 | 0 | 0
39 | Active | 20857 | Peabody | One Magnolia Circle - Elevator Modernization | 499184 | 0 | 499184 | 0
40 | Active | 20884 | Law | Law School - Exterior Window Painting | 675650 | 0 | 675650 | 0
41 | Active | 20885 | Arts & Science | NMR - Replace Air Compressors | 99000 | 0 | 113053.4 | 30000
42 | Active | 20911 | Arts & Science | Buttrick Hall - Elevator Upgrades | 61045 | 0 | 61045 | 0
43 | Active | 20912 | Arts & Science | Benson Hall - Elevator Upgrades | 59798 | 0 | 59798 | 0
44 | Active | 20913 | Arts & Science | Wilson Hall - Elevator Upgrades | 96612 | 0 | 96612 | 0
45 | Active | 20922 | Arts & Science | Vaughn Home - Exterior Improvements | 170000 | 0 | 197150 | 0
46 | Active | 20924 | Nursing | Frist Hall - Stairwell Roof Replacement | 30570 | 0 | 30570 | 0
47 | Active | 20925 | Blair | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | 2750000 | 0 | 0 | 0
48 | Voided | 20934 | Arts & Science | Neely Auditorium - MEP Feasibility Study | 0 | 0 | 0 | TBD
49 | Active | 20936 | Arts & Science | Wilson Hall - Lighting Retrofit for 103 and 126 | 405000 | 0 | 404655.91 | 0
50 | Active | 20940 | Engineering | 1025 16th Avenue - Security System Replacement | 310000 | 0 | 0 | 309548.64
51 | Active | 20945 | Other | Seigenthaler Building - HVAC Improvements | 99000 | 0 | 99000 | 0
52 | Voided | 20957 | Arts & Science | SC6 - Roof Replacement | 500000 | 0 | 0 | 0
53 | Active | 20958 | Arts & Science | Furman Hall - Elevator Modernization | 290000 | 0 | 18175 | 243454
54 | Active | 20962 | Arts & Science | Vaughn Home - Roof Replacement | 1750000 | 0 | 0 | 2001800
55 | Active | 20979 | Engineering | 1025 16th Avenue - Roof Replacement | 270000 | 0 | 0 | 0
56 | Active | 20982 | Law | Law School - Elevator 1 Modernization | 272000 | 0 | 18175 | 253825
57 | Active | 20984 | Arts & Science | Wilson Hall - 1st Floor Urinal Replacement | 167000 | 0 | 0 | 167000
58 | Active | 21004 | Arts & Science | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | 0 | 0 | 0 | 54000
59 | Deferred / On Hold | 21005 | Arts & Science | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | 0 | 0 | 0 | 0
60 | Deferred / On Hold | 21006 | Engineering | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | 0 | 0 | 0 | 0
61 | Deferred / On Hold | 21007 | Engineering | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | 0 | 0 | 0 | 0
62 | Active | 21010 | Engineering | Featheringill-Jacobs Hall - Hot Water Tank Replacement | 30000 | 0 | 0 | 0
63 | Active | 21051 | SOM Basic Sciences | MRBIII - 5th Floor Controls | 0 | 0 | 0 | 0
64 | Active | 21066 | Arts & Science | SC2 - MEP Feasibility Study | 0 | 0 | 0 | 0
65 | Active | 21067 | Nursing | Godchaux Hall - Phase 2 HVAC Upgrades | 0 | 0 | 0 | 0
66 | Active | 21068 | Arts & Science | Buttrick Hall - Insulate First Floor Slab | 0 | 0 | 0 | 0
67 | Active | 21070 | Engineering | Olin Hall - Exterior Facade Cleaning | 0 | 0 | 0 | 0
68 | Active | 21071 | Arts & Science | SC1 - MEP Feasibility Study | 0 | 0 | 0 | 0
69 | Active | 21072 | Arts & Science | Calhoun Hall - MEP Feasibility Study | 0 | 0 | 0 | 0
70 | Active | 21073 | Arts & Science | Furman Hall - MEP Feasibility Study | 0 | 0 | 0 | 0
71 | Active | 21074 | Law | Law School - MEP Feasibility Study | 0 | 0 | 0 | 0
72 | Active | 21076 | #N/A | 2500 Kensington Place - Sewer Line Replacement | 0 | 0 | 0 | 0
73 | Active | 21094 | Nursing | Godchaux Hall - Replace Fire Pump | 0 | 0 | 0 | 0
74 | Active | 21107 | Blair | Blair School of Music - Locker Replacement | 0 | 0 | 0 | 0
75 | Active | 21108 | Engineering | 1025 16th Avenue - Electrical and HVAC Study | 5000 | 0 | 0 | 0
76 | Active | 21113 | SOM Basic Sciences | MRBIII - Lecture Hall V1220 Lighting Upgrade | 0 | 0 | 0 | 0
77 | Active | 21114 | SOM Basic Sciences | MRBIII - Chemical Discharge Tank Replacement | 0 | 0 | 0 | 0
[5 empty] | 41255601.76 | 8797286.26 | 11427472.94 | 9182021.78
Estimated total budget represents the best rough order of magnitude for total project costs.
FYxx FRP funding indicates anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25 |  |  | Facility Renewal Program: Contributions - FY26
|  | 3.41 |  |  | 3.97 |  |  | 4.54 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141 | Arts & Science | 1168519.772 | 5305079.765
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118 | Blair | 121417.211 | 551234.1379
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938 | College of Connected Computing | 42638.0889 | 193576.9234
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343 | Divinity | 58286.9615 | 264622.8051
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131 | Engineering | 490439.8851 | 2226597.0781
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78 | SOM Basic Sciences | 315635.413 | 1432984.7751 | Law | 119265.3553 | 541464.7131
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62 | Nursing | 105746.41 | 480088.7014 | Nursing | 105746.45 | 480088.883
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035 | Owen | 99610.0673 | 452229.7056
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883 | Peabody | 381580.0251 | 1732373.3138
[9 empty] | SOM Basic Sciences | 334042.3631 | 1516552.3283
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623 |  | 2921546.1792 | 13263819.6534
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623 | Contribution |  | 13263819.6534
Anticipated spend |  | 8797286.26 | Anticipated spend |  | 11427472.94 | Anticipated spend |  | 9182021.78 | Anticipated spend |  | 0
Remaining funds |  | 567212.74 | Remaining funds |  | -398189.65 | Remaining funds |  | 3675262.6823 | Remaining funds |  | 13263819.6534
TRUE

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 FRP funding | MRB III Adj | FY24 FRP | Contribution vs. FY24 FRP funding | FY25 Contribution | FY25 estimated FRP funding | MRB III Adj | FY25 FRP | Contribution vs. FY25 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 2.6288 | -0.0094283 | 2.6193 | 1.5855 | 4.8792 | 2.4963 | 0.53882 | 3.0351 | 1.8442
Blair | 121421.4269 | 0.41365 | 0.57429 |  | 0.57429 | -0.16064 | 0.48204 | 1.9168 |  | 1.9168 | -1.4348 | 0.60114 | 1.077 |  | 1.077 | -0.47586
Divinity | 57814.7309 | 0.19696 | 0.096363 |  | 0.096363 | 0.1006 | 0.2313 | 3.6604 |  | 3.6604 | -3.4291 | 0.26451 | 0 |  | 0 | 0.26451
Engineering | 537962.3327 | 1.8327 | 0.353 |  | 0.353 | 1.4797 | 2.1933 | 0.024933 |  | 0.024933 | 2.1684 | 2.4896 | 2.3084 |  | 2.3084 | 0.18117
Law | 120155.4846 | 0.40934 | 1.2061 |  | 1.2061 | -0.7968 | 0.47702 | 0.66116 |  | 0.66116 | -0.18414 | 0.54146 | 0.16086 |  | 0.16086 | 0.38061
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | -0.026938 | 0.0094283 | -0.01751 | 1.0722 | 1.433 | 1.5395 | -0.53882 | 1.0007 | 0.43231
Nursing | 106166.7 | 0.36168 | 0.0049 |  | 0.0049 | 0.35678 | 0.41981 | 0.28653 |  | 0.28653 | 0.13328 | 0.48009 | 0 |  | 0 | 0.48009
Owen | 59008.3617 | 0.20103 | 0.3 |  | 0.3 | -0.098973 | 0.39359 | 1.5765 |  | 1.5765 | -1.1829 | 0.45218 | 1.6 |  | 1.6 | -1.1478
Peabody | 390796.8848 | 1.3313 | 2.9494 |  | 2.9494 | -1.6181 | 1.5726 | 0.60035 |  | 0.60035 | 0.9723 | 1.7161 | 0 |  | 0 | 1.7161
| 2748810.0535 | 9.3645 | 8.7973 |  | 8.7973 | 0.56721 | 11.0293 | 11.3285 |  | 11.3285 | -0.29919 | 12.8573 | 9.182 |  | 9.182 | 3.6753
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24 |  |  |  |  | FY25
MRB III BIO/SCI |  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1539500
A&S |  |  | 558315.625 |  |  |  |  | -9428.286 |  |  |  |  | 538825
SOM |  |  | 1036871.875 |  |  |  |  | -17509.674 |  |  |  |  | 1000675
|  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1539500

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
21000 - Peabody College: Office of the Dean | 4035715.26 | 4264088.53
Construction | 723184 | 932716.27
Six Magnolia Circle - Foundation Repairs | 149000 | 148299
One Magnolia Circle - Elevator Modernization | 499184 | 499184
One Magnolia Circle - Retaining Wall Repair | 75000 | 285233.27
Finalized | 3312531.26 | 3331372.26
Jesup - Roof Replacement | 456850 | 456850
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000
Peabody Administration - Envelope Repairs | 630554 | 630554
Wyatt Center - Elevator #2 Modernization | 225791 | 239341
Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0
Wyatt Center - Roof Replacement | 1232681 | 1232681
Wyatt Center - VAV Replacement | 400000 | 405791
Wyatt Center - Window Replacement | 344155.26 | 344155.26
Grand Total | 4035715.26 | 4264088.53
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Status
Facility Renewal Program: Projects | [17 empty] | JE LOG_FY23'!A1 | JE LOG_FY24'!A1 |  |  | JE LOG_FY25'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Project Status | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Unallocated Reserve | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY25 FRP Transferred | FY25 FRP Estimated | FY25 FRP Total Contribution | FY26 FRP Estimated | Project status update | Check
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout. | 10085
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized | Hans Mooy | 1216485.5 | 1216485.5 | 1212084.54 | 1212084.54 | 1212084.54 | 0 | 1216485.5 | -4400.96 | 0 | 0 | 0 | 0 | 08/22/2023 project complete | 10098
3 | Capital | 10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Active | Financial Closeout | Sean Rewers | 318000 | 318057 | 253826.81 | 253826.81 | 253826.81 | 64230.19 | 4900 | 255957 | 0 | 0 | 0 | 0 | 09/26/2024 Project is in library closeout. Will complete financial closeout after. | 10146
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Fire Alarm System Replacement | Complete | Finalized | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 |  | 722694.5 | 0 | -92965.86 | 0 | -92965.86 | 0 | 07/29/2024 work is complete | 20179
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Complete | Finalized | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 280600 |  | 327890 | -47290 | 0 | 0 | 0 | 0 | 01/22/2024 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20336
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Active | Warranty or Construction Closeout | Hans Mooy | 3800000 | 3800000 | 3618276.67 | 3620301.67 | 3470398.86 | 191010.33 | 69862.5 | 3660360 | 0 | 0 | 0 | 0 | 01/22/2025 Project Complete | 20431
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Active | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2790000 | 2652824.48 | 2652824.48 | 2652824.48 | 0 | 81100 | 1028900 | 0 | 0 | 0 | 0 | 01/25/2025 Door hardware will be replaced early 2025 then the project will be closed out. | 20478
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Active | Design | Hans Mooy | 4750000 | 26500 | 15895 | 15895 | 14407.5 |  | 26500 | 0 | 0 | 0 | 0 | 3170000 | 01/22/2025 Kick off/page flip meeting to occur in February 2025. | 20489
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Complete | Finalized | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 |  | 79415.5 | -44850 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20497
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Complete | Finalized | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 |  | 344155.26 | -36379 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20506
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Complete | Finalized | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 |  | 405791 | -43231.36 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20562
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Deferred / On Hold | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | On hold per FRP 07/24/2024 until summer of 2026 | 20563
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 722586.68 |  | 781870 | -59283.32 | 0 | 0 | 0 | 0 | 11/22/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20566
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Complete | Finalized | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 1113460 |  | 1232681 | -119221 | 0 | 0 | 0 | 0 | 01/22/2024 Project is complete. Waiting on final invoice to clear to begin the closeout process. | 20573
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Complete | Finalized | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 195665 |  | 218202 | -22537 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20574
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Active | Construction | Hans Mooy | 1300000 | 1300000 | 1092354.21 | 1092354.21 | 259050.21 |  | 223000 | 0 | 1077000 | 0 | 1077000 | 2510000 | 01/22/2025 AHU in production, delivery is 24 weeks out (May 2025). Meeting scheduled in late January. | 20577
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Complete | Finalized | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 571789 |  | 630554 | -58765 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20644
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Complete | Finalized | Ben Bedock | 125875 | 125875 | 114350 | 114350 | 114350 |  | 125875 | -11525 | 0 | 0 | 0 | 0 | 02/26/2024 Punchlist items have been discussed with the contractor. Once items are completed, project is ready to closeout. | 20645
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Active | Award | Sean Rewers | 1550000 | 1545360 | 1355049 | 1355049 | 119500 |  | 146500 | 0 | 1398860 | 0 | 1398860 | 0 | 01/23/2025 PO has been issued and we are awaiting submittals for equipment. We want to get these ordered asap so we can install in summer 2025, mitigate lead time. Actual construction to start in late spring. | 20667
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design | Sean Rewers | 0 | 231433 | 231433 | 231433 | 116143 |  | 206500 | 24933 | 0 | 0 | 0 | TBD | 01/28/2025 We are awaiting definitive plans from the CUI project to determine where our chilled water connection will be. If hot water goes past the building as part of CUI we will rework the design to include hot water connection. | 20668
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Active | Financial Closeout | Sean Rewers | 680000 | 678513 | 586776.36 | 586776.36 | 586776.36 | 91736.64 | 29250 | 649263 | 0 | 0 | 0 | 0 | 11/25/2024 Project in FX | 20698
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 85576.77 |  | 79623 | 5954 | 0 | 0 | 0 | 0 | 11/27/2023 Project is in closeout | 20700
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Active | Construction | Sean Rewers | 500000 | 499093 | 419024.05 | 419024.05 | 247130 |  | 499093 | 0 | 0 | 0 | 0 | 0 | 01/28/2025 New tanks and bypass was installed over winter break. We issued a CO to add in grating around the tanks and a ladder for easier access. We are awaiting a few parts for the discharge system and will schedule an outage with help from building occupants. | 20701
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Complete | Finalized | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 209419 |  | 239341 | -29922 | 0 | 0 | 0 | 0 | 12/18/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20702
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Complete | Finalized | Erin Fry | 715000 | 715000 | 656784.6 | 656784.6 | 656576.59 |  | 96166 | 0 | 0 | 0 | 0 | 0 | 02/23/2024 Construction complete. Library Closeout process complete. The Financial closeout process has been started. | 20718
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Active | Award | Jay Surprenant | 1610000 | 1700000 | 511232.52 | 1521240.72 | 138595.02 |  | 160500 | 0 | 1539500 | 0 | 1539500 | 0 | 02/05/2025 PO is in process. Once completed, work will begin. Pre-exploratory work has been completed of above ceiling conditions, VAVs in need of replacement have been identified. Targeting March to begin work. | 20723
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Active | Warranty or Construction Closeout | Hans Mooy | 1987500 | 1987500 | 1819618.65 | 1819618.65 | 1785460.4 | 185068.1 | 23400 | 1964100 | 0 | 0 | 0 | 0 | 01/22/2025 Project substantially complete. | 20724
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Complete | Finalized | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 276500 | 0 | 300000 | -23500 | 0 | 0 | 0 | 0 | 04/23/2024 Project is complete. | 20735
29 | Capital | 20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Active | Warranty or Construction Closeout | Jay Surprenant | 149000 | 148299 | 125699 | 125699 | 125699 | 22600 | 0 | 148299 | 0 | 0 | 0 | 0 | 01/29/2025 Moving through LC process. no change from last month. | 20767
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 |  | 24997 | -7025 | 0 | 0 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space. | 20771
31 | Capital | 20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction | Ben Bedock | 3200000 | 3200000 | 2936840.14 | 2936840.14 | 2911828.14 |  | 0 | 1600000 | 1600000 | 0 | 1600000 | 0 | 01/22/2025 Project is 99% complete. Scaffolding has been removed. Items that remain are one downspout, basement window painting and grate painting. | 20772
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized | Ben Bedock | 400000 | 483440 | 450775 | 450775 | 450775 |  | 483440 | -32665 | 0 | 0 | 0 | 0 | 12/18/2023 Construction complete. Waiting on final invoices to clear to begin the closeout process. | 20792
33 | Capital | 20811 |  | CP_400224 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Active | Warranty or Construction Closeout | Ben Bedock | 75000 | 285233.27 | 253063.19 | 253063.19 | 121573.71 |  | 0 | 285233.27 | 0 | 0 | 0 | 0 | 01/22/2025 Project is complete. Waiting on final invoices to clear to begin the closeout process. | 20811
34 | Capital | 20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Active | Design | Sean Rewers | 600000 | 38500 | 38500 | 38500 | 4500 |  |  |  | 38500 | 561500 | 600000 |  | 01/23/2025 THP has completed the majority of design, we are getting input on lighting and possibly fencing as final part of design. THP will bid out in the spring and work will start late summer 2025 | 20812
35 | Operating | 20831 | 8230 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/30/2024 Project is in closeout. Study was completed and findings were shared with Provost and A&S. Due to the large scale renovations needed to the building this project will require further planning and cannot be priced our accurately. A&S will present the findings to their dean for further guidance on how to tackle the buildings issues. | 20831
36 | Operating | 20832 | 8220 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/22/2024 Project study and estimated pricing is complete. Project in closeout. | 20832
37 | Operating | 20833 | 8215 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 04/24/2024 Project is in closeout | 20833
38 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Voided | Finalized | Sean Rewers | 5000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/27/2023 This project is on hold until October. We are awaiting approval from the CBO for initial funding which will be repaid by the FRP. | #N/A
39 | Capital | 20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Active | Construction | Ben Bedock | 499184 | 499184 | 472444.67 | 475944.67 | 243906.27 |  | 0 | 499184 | 0 | 0 | 0 | 0 | 01/22/2025 Fire system to be completed the week of 01/20. Inspection shifted to Jan 30. Cab interiors to follow the next week after inspection. Working with jack company to schedule jack installation per our discussion. | 20857
40 | Capital | 20884 |  | CP_400251 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Exterior Window Painting | Active | Financial Closeout | Ben Bedock | 675650 | 675650 | 480318 | 480318 | 480318 | 124367 | 0 | 675650 | 0 | 0 | 0 | 0 | 08/23/2024 VUMO is managing this project. CPC is helping with the PO/financial process. | 20884
41 | Operating | 20885 | 8676 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Construction | Sean Rewers | 99000 | 143053.4 | 121224.26 | 121224.26 | 97943.4 |  | 0 | 113053.4 | 30000 | 0 | 30000 | 0 | 01/31/2025 Alas has been making repairs to fans and down compressors during the month of January. Controls need to be updated once all repairs are made. | 20885
42 | Operating | 20911 | 8819 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | Ben Bedock | 61045 | 61045 | 54613 | 54613 | 54613 | 6432 | 0 | 61045 | 0 | 0 | 0 | 0 | 01/22/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20911
43 | Operating | 20912 | 8822 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | Ben Bedock | 59798 | 59798 | 53366 | 53366 | 27741.06 |  | 0 | 59798 | 0 | 0 | 0 | 0 | 01/22/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20912
44 | Operating | 20913 | 8818 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | Ben Bedock | 96612 | 96612 | 86900 | 86900 | 45263.09 |  | 0 | 96612 | 0 | 0 | 0 | 0 | 01/22/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20913
45 | Capital | 20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Exterior Improvements | Active | Warranty or Construction Closeout | Jay Surprenant | 170000 | 197150 | 170000 | 170000 | 170000 | 27150 | 0 | 197150 | 0 | 0 | 0 | 0 | 01/29/2025 Moved to library closeout. waiting on closeout documents from contractor. No change from last month. | 20922
46 | Operating | 20924 |  |  | 19000 - Nursing: Office of the Dean | Nursing | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Active | Financial Closeout | Ben Bedock | 30570 | 30570 | 24500 | 24500 | 24500 | 6070 | 0 | 30570 | 0 | 0 | 0 | 0 | 11/26/2024 Construction is complete. Waiting on the final invoice to begin the closeout process. | 20924
47 | Capital | 20925 | 8260 |  | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Active | Design | Hans Mooy | 2750000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2750000 | 01/22/2025 Kickoff meeting to occur in February | 20925
48 | TBD | 20934 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | NEELY AUDITORIUM | Neely Auditorium - MEP Feasibility Study | Voided | Not Started | Sean Rewers |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | TBD | TBD | 0 | Project was cancelled per Aaron Covey and Chris Preston. Email in documents folder. | #N/A
49 | Operating | 20936 | 8814 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Active | Warranty or Construction Closeout | Jay Surprenant | 405000 | 404655.91 | 357255.91 | 357255.91 | 357255.91 | 47400 | 0 | 404655.91 | 0 | 0 | 0 | 0 | 01/29/2025 Project completed. Moving to Library Closeout. No change from last month. | 20936
50 | Capital | 20940 |  | CP_400291 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Active | Construction | Sean Rewers | 310000 | 309548.64 | 271388.49 | 296749.81 | 22423.67 |  | 0 | 0 | 309548.64 | 0 | 309548.64 | 0 | 01/28/2025 Cameras have been installed and last of the hardware should be received end of January. All wiring has been pulled, remaining work all to be completed at once. | 20940
51 | Operating | 20945 |  |  | 10000 - Chancellor | Other | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Active | Financial Closeout | Sean Rewers | 99000 | 99000 | 82897 | 82897 | 0 | 16103 | 0 | 99000 | 0 | 0 | 0 | 0 | 11/25/2024 We are awaiting TAB and other reports from Nashville Machine, then we will put into FX. | 20945
52 | Capital | 20957 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - Roof Replacement | Voided | Finalized | Hans Mooy | 500000 | 0 | 0 | 0 | 0 | [7 empty] | 05/21/2024 04/23/2024 BAC to be submitted for funding x-fer. 05/21 project on hold | #N/A
53 | Capital | 20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction | Ben Bedock | 290000 | 261629 | 235633 | 239133 | 77312.4 |  | 0 | 18175 | 243454 | 0 | 243454 | 0 | 01/22/2025 PO has been issued to the contractor. Engineering drawings, review and production has started. Construction to start on 05/13/2025. | 20958
54 | Capital | 20962 | 8754 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Roof Replacement | Active | Award | Ben Bedock | 1750000 | 1800 | 1800 | 1800 | 0 |  | 0 | 0 | 1800 | 2000000 | 2001800 | 0 | 01/22/2025 Project is currently out to bid. Bids are due 01/31 | 20962
55 | Capital | 20979 | 9 |  | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Active | Programming or Planning | Ben Bedock | 270000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 01/22/2025 Working with the appropriate parties to determine the scope of work and the time frame of the work. | 20979
56 | Capital | 20982 |  | CP_400270 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction | Ben Bedock | 272000 | 272000 | 246321 | 249821 | 11175 |  | 0 | 18175 | 253825 | 0 | 253825 | 0 | 01/22/2025 PO has been issued to the contractor. Engineering drawings, review and production has started. Construction to start on 05/13/2025. | 20982
57 | Operating | 20984 | 8712 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Active | Warranty or Construction Closeout | Hans Mooy | 167000 | 167000 | 143484.6 | 143484.6 | 122986 |  | 0 | 0 | 167000 | 0 | 167000 | 0 | 01/22/2025 Project complete | 20984
58 | Capital | 21004 | 1010 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Active | Programming or Planning | Jay Surprenant | 0 | 54000 | 44000 | 44000 | 17600 |  | 0 | 0 | 54000 | 0 | 54000 | 0 | 01/28/2025 Project bid walk scheduled for 1/31, bids due 1/14. | 21004
59 | Capital | 21005 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 09/24/2024 This is FY 26 project. No updates to provide yet. Project not started. | 21005
60 | Capital | 21006 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 09/24/2024 Project not started. this is an FY28 project. | 21006
61 | Capital | 21007 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 09/24/2024 Project not started. This is an FY29 project. | 21007
62 | TBD | 21010 |  |  | 15000 - Engineering: Office of the Dean | Engineering | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Programming or Planning | Sean Rewers | 30000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 01/28/2025 We have received a cost estimate for replacing the existing heat exchanger. We have decided to ask for a hot water tank replacement as HX is not needed. Awaiting pricing on hot water tank. | 21010
63 | TBD | 21051 |  |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 01/28/2025 Project put out to bid, bids due 2/14. | 21051
64 | TBD | 21066 |  |  | 12100 - Arts and Science: Business Affairs | Arts & Science | SC MOLEC BIOLOGY | SC2 - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21066
65 | Capital | 21067 |  |  | 19000 - Nursing: Office of the Dean | Nursing | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades | Active | Design | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 01/28/2025 Awaiting proposal for design from SSR and John Teselle. Will get design started and finalize design for rooftop covering with building occupants. | 21067
66 | TBD | 21068 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Insulate First Floor Slab | Active | Bidding | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 01/28/2025 seeking bids for insulation work. Targeting 2/21 for budget numbers. | 21068
67 | TBD | 21070 |  |  | 15000 - Engineering: Office of the Dean | Engineering | OLIN HALL | Olin Hall - Exterior Facade Cleaning | Active | Programming or Planning | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 01/22/2025 Met with the customer to determine the needs for the scope of work. Will include 4 prices for cleaning and sealing ESB and Olin. | 21070
68 | TBD | 21071 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC MATH | SC1 - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21071
69 | TBD | 21072 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | CALHOUN HALL | Calhoun Hall - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21072
70 | TBD | 21073 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21073
71 | TBD | 21074 |  |  | 17000 - Law: Office of the Dean | Law | LAW SCHOOL | Law School - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21074
72 | TBD | 21076 |  |  | 30400 - Greek Life | #N/A | 2500 KENSINGTON PL | 2500 Kensington Place - Sewer Line Replacement | Active | Not Started | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21076
73 | TBD | 21094 |  |  | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - Replace Fire Pump | Active | Programming or Planning | Sean Rewers | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21094
74 | TBD | 21107 |  |  | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Locker Replacement | Active | Not Started | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21107
75 | Operating | 21108 |  |  | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Electrical and HVAC Study | Active | Design | Sean Rewers | 5000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21108
76 | TBD | 21113 |  |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - Lecture Hall V1220 Lighting Upgrade | Active | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21113
77 | TBD | 21114 |  |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - Chemical Discharge Tank Replacement | Active | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | New project | 21114
[12 empty] | 41255601.76 | 31009281.98 | 27188380.64 | 28236275.16 | 22992364.91 | 782167.26 | 8797286.26 | 11427472.94 | 6620521.78 | 2561500 | 9182021.78 | 8430000
[18 empty] | TRUE | TRUE
[18 empty] | TRUE | TRUE | TRUE |  | TRUE
Projects to be discussed
Law School - replace front stairs ($200k - $400k)
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes roof repairs in scope.
Note on M10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on X11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project will be joint funded, FPR / Divinity + Dean of Students.
Note on X19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase 2 estimate. May be a separate project ID.
Note on M28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10085 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | 9364499 | 17500 |  | 17500
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Finalized |  | 1216485.5 |  | 1216485.5
| 3 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Financial Closeout |  | 4900 |  | 4900
| 4 | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Finalized |  | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Finalized |  | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Warranty or Construction Closeout |  | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Warranty or Construction Closeout |  | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Design | Design |  | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Finalized |  | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Finalized |  | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Finalized |  | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Finalized |  | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Finalized |  | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Finalized |  | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Design | Construction |  | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Finalized |  | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Finalized |  | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Award |  | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Design |  | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Financial Closeout |  | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Finalized |  | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Construction |  | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Finalized |  | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Finalized |  | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Award |  | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Design | Warranty or Construction Closeout |  | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Finalized |  | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Finalized |  | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Finalized |  | 483440 |  | 483440
[8 empty] | 8797286.26 | 0 | 8797286.26 | 567212.74
TRUE
FY 2024 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Active | Financial Closeout | 11029283.29 | 255957 |  | 255957 |  | phase 1
| 2 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Active | Warranty or Construction Closeout |  | 3660360 |  | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Active | Warranty or Construction Closeout |  | 1028900 |  | 1028900
| 4 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design |  | 24933 |  | 24933
| 5 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Active | Financial Closeout |  | 649263 |  | 649263
| 6 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized |  | 5954 |  | 5954
| 7 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Active | Warranty or Construction Closeout |  | 1964100 |  | 1964100
| 8 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Active | Warranty or Construction Closeout |  | 148299 |  | 148299
| 9 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction |  | 1600000 |  | 1600000
| 10 | 20811 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Active | Warranty or Construction Closeout |  | 285233.27 |  | 285233.27
| 11 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized |  | 24000 |  | 24000
| 12 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Complete | Finalized |  | 24000 |  | 24000
| 13 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Complete | Finalized |  | 24000 |  | 24000
| 14 | 20857 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Active | Construction |  | 499184 |  | 499184
| 15 | 20884 | LAW SCHOOL | Law School - Exterior Window Painting | Active | Financial Closeout |  | 675650 |  | 675650
| 16 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Construction |  | 113053.4 |  | 113053.4
| 17 | 20911 | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Active | Warranty or Construction Closeout |  | 61045 |  | 61045
| 18 | 20912 | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout |  | 59798 |  | 59798
| 19 | 20913 | WILSON HALL | Wilson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout |  | 96612 |  | 96612
| 20 | 20922 | VAUGHN HOME | Vaughn Home - Exterior Improvements | Active | Warranty or Construction Closeout |  | 197150 |  | 197150
| 21 | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Active | Financial Closeout |  | 30570 |  | 30570
| 22 | 20936 | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Active | Warranty or Construction Closeout |  | 404655.91 |  | 404655.91
| 23 | 20945 | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Active | Financial Closeout |  | 99000 |  | 99000
| 24 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction |  | 18175 |  | 18175
| 25 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction |  | 18175 |  | 18175
|  | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized |  | -4400.96 |  | -4400.96
|  | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Complete | Finalized |  | -47290 |  | -47290
|  | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Complete | Finalized |  | -44850 |  | -44850
|  | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Complete | Finalized |  | -36379 |  | -36379
|  | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Complete | Finalized |  | -43231.36 |  | -43231.36
|  | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized |  | -59283.32 |  | -59283.32
|  | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Complete | Finalized |  | -119221 |  | -119221
|  | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Complete | Finalized |  | -22537 |  | -22537
|  | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Complete | Finalized |  | -58765 |  | -58765
|  | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Complete | Finalized |  | -11525 |  | -11525 | prior year
|  | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Complete | Finalized |  | -29922 |  | -29922 | carryforward
|  | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized |  | -7025 |  | -7025
|  | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized |  | -32665 |  | -32665 | 567212.74
|  | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Complete | Finalized |  | -23500 |  | -23500
[8 empty] | 11427472.94 | 0 | 11427472.94 | 169023.09
FY 2025 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining | Estimated
| 1 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Active | Construction | 12857284.4623 | 1077000 | 0 | 1077000 |  | Hans Mooy
| 2 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Active | Award |  | 1398860 | 0 | 1398860 |  | Sean Rewers
| 3 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Active | Award |  | 1539500 | 0 | 1539500 |  | Jay Surprenant
| 4 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction |  | 1600000 | 0 | 1600000 |  | Ben Bedock
| 5 | 20812 | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Active | Design |  | 38500 | 561500 | 600000 |  | Sean Rewers
| 6 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Construction |  | 30000 | 0 | 30000
| 7 | 20940 | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Active | Construction |  | 309548.64 | 0 | 309548.64 |  | Sean Rewers
| 8 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction |  | 243454 | 0 | 243454 |  | Ben Bedock
| 9 | 20962 | VAUGHN HOME | Vaughn Home - Roof Replacement | Active | Award |  | 1800 | 2000000 | 2001800 |  | Ben Bedock
| 10 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction |  | 253825 | 0 | 253825 |  | Ben Bedock
| 11 | 20984 | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Active | Warranty or Construction Closeout |  | 167000 | 0 | 167000 |  | Hans Mooy
| 12 | 21004 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Active | Programming or Planning |  | 54000 | 0 | 54000 |  | Jay Surprenant
| 13 | 21010 | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Programming or Planning |  | 0 | 0 | 0 |  | Sean Rewers
| 14 | 21051 | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning |  | 0 | 0 | 0
| 15 | 21066 | SC MOLEC BIOLOGY | SC2 - MEP Feasibility Study | Active | Programming or Planning |  | 0 | 0 | 0
| 16 | 21067 | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades | Active | Design |  | 0 | 0 | 0
| 17 | 21068 | BUTTRICK HALL | Buttrick Hall - Insulate First Floor Slab | Active | Bidding |  | 0 | 0 | 0
| 18 | 21070 | OLIN HALL | Olin Hall - Exterior Facade Cleaning | Active | Programming or Planning |  | 0 | 0 | 0
| 19 | 21071 | SC MATH | SC1 - MEP Feasibility Study | Active | Programming or Planning |  | 0 | 0 | 0
| 20 | 21072 | CALHOUN HALL | Calhoun Hall - MEP Feasibility Study | Active | Programming or Planning |  | 0 | 0 | 0
| 21 | 21073 | FURMAN HALL | Furman Hall - MEP Feasibility Study | Active | Programming or Planning |  | 0 | 0 | 0
| 22 | 21074 | LAW SCHOOL | Law School - MEP Feasibility Study | Active | Programming or Planning |  | 0 | 0 | 0
| 23 | 21076 | 2500 KENSINGTON PL | 2500 Kensington Place - Sewer Line Replacement | Active | Not Started |  | 0 | 0 | 0
| 24 | 21094 | GODCHAUX HALL | Godchaux Hall - Replace Fire Pump | Active | Programming or Planning |  | 0 | 0 | 0
| 25 | 21107 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Locker Replacement | Active | Not Started |  | 0 | 0 | 0
| 26 | 21108 | 1025 16TH AVE S | 1025 16th Avenue - Electrical and HVAC Study | Active | Design |  | 0 | 0 | 0
| 27 | 21113 | MRB III BIO/SCI | MRBIII - Lecture Hall V1220 Lighting Upgrade | Active | Programming or Planning |  | 0 | 0 | 0
| 28 | 21114 | MRB III BIO/SCI | MRBIII - Chemical Discharge Tank Replacement | Active | Programming or Planning |  | 0 | 0 | 0
prior year
carryforward
|  | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Complete | Finalized |  | -92965.86 | 0 | -92965.86 | 169023.09
[8 empty] | 6620521.78 | 2561500 | 9182021.78 | 3844285.7723 | 0
TRUE
FY 2026 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Active | Design | 13263819.6534 |  | 0 | 0
| 2 | 20925 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Active | Design |  |  | 0 | 0
| 3 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design |  |  | 0 | 0
| 4 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Deferred / On Hold | Not Started |  |  | 0 | 0
| 5 | 20979 | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Active | Programming or Planning |  |  | 0 | 0
| 6 | 21005 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Deferred / On Hold | Programming or Planning |  |  | 0 | 0
| 7 | 21006 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Deferred / On Hold | Programming or Planning |  |  | 0 | 0
| 8 | 21007 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Deferred / On Hold | Programming or Planning |  |  | 0 | 0
| 9 | 21010 | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Programming or Planning |  |  | 0 | 0
| 10 | 21051 | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning |  |  | 0 | 0
[8 empty] | 0 | 0 | 0 | 13263819.6534
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Preliminary cost estimates presented in three options. $4M - $5M range.

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | 17500 | 22000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 4500

## 10098 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized | 1216485.5 | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | crowhus_01302024_FRP | FX2-1 |  | -4400.96
|  |  |  | Total transfers from FRP cash |  |  | 1212084.54
|  |  |  | Balance |  |  | 4400.96

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Active | Financial Closeout | 318000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | crowhus_01302024_FRP | BAC-5 |  | 244457
|  |  |  | FY24 subtotal |  |  | 255957
|  |  |  | Balance |  |  | -57

## 20179 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Complete | Finalized | 1445389 | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
|  |  |  | crowhus_08312024_FRP |  |  | -92965.86
1352423.14
|  |  |  | Total transfers from FRP cash |  |  | 629728.64
|  |  |  | Balance |  |  | 92965.86

## 20336 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Complete | Finalized | 327890 | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -47290
|  |  |  | Total transfers from FRP cash |  |  | 280600
|  |  |  | Balance |  |  | 47290

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Active | Warranty or Construction Closeout | 3800000
[8 empty] | 75% | 25%
[8 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360
All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
3800000
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Active | Warranty or Construction Closeout | 2790000 | 2790000
[9 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 |  | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 |  | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 |  | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
[7 empty] | 2790000 |  | 1110000 | 1680000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Active | Design | 4750000
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 4723500

## 20497 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Complete | Finalized | 456850 | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -44850
|  |  |  | Total transfers from FRP cash |  |  | 412000
|  |  |  | Balance |  |  | 44850

## 20506 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Complete | Finalized | 344155.26 | 344155.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -36379
|  |  |  | Total transfers from FRP cash |  |  | 307776.26
|  |  |  | Balance |  |  | 36379

## 20562 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Complete | Finalized | 400000 | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -43231.36
|  |  |  | Total transfers from FRP cash |  |  | 362559.64
|  |  |  | Balance |  |  | 43231.36

## 20566 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized | 781870 | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | crowhus_02292024_FRP | FX |  | -59283.32
|  |  |  | Total transfers from FRP cash |  |  | 722586.68
|  |  |  | Balance |  |  | 59283.32

## 20573 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Complete | Finalized | 1232681 | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -119221
|  |  |  | Total transfers from FRP cash |  |  | 1113460
|  |  |  | Balance |  |  | 119221

## 20574 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Complete | Finalized | 218202 | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -22537
|  |  |  | Total transfers from FRP cash |  |  | 195665
|  |  |  | Balance |  |  | 22537

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Active | Construction | 1300000
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | crowhus_10312024_FRP | BAC-4 |  | 1077000
|  |  |  | Total transfers from FRP cash |  |  | 1300000
|  |  |  | Balance |  |  | 0

## 20644 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Complete | Finalized | 630554 | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -58765
|  |  |  | Total transfers from FRP cash |  |  | 571789
|  |  |  | Balance |  |  | 58765

## 20645 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Complete | Finalized | 125875 | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | crowhus_04302024_FRP | FX2-1 |  | -11525
|  |  |  | Total transfers from FRP cash |  |  | 114350
|  |  |  | Balance |  |  | 11525

## 20667
Project Status'!A1
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Active | Award | 1550000
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_12312024_FRP | BAC-4 |  | 1398860
|  |  |  | Total transfers from FRP cash |  |  | 1545360
|  |  |  | Balance |  |  | 4640

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Active | Design | 0
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_10312023_FRP | BAC-4 |  | 24933
|  |  |  | Total transfers from FRP cash |  |  | 231433
|  |  |  | Balance |  |  | -231433

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Active | Financial Closeout | 680000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | crowhus_01302024_FRP | BAC-4 | ` | 649263
|  |  |  | Total transfers from FRP cash |  |  | 678513
|  |  |  | Balance |  |  | 1487

## 20700 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized | 80000 | 85577
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | -5577

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Active | Construction | 500000
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 907

## 20702 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Complete | Finalized | 225791 | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | crowhus_02292024_FRP | FX |  | -29922
|  |  |  | Total transfers from FRP cash |  |  | 209419
|  |  |  | Balance |  |  | 29922

## 20718 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Complete | Finalized | 715000 | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Active | Award | 1610000
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | crowhus_10312024_FRP |  |  | 1539500
|  |  |  | Total transfers from FRP cash |  |  | 1700000
|  |  |  | Balance |  |  | -90000

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line - FY 23 | Active | Warranty or Construction Closeout | 1987500
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | crowhus_12192023_FRP | BAC-2 |  | 1964100
|  |  |  | Total transfers from FRP cash |  |  | 1987500
|  |  |  | Balance |  |  | 0

## 20735 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Complete | Finalized | 300000 | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | crowhus_06302024_FRP | FX2-1 |  | -23500
|  |  |  | Total transfers from FRP cash |  |  | 276500
|  |  |  | Balance |  |  | 23500

## 20767
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Six Magnolia Circle - Foundation Repairs | Active | Warranty or Construction Closeout | 149000 | 148299
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 148299
|  |  |  | Total transfers from FRP cash |  |  | 148299
|  |  |  | Balance |  |  | 701

## 20771 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized | 25000 | 24997
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -7025
|  |  |  | Total transfers from FRP cash |  |  | 17972
|  |  |  | Balance |  |  | 7025

## 20792 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized | 400000 | 483440
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | crowhus_02292024_FRP | FX |  | -32665
|  |  |  | Total transfers from FRP cash |  |  | 450775
|  |  |  | Balance |  |  | 32665

## 20831 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20831 | 8230 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20832 | 8220 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20833 | 8215 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement (Design Services) | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20772
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction | 3200000
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 1600000
|  |  |  | crowhus_07312024_FRP | BAC-1 |  | 1600000
|  |  |  | Total transfers from FRP cash |  |  | 3200000
|  |  |  | Balance |  |  | 0

## 20811
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20811 | 0 | CP_400224 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Retaining Wall Repair | Active | Warranty or Construction Closeout | 75000
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 285233.27
|  |  |  | Total transfers from FRP cash |  |  | 285233.27
|  |  |  | Balance |  |  | -210233.27
Original budget (BAC-1) for $2,640 set up as a Facilities capital project, owning org 37000. It has been determined this is an FRP project and will be assigned to Peabody. Owning org has been updated in Oracle.

## 20812
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Patio Repairs | Active | Design | 600000
Funding transfers
|  |  |  | crowhus_08312024_FRP | BAC-1 |  | 4500
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 34000
|  |  |  | Total transfers from FRP cash |  |  | 38500
|  |  |  | Balance |  |  | 561500

## 20857
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Elevator Modernization | Active | Construction | 499184
Funding transfers
|  |  |  | crowhus_10312023_FRP | BAC-1 |  | 17600
|  |  |  | crowhus_01302024_FRP | BAC-2 |  | 4000
|  |  |  | crowhus_03312024_FRP | BAC-3 |  | 477584
|  |  |  | Total transfers from FRP cash |  |  | 499184
|  |  |  | Balance |  |  | 0

## 20884
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20884 | 0 | CP_400251 | 17100 - Law: Business Affairs | Law School - Exterior Window Painting | Active | Financial Closeout | 675650
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-3 |  | 675650
|  |  |  | Total transfers from FRP cash |  |  | 675650
|  |  |  | Balance |  |  | 0

## 20885
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20885 | 8676 | 0 | 12000 - Arts and Science: Office of the Dean | NMR - Replace Air Compressors | Active | Construction | 99000
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-2 |  | 98341
|  |  |  | crowhus_05312024_FRP | BAC-3 |  | 14712.4
|  |  |  | crowhus_09302024_FRP | BAC-4 |  | 30000
|  |  |  | Total transfers from FRP cash |  |  | 143053.4
|  |  |  | Balance |  |  | -44053.4

## 20911
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20911 | 8819 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | 61045
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 56945
|  |  |  | Total transfers from FRP cash |  |  | 61045
|  |  |  | Balance |  |  | 0

## 20912
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20912 | 8822 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | 59798
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 55698
|  |  |  | Total transfers from FRP cash |  |  | 59798
|  |  |  | Balance |  |  | 0

## 20913
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20913 | 8818 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | 96612
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 92512
|  |  |  | Total transfers from FRP cash |  |  | 96612
|  |  |  | Balance |  |  | 0

## 20922
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Vaughn Home - Exterior Improvements | Active | Warranty or Construction Closeout | 170000
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 197150
|  |  |  | Total transfers from FRP cash |  |  | 197150
|  |  |  | Balance |  |  | -27150

## 20924
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20924 | 0 | 0 | 19000 - Nursing: Office of the Dean | Frist Hall - Stairwell Roof Replacement | Active | Financial Closeout | 30570
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 30570
|  |  |  | Total transfers from FRP cash |  |  | 30570
|  |  |  | Balance |  |  | 0

## 20936
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20936 | 8814 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Lighting Retrofit for 103 and 126 | Active | Warranty or Construction Closeout | 405000
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 404655.91
|  |  |  | Total transfers from FRP cash |  |  | 404655.91
|  |  |  | Balance |  |  | 344.09

## 20940
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20940 | 0 | CP_400291 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Security System Replacement | Bidding | Rewers, Sean | 0
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 294789
|  |  |  | crowhus_01312025_FRP | BAC-3 |  | 14759.64
|  |  |  | Total transfers from FRP cash |  |  | 309548.64
|  |  |  | Balance |  |  | -309548.64

## 20945
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20945 | 0 | 0 | 10000 - Chancellor | Seigenthaler Building - HVAC Improvements | Active | Financial Closeout | 99000
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 99000
|  |  |  | Total transfers from FRP cash |  |  | 99000
|  |  |  | Balance |  |  | 0

## 20958
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Furman Hall - Elevator Modernization | Active | Construction | 290000
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 243454
|  |  |  | Total transfers from FRP cash |  |  | 261629
|  |  |  | Balance |  |  | 28371

## 20962
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20962 | 8754 | 0 | 12100 - Arts and Science: Business Affairs | Vaughn Home - Roof Replacement | Programming or Planning | Ben Bedock | 0
Funding transfers
|  |  |  | crowhus_01312025_FRP | BAC-1 |  | 1800
|  |  |  | Total transfers from FRP cash |  |  | 1800
|  |  |  | Balance |  |  | -1800

## 20982
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20982 | 0 | CP_400270 | 17100 - Law: Business Affairs | Law School - Elevator 1 Modernization | Active | Construction | 272000
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_10312024_FRP | BAC-2 |  | 253825
|  |  |  | Total transfers from FRP cash |  |  | 272000
|  |  |  | Balance |  |  | 0

## 20984
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
20984 | 8712 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - 1st Floor Urinal Replacement | Active | Warranty or Construction Closeout | 167000
Funding transfers
|  |  |  | crowhus_09302024_FRP | BAC-1 |  | 167000
|  |  |  | Total transfers from FRP cash |  |  | 167000
|  |  |  | Balance |  |  | 0

## 21004
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget
21004 | 1010 | 0 | 12100 - Arts and Science: Business Affairs | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Programming or Planning | Jay Surprenant | 0
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 54000
|  |  |  | Total transfers from FRP cash |  |  | 54000
|  |  |  | Balance |  |  | -54000

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
Sources
| crowhus_08072023_FRP | 11029283.29
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| crowhus_10312023_FRP | -45721
| crowhus_12192023_FRP | 1964100
| crowhus_01302024_FRP | 893319.04
| crowhus_02292024_FRP | -11229.32
| crowhus_03312024_FRP | 638993.64
| crowhus_04302024_FRP | 1384584.18
| crowhus_05312024_FRP | 230037.4
| crowhus_06302024_FRP | 1594675
| Total Uses | 11427472.94
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 169023.09 | DB: | CR:
|  |  | 7025 | 24933
|  |  | 36379 | 17600
44850
|  |  | 88254 | 42533 | 130787
-45721
|  |  | DB: | CR:
|  |  | 1964100 | 1964100
|  |  | 1964100 | 1964100
|  |  | 3928200 | 3928200
0
|  |  | DB: | CR:
649263
244457
4000
4400.96
|  |  | 4400.96 | 897720 | 902120.96
893319.04
|  |  | DB: | CR:
12300
98341
59283.32
29922
32665
|  |  | 121870.32 | 110641 | 232511.32
-11229.32
|  |  | DB: | CR:
148299
|  |  | 47290 | 477584
|  |  | 43231.36 | 56945
|  |  | 119221 | 55698
|  |  | 22537 | 92512
|  |  | 58765 | 99000
|  |  | 291044.36 | 930038 | 1221082.36
638993.64
|  |  | DB: | CR:
285233.27
675650
30570
404655.91
11525
|  |  | 11525 | 1396109.18 | 1407634.18
1384584.18
|  |  | 460074.8 | 230037.4
|  |  | DB: | CR:
18175
1600000
23500
|  |  | 23500 | 1618175 | 1641675
1594675

## JE LOG_FY25
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 12857284.4623 | tbd | 0
| Total sources | 12857284.4623
Uses
| crowhus_07312024_FRP | 1600000
| crowhus_08312024_FRP | 188988.14
| crowhus_09302024_FRP | 197000
| crowhus_10312024_FRP | 3219114
| crowhus_12312024_FRP | 1398860
| crowhus_01312025_FRP | 16559.64
| Total Uses | 6620521.78
| plus carryforward | 169023.09
| (less) TBD | 0 |  |  | DB: | CR:
38500
| Balance | 6405785.7723 |  |  |  | 243454
92965.86
[5 empty] | 92965.86 | 281954 | 374919.86
188988.14
[5 empty] | DB: | CR:
1800
14759.64
33119.28
[5 empty] | 33119.28 | 16559.64 | 49678.92
-16559.64

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
12100 - Arts and Science: Business Affairs | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17000 - Law: Office of the Dean | Law
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19000 - Nursing: Office of the Dean | Nursing
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.