## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.
Notes about upcoming planning

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2025-03-05
School | GSF | FY23 - FY25 Cumulative Contribution | FY23 Funded Projects | FY24 Funded Projects | FY25 Estimated Projects | Contribution vs. Funded
Arts & Science | 1075461.7321 | 12747868.731 | 2276289.625 | 2619344.704 | 3118516.4 | 4733718.002
Blair | 121421.4269 | 1496829.2818 | 574290 | 1916810 | 1077000 | -2071270.7182
Divinity | 57814.7309 | 692779.0038 | 96362.5 | 3660360 | 0 | -3063943.4962
Engineering | 537962.3327 | 6515613.1943 | 353000 | 24933 | 2439432.64 | 3698247.5543
Law | 120155.4846 | 1427819.0631 | 1206134.5 | 661160 | 160859.14 | -600334.5769
SOM Basic Sciences | 280022.3999 | 3441675.5551 | 1036871.875 | -17509.674 | 1000675 | 1421638.3541
Nursing | 106166.7 | 1261583.3214 | 4900 | 286527 | 134100 | 836056.3214
Owen | 59008.3617 | 1046789.5035 | 300000 | 1576500 | 1600000 | -2429710.4965
Peabody | 390796.8848 | 4620109.0983 | 2949437.76 | 600347.91 | 0 | 1070323.4283
| 2748810.0535 | 33251066.7523 | 8797286.26 | 11328472.94 | 9530583.18 | 3594724.3723
Estimated funded projects is anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2025-03-05
| Projects |  |  |  | (1) | (2) | (2) | (2)
| Project Phase | eBuilder Project No | School | Project Description | Estimated Total Budget | FY23 FRP Funding | FY24 FRP Funding | FY25 FRP Funding
1 | Complete | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0 | 0
2 | Complete | 10098 | SOM Basic Sciences | MRB III - 4th Floor - Replace Controls (Phase 2) | 1216485.5 | 1216485.5 | -4400.96 | 0
3 | Active | 10146 | Nursing | Godchaux Hall - HVAC Upgrade | 318000 | 4900 | 255957 | 0
4 | Complete | 20179 | Law | Law School - Fire Alarm System Replacement | 1445389 | 722694.5 | 0 | -92965.86
5 | Complete | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 327890 | 327890 | -47290 | 0
6 | Active | 20431 | Divinity | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 69862.5 | 3660360 | 0
7 | Active | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2790000 | 81100 | 1028900 | 0
8 | Active | 20489 | Divinity | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | 5150000 | 26500 | 0 | 0
9 | Complete | 20497 | Peabody | Jesup - Roof Replacement | 456850 | 79415.5 | -44850 | 0
10 | Complete | 20506 | Peabody | Wyatt Center - Window Replacement | 344155.26 | 344155.26 | -36379 | 0
11 | Complete | 20562 | Peabody | Wyatt Center - VAV Replacement | 400000 | 405791 | -43231.36 | 0
12 | Deferred / On Hold | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0 | 0
13 | Complete | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 781870 | 781870 | -59283.32 | 0
14 | Complete | 20573 | Peabody | Wyatt Center - Roof Replacement | 1232681 | 1232681 | -119221 | 0
15 | Complete | 20574 | SOM Basic Sciences | MRB III - Steam Coil Replacement | 218202 | 218202 | -22537 | 0
16 | Active | 20577 | Blair | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | 1300000 | 223000 | 0 | 1077000
17 | Complete | 20644 | Peabody | Peabody Administration - Envelope Repairs | 630554 | 630554 | -58765 | 0
18 | Complete | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 125875 | 125875 | -11525 | 0
19 | Active | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 1550000 | 146500 | 0 | 1398860
20 | Active | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 0 | 206500 | 24933 | 0
21 | Active | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 680000 | 29250 | 649263 | 0
22 | Complete | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 80000 | 79623 | 5954 | 0
23 | Active | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 500000 | 499093 | 0 | 0
24 | Complete | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 225791 | 239341 | -29922 | 0
25 | Complete | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 715000 | 96166 | 0 | 0
26 | Active | 20723 | SOM Basic Sciences | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500 | 0 | 1539500
27 | Active | 20724 | Blair | Blair School of Music - Steam Line - FY 23 | 1987500 | 23400 | 1964100 | 0
28 | Complete | 20735 | Owen | Owen - Roof Replacement (Third Level) | 300000 | 300000 | -23500 | 0
29 | Active | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 149000 | 0 | 148299 | 0
30 | Complete | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 25000 | 24997 | -7025 | 0
31 | Active | 20772 | Owen | OGSM Old Mechanical- Slate Roof & Window Replacement | 3200000 | 0 | 1600000 | 1600000
32 | Complete | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 400000 | 483440 | -32665 | 0
33 | Active | 20811 | Peabody | One Magnolia Circle - Retaining Wall Repair | 75000 | 0 | 285233.27 | 0
34 | Active | 20812 | Engineering | 1025 16th Avenue - Patio Repairs | 600000 | 0 | 0 | 600000
35 | Complete | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 24000 | 0
36 | Complete | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 24000 | 0 | 24000 | 0
37 | Complete | 20833 | Arts & Science | SC5 - HVAC Replacement (Design Services) | 24000 | 0 | 24000 | 0
38 | Voided | 20834 | Peabody | Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0 | 0 | 0
39 | Active | 20857 | Peabody | One Magnolia Circle - Elevator Modernization | 499184 | 0 | 499184 | 0
40 | Active | 20884 | Law | Law School - Exterior Window Painting | 675650 | 0 | 675650 | 0
41 | Active | 20885 | Arts & Science | NMR - Replace Air Compressors | 99000 | 0 | 113053.4 | 30000
42 | Active | 20911 | Arts & Science | Buttrick Hall - Elevator Upgrades | 61045 | 0 | 61045 | 0
43 | Active | 20912 | Arts & Science | Benson Hall - Elevator Upgrades | 59798 | 0 | 59798 | 0
44 | Active | 20913 | Arts & Science | Wilson Hall - Elevator Upgrades | 96612 | 0 | 96612 | 0
45 | Active | 20922 | Arts & Science | Vaughn Home - Exterior Improvements | 170000 | 0 | 197150 | 0
46 | Active | 20924 | Nursing | Frist Hall - Stairwell Roof Replacement | 30570 | 0 | 30570 | 0
47 | Active | 20925 | Blair | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | 2850000 | 0 | 0 | 0
48 | Active | 20936 | Arts & Science | Wilson Hall - Lighting Retrofit for 103 and 126 | 405000 | 0 | 404655.91 | 0
49 | Active | 20940 | Engineering | 1025 16th Avenue - Security System Replacement | 310000 | 0 | 0 | 309548.64
50 | Active | 20945 | Other | Seigenthaler Building - HVAC Improvements | 99000 | 0 | 99000 | 0
51 | Active | 20958 | Arts & Science | Furman Hall - Elevator Modernization | 290000 | 0 | 18175 | 243454
52 | Active | 20962 | Arts & Science | Vaughn Home - Roof Replacement | 1750000 | 0 | 0 | 2001800
53 | Active | 20979 | Engineering | 1025 16th Avenue - Roof Replacement | 270000 | 0 | 0 | 0
54 | Active | 20982 | Law | Law School - Elevator 1 Modernization | 272000 | 0 | 18175 | 253825
55 | Active | 20984 | Arts & Science | Wilson Hall - 1st Floor Urinal Replacement | 167000 | 0 | 0 | 167000
56 | Active | 21004 | Arts & Science | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | 0 | 0 | 0 | 54000
57 | Deferred / On Hold | 21005 | Arts & Science | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | 0 | 0 | 0 | 0
58 | Deferred / On Hold | 21006 | Engineering | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | 0 | 0 | 0 | 0
59 | Deferred / On Hold | 21007 | Engineering | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | 0 | 0 | 0 | 0
60 | Active | 21010 | Engineering | Featheringill-Jacobs Hall - Hot Water Tank Replacement | 125000 | 0 | 0 | 126024
61 | Active | 21051 | SOM Basic Sciences | MRBIII - 5th Floor Controls | 0 | 0 | 0 | 0
62 | Active | 21066 | Arts & Science | SC2 - MEP Feasibility Study | 0 | 0 | 0 | 29160
63 | Active | 21067 | Nursing | Godchaux Hall - Phase 2 HVAC Upgrades | 0 | 0 | 0 | 46600
64 | Active | 21068 | Arts & Science | Buttrick Hall - Insulate First Floor Slab | 0 | 0 | 0 | 34837.4
65 | Active | 21070 | Engineering | Olin Hall - Exterior Facade Cleaning | 0 | 0 | 0 | 0
66 | Active | 21071 | Arts & Science | SC1 - MEP Feasibility Study | 0 | 0 | 0 | 19440
67 | Active | 21094 | Nursing | Godchaux Hall - Replace Fire Pump | 87500 | 0 | 0 | 87500
68 | Active | 21108 | Engineering | 1025 16th Avenue - Electrical and HVAC Study | 5000 | 0 | 0 | 5000
69 | Active | 21113 | SOM Basic Sciences | MRBIII - Lecture Hall V1220 Lighting Upgrade | 0 | 0 | 0 | 0
70 | Active | 21114 | SOM Basic Sciences | MRBIII - Chemical Discharge Tank Replacement | 0 | 0 | 0 | 0
[5 empty] | 41438101.76 | 8797286.26 | 11427472.94 | 9530583.18
Estimated total budget represents the best rough order of magnitude for total project costs.
FYxx FRP funding indicates anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25 |  |  | Facility Renewal Program: Contributions - FY26
|  | 3.41 |  |  | 3.97 |  |  | 4.54 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141 | Arts & Science | 1168519.772 | 5305079.765
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118 | Blair | 121417.211 | 551234.1379
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938 | College of Connected Computing | 42638.0889 | 193576.9234
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343 | Divinity | 58286.9615 | 264622.8051
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131 | Engineering | 490439.8851 | 2226597.0781
SOM Basic Sciences | 280022.3999 | 953965 | SOM Basic Sciences | 265674 | 1054725.78 | SOM Basic Sciences | 315635.413 | 1432984.7751 | Law | 119265.3553 | 541464.7131
Nursing | 106166.7 | 361683 | Nursing | 105746 | 419811.62 | Nursing | 105746.41 | 480088.7014 | Nursing | 105746.45 | 480088.883
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035 | Owen | 99610.0673 | 452229.7056
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883 | Peabody | 381580.0251 | 1732373.3138
[9 empty] | SOM Basic Sciences | 334042.3631 | 1516552.3283
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623 |  | 2921546.1792 | 13263819.6534
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623 | Contribution |  | 13263819.6534
Anticipated spend |  | 8797286.26 | Anticipated spend |  | 11427472.94 | Anticipated spend |  | 9530583.18 | Anticipated spend |  | 0
Remaining funds |  | 567212.74 | Remaining funds |  | -398189.65 | Remaining funds |  | 3326701.2823 | Remaining funds |  | 13263819.6534
TRUE

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 FRP funding | MRB III Adj | FY24 FRP | Contribution vs. FY24 FRP funding | FY25 Contribution | FY25 estimated FRP funding | MRB III Adj | FY25 FRP | Contribution vs. FY25 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 2.6288 | -0.0094283 | 2.6193 | 1.5855 | 4.8792 | 2.5797 | 0.53882 | 3.1185 | 1.7607
SOM Basic Sciences | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | -0.026938 | 0.0094283 | -0.01751 | 1.0722 | 1.433 | 1.5395 | -0.53882 | 1.0007 | 0.43231
| 2748810.0535 | 4.6178 | 3.3132 |  | 3.3132 | 1.3046 | 5.2595 | 2.6018 |  | 2.6018 | 2.6577 | 6.3122 | 4.1192 |  | 4.1192 | 2.193
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24 |  |  |  |  | FY25
MRB III BIO/SCI |  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1539500
A&S |  |  | 558315.625 |  |  |  |  | -9428.286 |  |  |  |  | 538825
SOM |  |  | 1036871.875 |  |  |  |  | -17509.674 |  |  |  |  | 1000675
|  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1539500

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
21000 - Peabody College: Office of the Dean | 4035715.26 | 4264088.53
Construction | 499184 | 499184
One Magnolia Circle - Elevator Modernization | 499184 | 499184
Finalized | 3312531.26 | 3331372.26
Jesup - Roof Replacement | 456850 | 456850
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000
Peabody Administration - Envelope Repairs | 630554 | 630554
Wyatt Center - Elevator #2 Modernization | 225791 | 239341
Wyatt Center - HVAC Upgrades - Engineering Study | 5000 | 0
Wyatt Center - Roof Replacement | 1232681 | 1232681
Wyatt Center - VAV Replacement | 400000 | 405791
Wyatt Center - Window Replacement | 344155.26 | 344155.26
Warranty or Construction Closeout | 224000 | 433532.27
Six Magnolia Circle - Foundation Repairs | 149000 | 148299
One Magnolia Circle - Retaining Wall Repair | 75000 | 285233.27
Grand Total | 4035715.26 | 4264088.53
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Status
Facility Renewal Program: Projects | [17 empty] | JE LOG_FY23'!A1 | JE LOG_FY24'!A1 |  |  | JE LOG_FY25'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Project Status | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Unallocated Reserve | FY23 FRP Cash Transferred | FY24 FRP Transferred | FY25 FRP Transferred | FY25 FRP Estimated | FY25 FRP Total Contribution | FY26 FRP Estimated | Project status update | Check
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 | 0 | 17500 | 0 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout. | 10085
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized | Hans Mooy | 1216485.5 | 1216485.5 | 1212084.54 | 1212084.54 | 1212084.54 | 0 | 1216485.5 | -4400.96 | 0 | 0 | 0 | 0 | 08/22/2023 project complete | 10098
3 | Capital | 10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Active | Financial Closeout | Sean Rewers | 318000 | 318057 | 253826.81 | 253826.81 | 253826.81 | 64230.19 | 4900 | 255957 | 0 | 0 | 0 | 0 | 09/26/2024 Project is in library closeout. Will complete financial closeout after. | 10146
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Fire Alarm System Replacement | Complete | Finalized | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 |  | 722694.5 | 0 | -92965.86 | 0 | -92965.86 | 0 | 07/29/2024 work is complete | 20179
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Complete | Finalized | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 280600 |  | 327890 | -47290 | 0 | 0 | 0 | 0 | 01/22/2024 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20336
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Active | Warranty or Construction Closeout | Hans Mooy | 3800000 | 3800000 | 3624305.72 | 3624305.72 | 3529404.41 | 191010.33 | 69862.5 | 3660360 | 0 | 0 | 0 | 0 | 02/24/2025 Project Complete | 20431
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Active | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2790000 | 2652824.48 | 2652824.48 | 2652824.48 | 0 | 81100 | 1028900 | 0 | 0 | 0 | 0 | 01/25/2025 Door hardware will be replaced early 2025 then the project will be closed out. | 20478
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Active | Design | Hans Mooy | 5150000 | 26500 | 15895 | 15895 | 14407.5 |  | 26500 | 0 | 0 | 0 | 0 | 3620000 | 02/24/2025 Construction documents being updated. | 20489
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Complete | Finalized | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 |  | 79415.5 | -44850 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20497
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Complete | Finalized | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 |  | 344155.26 | -36379 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20506
11 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Complete | Finalized | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 |  | 405791 | -43231.36 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20562
12 | TBD | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Deferred / On Hold | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | On hold per FRP 07/24/2024 until summer of 2026 | 20563
13 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 722586.68 |  | 781870 | -59283.32 | 0 | 0 | 0 | 0 | 11/22/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20566
14 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Complete | Finalized | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 1113460 |  | 1232681 | -119221 | 0 | 0 | 0 | 0 | 01/22/2024 Project is complete. Waiting on final invoice to clear to begin the closeout process. | 20573
15 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Complete | Finalized | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 195665 |  | 218202 | -22537 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20574
16 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Active | Construction | Hans Mooy | 1300000 | 1300000 | 1092354.21 | 1092354.21 | 259050.21 |  | 223000 | 0 | 1077000 | 0 | 1077000 | 2510000 | 02/24/2025 AHU in production, delivery is 26 weeks out (May/June 2025). | 20577
17 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Complete | Finalized | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 571789 |  | 630554 | -58765 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20644
18 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Complete | Finalized | Ben Bedock | 125875 | 125875 | 114350 | 114350 | 114350 |  | 125875 | -11525 | 0 | 0 | 0 | 0 | 02/26/2024 Punchlist items have been discussed with the contractor. Once items are completed, project is ready to closeout. | 20645
19 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Active | Award | Sean Rewers | 1550000 | 1545360 | 1355049 | 1355049 | 119500 |  | 146500 | 0 | 1398860 | 0 | 1398860 | 0 | 02/26/2025 Equipment submittals have been reviewed, awaiting some feedback from manufacturer but should release RTU in late Feb early march. Electrical is on order, controls we are awaiting submittals. Project slated for summer construction. | 20667
20 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design | Sean Rewers | 0 | 231433 | 231433 | 231433 | 116143 |  | 206500 | 24933 | 0 | 0 | 0 | 3960000 | 02/26/2025 We are awaiting definitive plans from the CUI project to determine where our chilled water connection will be. If hot water goes past the building as part of CUI we will rework the design to include hot water connection. | 20668
21 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Active | Financial Closeout | Sean Rewers | 680000 | 678513 | 586776.36 | 586776.36 | 586776.36 | 91736.64 | 29250 | 649263 | 0 | 0 | 0 | 0 | 11/25/2024 Project in FX | 20698
22 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 85576.77 |  | 79623 | 5954 | 0 | 0 | 0 | 0 | 11/27/2023 Project is in closeout | 20700
23 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Active | Construction | Sean Rewers | 500000 | 499093 | 419024.05 | 419024.05 | 248030 |  | 499093 | 0 | 0 | 0 | 0 | 0 | 03/03/2025 Remaining parts should be received early March. We will need to schedule reconnection of the building to the tanks which is ebing discussed first week of March. Steel grating has been installed. Adding pump repair to the project. | 20701
24 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Complete | Finalized | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 209419 |  | 239341 | -29922 | 0 | 0 | 0 | 0 | 12/18/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20702
25 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Complete | Finalized | Erin Fry | 715000 | 715000 | 656784.6 | 656784.6 | 656576.59 |  | 96166 | 0 | 0 | 0 | 0 | 0 | 02/23/2024 Construction complete. Library Closeout process complete. The Financial closeout process has been started. | 20718
26 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Active | Award | Jay Surprenant | 1610000 | 1700000 | 1521240.72 | 1521240.72 | 138595.02 |  | 160500 | 0 | 1539500 | 0 | 1539500 | 0 | 02/27/2025 Work began on identifying VAVs in need of replacement. Once final list is compiled, a CO will be issued. | 20723
27 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Active | Warranty or Construction Closeout | Hans Mooy | 1987500 | 1987500 | 1819618.65 | 1835588.65 | 1785460.4 | 167881.35 | 23400 | 1964100 | 0 | 0 | 0 | 0 | 02/24/2025 Project substantially complete. | 20724
28 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Complete | Finalized | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 276500 | 0 | 300000 | -23500 | 0 | 0 | 0 | 0 | 04/23/2024 Project is complete. | 20735
29 | Capital | 20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Active | Warranty or Construction Closeout | Jay Surprenant | 149000 | 148299 | 125699 | 125699 | 125699 | 22600 | 0 | 148299 | 0 | 0 | 0 | 0 | 02/27/2025 Moving through LC process. no change from last month. | 20767
30 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 |  | 24997 | -7025 | 0 | 0 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space. | 20771
31 | Capital | 20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction | Ben Bedock | 3200000 | 3200000 | 2936840.14 | 2936840.14 | 2911828.14 |  | 0 | 1600000 | 1600000 | 0 | 1600000 | 0 | 02/24/2025 Project is 99% complete. Scaffolding has been removed. Items that remain are one downspout, basement window painting and grate painting. | 20772
32 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized | Ben Bedock | 400000 | 483440 | 450775 | 450775 | 450775 |  | 483440 | -32665 | 0 | 0 | 0 | 0 | 12/18/2023 Construction complete. Waiting on final invoices to clear to begin the closeout process. | 20792
33 | Capital | 20811 | 8729 | CP_400224 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Active | Warranty or Construction Closeout | Ben Bedock | 75000 | 285233.27 | 253063.19 | 253063.19 | 121573.71 | 32170.08 | 0 | 285233.27 | 0 | 0 | 0 | 0 | 02/24/2025 Project is complete. Waiting on final invoices to clear to begin the closeout process. | 20811
34 | Capital | 20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Active | Design | Sean Rewers | 600000 | 38500 | 38500 | 38500 | 4500 |  |  |  | 38500 | 561500 | 600000 |  | 02/25/2025 Project will go out to bid in March for summer construction | 20812
35 | Operating | 20831 | 8230 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/30/2024 Project is in closeout. Study was completed and findings were shared with Provost and A&S. Due to the large scale renovations needed to the building this project will require further planning and cannot be priced our accurately. A&S will present the findings to their dean for further guidance on how to tackle the buildings issues. | 20831
36 | Operating | 20832 | 8220 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/22/2024 Project study and estimated pricing is complete. Project in closeout. | 20832
37 | Operating | 20833 | 8215 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 04/24/2024 Project is in closeout | 20833
38 | Operating | 20834 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - HVAC Upgrades - Engineering Study | Voided | Finalized | Sean Rewers | 5000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/27/2023 This project is on hold until October. We are awaiting approval from the CBO for initial funding which will be repaid by the FRP. | #N/A
39 | Capital | 20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Active | Construction | Ben Bedock | 499184 | 499184 | 475944.67 | 475944.67 | 243906.27 |  | 0 | 499184 | 0 | 0 | 0 | 0 | 02/24/2025 Finalizing the cab interiors. Jack replacement is scheduled for the week of spring break. | 20857
40 | Capital | 20884 | 8807 | CP_400251 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Exterior Window Painting | Active | Financial Closeout | Ben Bedock | 675650 | 675650 | 480318 | 480318 | 480318 | 195332 | 0 | 675650 | 0 | 0 | 0 | 0 | 08/23/2024 VUMO is managing this project. CPC is helping with the PO/financial process. | 20884
41 | Operating | 20885 | 8676 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Construction | Sean Rewers | 99000 | 143053.4 | 121224.26 | 121224.26 | 97943.4 |  | 0 | 113053.4 | 30000 | 0 | 30000 | 0 | 03/03/2025 Reworking vent lines to reduce condensation. Atlas is replacing all fans in all 3 compressors and still troubleshooting compressors that are not working. | 20885
42 | Operating | 20911 | 8819 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | Ben Bedock | 61045 | 61045 | 54613 | 54613 | 54613 | 6432 | 0 | 61045 | 0 | 0 | 0 | 0 | 02/24/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20911
43 | Operating | 20912 | 8822 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | Ben Bedock | 59798 | 59798 | 53366 | 53366 | 27741.06 | 6432 | 0 | 59798 | 0 | 0 | 0 | 0 | 02/24/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20912
44 | Operating | 20913 | 8818 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout | Ben Bedock | 96612 | 96612 | 86900 | 86900 | 45263.09 | 9712 | 0 | 96612 | 0 | 0 | 0 | 0 | 02/24/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20913
45 | Capital | 20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Exterior Improvements | Active | Warranty or Construction Closeout | Jay Surprenant | 170000 | 197150 | 170000 | 170000 | 170000 | 27150 | 0 | 197150 | 0 | 0 | 0 | 0 | 02/27/2025 Moved to library closeout. waiting on closeout documents from contractor. No change from last month. | 20922
46 | Operating | 20924 | 8737 |  | 19000 - Nursing: Office of the Dean | Nursing | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Active | Financial Closeout | Ben Bedock | 30570 | 30570 | 24500 | 24500 | 24500 | 6070 | 0 | 30570 | 0 | 0 | 0 | 0 | 11/26/2024 Construction is complete. Waiting on the final invoice to begin the closeout process. | 20924
47 | Capital | 20925 | 8260 |  | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Active | Design | Hans Mooy | 2850000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3140000 | 02/24/2025 Kickoff meeting to occurred. Page Flip scheduled for 03/17/25. | 20925
48 | Operating | 20936 | 8814 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Active | Warranty or Construction Closeout | Jay Surprenant | 405000 | 404655.91 | 357255.91 | 357255.91 | 357255.91 | 47400 | 0 | 404655.91 | 0 | 0 | 0 | 0 | 02/27/2025 Project completed. Moving to Library Closeout. No change from last month. | 20936
49 | Capital | 20940 | 8412 | CP_400291 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Active | Construction | Sean Rewers | 310000 | 309548.64 | 296749.81 | 296749.81 | 22423.67 |  | 0 | 0 | 309548.64 | 0 | 309548.64 | 0 | 02/25/2025 Door hardware has been installed, all but 1 camera has been installed, punchlist walk scheduled for the end of February | 20940
50 | Operating | 20945 | 8905 |  | 10000 - Chancellor | Other | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Active | Financial Closeout | Sean Rewers | 99000 | 99000 | 82897 | 82897 | 70200 | 16103 | 0 | 99000 | 0 | 0 | 0 | 0 | 11/25/2024 We are awaiting TAB and other reports from Nashville Machine, then we will put into FX. | 20945
51 | Capital | 20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction | Ben Bedock | 290000 | 261629 | 239133 | 239133 | 77312.4 |  | 0 | 18175 | 243454 | 0 | 243454 | 0 | 02/24/2025 PO has been issued to the contractor. Engineering drawings, review and production has started. Construction to start on 05/13/2025. | 20958
52 | Capital | 20962 | 8754 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Roof Replacement | Active | Award | Ben Bedock | 1750000 | 1800 | 1800 | 1800 | 0 |  | 0 | 0 | 1800 | 2000000 | 2001800 | 0 | 02/24/2025 Pricing sent to FRP. Awaiting approval to move forward with the PO process. | 20962
53 | Capital | 20979 | 9 |  | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Active | Programming or Planning | Ben Bedock | 270000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 02/24/2025 Working with the appropriate parties to determine the scope of work and the time frame of the work. | 20979
54 | Capital | 20982 | 8442 | CP_400270 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction | Ben Bedock | 272000 | 272000 | 249821 | 249821 | 11175 |  | 0 | 18175 | 253825 | 0 | 253825 | 0 | 02/24/2025 PO has been issued to the contractor. Engineering drawings, review and production has started. Construction to start on 05/13/2025. | 20982
55 | Operating | 20984 | 8712 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Active | Warranty or Construction Closeout | Hans Mooy | 167000 | 167000 | 143484.6 | 143484.6 | 122986 | 23515.4 | 0 | 0 | 167000 | 0 | 167000 | 0 | 02/24/2025 Project complete... | 20984
56 | Capital | 21004 | 1010 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Active | Programming or Planning | Jay Surprenant | 0 | 54000 | 44000 | 44000 | 35200 |  | 0 | 0 | 54000 | 0 | 54000 | 0 | 02/27/2025 Bids received. De-scope discussion scheduled for 3/3, with budget submission to follow contractor selection. | 21004
57 | Capital | 21005 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 09/24/2024 This is FY 26 project. No updates to provide yet. Project not started. | 21005
58 | Capital | 21006 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 09/24/2024 Project not started. this is an FY28 project. | 21006
59 | Capital | 21007 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 09/24/2024 Project not started. This is an FY29 project. | 21007
60 | Capital | 21010 |  | CP_400312 | 15000 - Engineering: Office of the Dean | Engineering | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Award | Sean Rewers | 125000 | 126024 | 0 | 0 | 0 |  | 0 | 0 | 126024 | 0 | 126024 | TBD | 02/25/2025 VU Engineering has determined unit that needs to be installed, PO has been started for Nashville Machine. | 21010
61 | Capital | 21051 | 8784 |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 02/27/2025 Added to project discussion with Anthony Tharp. Not ready to bid out yet. | 21051
62 | Capital | 21066 |  | CP_400314 | 12100 - Arts and Science: Business Affairs | Arts & Science | SC MOLEC BIOLOGY | SC2 - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 0 | 29160 | 0 | 0 | 0 |  | 0 | 0 | 29160 | 0 | 29160 | TBD | 02/25/2025 Awaiting PO to start study | 21066
63 | Capital | 21067 |  | CP_400311 | 19000 - Nursing: Office of the Dean | Nursing | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades | Active | Design | Sean Rewers | 0 | 46600 | 0 | 46600 | 0 |  | 0 | 0 | 46600 | 0 | 46600 | TBD | 02/26/2025 Awaiting PO for mechanical and architectural design. | 21067
64 | Operating | 21068 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Insulate First Floor Slab | Active | Bidding | Jay Surprenant | 0 | 34837.4 | 0 | 24737.4 | 0 |  | 0 | 0 | 34837.4 | 0 | 34837.4 | TBD | 02/27/2025 Budget submitted, once approved work will be scheduled. | 21068
65 | TBD | 21070 |  |  | 15000 - Engineering: Office of the Dean | Engineering | OLIN HALL | Olin Hall - Exterior Facade Cleaning | Active | Bidding | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 02/24/2025 Project is currently out to bid. | 21070
66 | Capital | 21071 |  | CP_400313 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC MATH | SC1 - MEP Feasibility Study | Active | Award | Sean Rewers | 0 | 19440 | 0 | 0 | 0 |  | 0 | 0 | 19440 | 0 | 19440 | TBD | 02/25/2025 Po has been started | 21071
67 | Operating | 21094 |  |  | 19100 - Nursing: Business Affairs | Nursing | GODCHAUX HALL | Godchaux Hall - Replace Fire Pump | Active | Award | Sean Rewers | 87500 | 0 | 0 | 0 | 0 |  | 0 | 0 | 87500 | 0 | 87500 | TBD | 02/25/2025 Project has been awarded to Bouchard, awaiting PO, work will likely be during summer 2025 | 21094
68 | Operating | 21108 |  |  | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Electrical and HVAC Study | Active | Award | Sean Rewers | 5000 | 5000 | 0 | 5000 | 0 |  | 0 | 0 | 5000 | 0 | 5000 | TBD | 02/24/2025 Working on PO for Envision | 21108
69 | TBD | 21113 |  |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - Lecture Hall V1220 Lighting Upgrade | Active | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 02/27/2025 Discussing project details with Anthony Tharp week of March 3rd in our regular project update meeting. Will put together a scope for bid out after. | 21113
70 | TBD | 21114 |  |  | 18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences | MRB III BIO/SCI | MRBIII - Chemical Discharge Tank Replacement | Active | Bidding | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TBD | 02/27/2025 Project bid out 2/24, bids due 3/3. | 21114
[12 empty] | 41438101.76 | 31135305.98 | 28240279.21 | 28256249.21 | 23140070.46 | 907774.99 | 8797286.26 | 11427472.94 | 6969083.18 | 2561500 | 9530583.18 | 13230000
[18 empty] | TRUE | TRUE
[18 empty] | TRUE | TRUE | TRUE |  | TRUE
Projects to be discussed
Law School - replace front stairs ($200k - $400k)
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes roof repairs in scope.
Note on M10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on X11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project will be joint funded, FPR / Divinity + Dean of Students.
Note on X19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Phase 2 estimate. May be a separate project ID.
Note on M28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10085 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | 9364499 | 17500 |  | 17500
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Warranty / Construction Closeout | Finalized |  | 1216485.5 |  | 1216485.5
| 3 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Design | Financial Closeout |  | 4900 |  | 4900
| 4 | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Warranty / Construction Closeout | Finalized |  | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Construction | Finalized |  | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Construction | Warranty or Construction Closeout |  | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Bidding | Warranty or Construction Closeout |  | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Design | Design |  | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Construction | Finalized |  | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Construction | Finalized |  | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Construction | Finalized |  | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Construction | Finalized |  | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Construction | Finalized |  | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Construction | Finalized |  | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Design | Construction |  | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Construction | Finalized |  | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Award | Finalized |  | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Design | Award |  | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Design |  | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Design | Financial Closeout |  | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Construction | Finalized |  | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Award | Construction |  | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Construction | Finalized |  | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Construction | Finalized |  | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Programming / Planning | Award |  | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Design | Warranty or Construction Closeout |  | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Construction | Finalized |  | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Construction | Finalized |  | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Award | Finalized |  | 483440 |  | 483440
[8 empty] | 8797286.26 | 0 | 8797286.26 | 567212.74
TRUE
FY 2024 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Active | Financial Closeout | 11029283.29 | 255957 |  | 255957 |  | phase 1
| 2 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Active | Warranty or Construction Closeout |  | 3660360 |  | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Active | Warranty or Construction Closeout |  | 1028900 |  | 1028900
| 4 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design |  | 24933 |  | 24933
| 5 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Active | Financial Closeout |  | 649263 |  | 649263
| 6 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized |  | 5954 |  | 5954
| 7 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Active | Warranty or Construction Closeout |  | 1964100 |  | 1964100
| 8 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Active | Warranty or Construction Closeout |  | 148299 |  | 148299
| 9 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction |  | 1600000 |  | 1600000
| 10 | 20811 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Active | Warranty or Construction Closeout |  | 285233.27 |  | 285233.27
| 11 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized |  | 24000 |  | 24000
| 12 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Complete | Finalized |  | 24000 |  | 24000
| 13 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Complete | Finalized |  | 24000 |  | 24000
| 14 | 20857 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Active | Construction |  | 499184 |  | 499184
| 15 | 20884 | LAW SCHOOL | Law School - Exterior Window Painting | Active | Financial Closeout |  | 675650 |  | 675650
| 16 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Construction |  | 113053.4 |  | 113053.4
| 17 | 20911 | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Active | Warranty or Construction Closeout |  | 61045 |  | 61045
| 18 | 20912 | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout |  | 59798 |  | 59798
| 19 | 20913 | WILSON HALL | Wilson Hall - Elevator Upgrades | Active | Warranty or Construction Closeout |  | 96612 |  | 96612
| 20 | 20922 | VAUGHN HOME | Vaughn Home - Exterior Improvements | Active | Warranty or Construction Closeout |  | 197150 |  | 197150
| 21 | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Active | Financial Closeout |  | 30570 |  | 30570
| 22 | 20936 | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Active | Warranty or Construction Closeout |  | 404655.91 |  | 404655.91
| 23 | 20945 | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Active | Financial Closeout |  | 99000 |  | 99000
| 24 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction |  | 18175 |  | 18175
| 25 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction |  | 18175 |  | 18175
|  | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized |  | -4400.96 |  | -4400.96
|  | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Complete | Finalized |  | -47290 |  | -47290
|  | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Complete | Finalized |  | -44850 |  | -44850
|  | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Complete | Finalized |  | -36379 |  | -36379
|  | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Complete | Finalized |  | -43231.36 |  | -43231.36
|  | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized |  | -59283.32 |  | -59283.32
|  | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Complete | Finalized |  | -119221 |  | -119221
|  | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Complete | Finalized |  | -22537 |  | -22537
|  | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Complete | Finalized |  | -58765 |  | -58765
|  | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Complete | Finalized |  | -11525 |  | -11525 | prior year
|  | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Complete | Finalized |  | -29922 |  | -29922 | carryforward
|  | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized |  | -7025 |  | -7025
|  | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized |  | -32665 |  | -32665 | 567212.74
|  | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Complete | Finalized |  | -23500 |  | -23500
[8 empty] | 11427472.94 | 0 | 11427472.94 | 169023.09
FY 2025 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining | Estimated
| 1 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Active | Construction | 12857284.4623 | 1077000 | 0 | 1077000 |  | Hans Mooy
| 2 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Active | Award |  | 1398860 | 0 | 1398860 |  | Sean Rewers
| 3 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Active | Award |  | 1539500 | 0 | 1539500 |  | Jay Surprenant
| 4 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Active | Construction |  | 1600000 | 0 | 1600000 |  | Ben Bedock
| 5 | 20812 | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Active | Design |  | 38500 | 561500 | 600000 |  | Sean Rewers
| 6 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Construction |  | 30000 | 0 | 30000
| 7 | 20940 | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Active | Construction |  | 309548.64 | 0 | 309548.64 |  | Sean Rewers
| 8 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction |  | 243454 | 0 | 243454 |  | Ben Bedock
| 9 | 20962 | VAUGHN HOME | Vaughn Home - Roof Replacement | Active | Award |  | 1800 | 2000000 | 2001800 |  | Ben Bedock
| 10 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction |  | 253825 | 0 | 253825 |  | Ben Bedock
| 11 | 20984 | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Active | Warranty or Construction Closeout |  | 167000 | 0 | 167000 |  | Hans Mooy
| 12 | 21004 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Active | Programming or Planning |  | 54000 | 0 | 54000 |  | Jay Surprenant
| 13 | 21010 | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Award |  | 126024 | 0 | 126024 |  | Sean Rewers
| 14 | 21051 | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning |  | 0 | 0 | 0
| 15 | 21066 | SC MOLEC BIOLOGY | SC2 - MEP Feasibility Study | Active | Programming or Planning |  | 29160 | 0 | 29160
| 16 | 21067 | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades | Active | Design |  | 46600 | 0 | 46600
| 17 | 21068 | BUTTRICK HALL | Buttrick Hall - Insulate First Floor Slab | Active | Bidding |  | 34837.4 | 0 | 34837.4
| 18 | 21070 | OLIN HALL | Olin Hall - Exterior Facade Cleaning | Active | Bidding |  | 0 | 0 | 0
| 19 | 21071 | SC MATH | SC1 - MEP Feasibility Study | Active | Award |  | 19440 | 0 | 19440
| 20 | 21094 | GODCHAUX HALL | Godchaux Hall - Replace Fire Pump | Active | Award |  | 87500 | 0 | 87500
| 21 | 21108 | 1025 16TH AVE S | 1025 16th Avenue - Electrical and HVAC Study | Active | Award |  | 5000 | 0 | 5000
| 22 | 21113 | MRB III BIO/SCI | MRBIII - Lecture Hall V1220 Lighting Upgrade | Active | Programming or Planning |  | 0 | 0 | 0
| 23 | 21114 | MRB III BIO/SCI | MRBIII - Chemical Discharge Tank Replacement | Active | Bidding |  | 0 | 0 | 0
prior year
carryforward
|  | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Complete | Finalized |  | -92965.86 | 0 | -92965.86 | 169023.09
[8 empty] | 6969083.18 | 2561500 | 9530583.18 | 3495724.3723 | 0
TRUE
FY 2026 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Active | Design | 13263819.6534 |  | 3620000 | 3620000
| 2 | 20925 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Active | Design |  |  | 3140000 | 3140000
| 3 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design |  |  | 3960000 | 3960000
| 4 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Deferred / On Hold | Not Started |  |  | TBD | TBD
| 5 | 20979 | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Active | Programming or Planning |  |  | TBD | TBD
| 6 | 21005 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Deferred / On Hold | Programming or Planning |  |  | TBD | TBD
| 7 | 21006 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Deferred / On Hold | Programming or Planning |  |  | TBD | TBD
| 8 | 21007 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Deferred / On Hold | Programming or Planning |  |  | TBD | TBD
| 9 | 21010 | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Award |  |  | TBD | TBD
| 10 | 21051 | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning |  |  | TBD | TBD
[8 empty] | 0 | 10720000 | 10720000 | 2543819.6534
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Preliminary cost estimates presented in three options. $4M - $5M range.

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | 17500 | 22000
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 4500

## 10098 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized | 1216485.5 | 1216485.5
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | crowhus_01302024_FRP | FX2-1 |  | -4400.96
|  |  |  | Total transfers from FRP cash |  |  | 1212084.54
|  |  |  | Balance |  |  | 4400.96

## 10146
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Financial Closeout | Sean Rewers | 318057 | 253826.81
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | crowhus_01302024_FRP | BAC-5 |  | 244457
|  |  |  | FY24 subtotal |  |  | 255957
|  |  |  | Balance |  |  | 0

## 20179 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Complete | Finalized | 1445389 | 1445389
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
|  |  |  | crowhus_08312024_FRP |  |  | -92965.86
1352423.14
|  |  |  | Total transfers from FRP cash |  |  | 629728.64
|  |  |  | Balance |  |  | 92965.86

## 20336 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Complete | Finalized | 327890 | 327890
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -47290
|  |  |  | Total transfers from FRP cash |  |  | 280600
|  |  |  | Balance |  |  | 47290

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy | 3800000 | 3529404.41
[9 empty] | 75% | 25%
[9 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 |  | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 |  | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 |  | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360
All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
3800000
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2652824.48
[9 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 |  | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 |  | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 |  | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
[7 empty] | 2790000 |  | 1110000 | 1680000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Design | Hans Mooy | 26500 | 14407.5
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | Total transfers from FRP cash |  |  | 26500
|  |  |  | Balance |  |  | 0

## 20497 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Complete | Finalized | 456850 | 456850
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -44850
|  |  |  | Total transfers from FRP cash |  |  | 412000
|  |  |  | Balance |  |  | 44850

## 20506 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Complete | Finalized | 344155.26 | 344155.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -36379
|  |  |  | Total transfers from FRP cash |  |  | 307776.26
|  |  |  | Balance |  |  | 36379

## 20562 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Complete | Finalized | 400000 | 405791
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -43231.36
|  |  |  | Total transfers from FRP cash |  |  | 362559.64
|  |  |  | Balance |  |  | 43231.36

## 20566 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized | 781870 | 781870
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | crowhus_02292024_FRP | FX |  | -59283.32
|  |  |  | Total transfers from FRP cash |  |  | 722586.68
|  |  |  | Balance |  |  | 59283.32

## 20573 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Complete | Finalized | 1232681 | 1232681
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -119221
|  |  |  | Total transfers from FRP cash |  |  | 1113460
|  |  |  | Balance |  |  | 119221

## 20574 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Complete | Finalized | 218202 | 218202
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -22537
|  |  |  | Total transfers from FRP cash |  |  | 195665
|  |  |  | Balance |  |  | 22537

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Hans Mooy | 1300000 | 259050.21
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | crowhus_10312024_FRP | BAC-4 |  | 1077000
|  |  |  | Total transfers from FRP cash |  |  | 1300000
|  |  |  | Balance |  |  | 0

## 20644 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Complete | Finalized | 630554 | 630554
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -58765
|  |  |  | Total transfers from FRP cash |  |  | 571789
|  |  |  | Balance |  |  | 58765

## 20645 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Complete | Finalized | 125875 | 125875
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | crowhus_04302024_FRP | FX2-1 |  | -11525
|  |  |  | Total transfers from FRP cash |  |  | 114350
|  |  |  | Balance |  |  | 11525

## 20667
Project Status'!A1
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Award | Sean Rewers | 1545360 | 119500
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_12312024_FRP | BAC-4 |  | 1398860
|  |  |  | Total transfers from FRP cash |  |  | 1545360
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 231433 | 116143
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_10312023_FRP | BAC-4 |  | 24933
|  |  |  | Total transfers from FRP cash |  |  | 231433
|  |  |  | Balance |  |  | 0

## 20698
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Financial Closeout | Sean Rewers | 678513 | 586776.36
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | crowhus_01302024_FRP | BAC-4 | ` | 649263
|  |  |  | Total transfers from FRP cash |  |  | 678513
|  |  |  | Balance |  |  | 0

## 20700 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized | 80000 | 85577
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | -5577

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Construction | Sean Rewers | 499093 | 248030
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | Total transfers from FRP cash |  |  | 499093
|  |  |  | Balance |  |  | 0

## 20702 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Complete | Finalized | 225791 | 239341
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | crowhus_02292024_FRP | FX |  | -29922
|  |  |  | Total transfers from FRP cash |  |  | 209419
|  |  |  | Balance |  |  | 29922

## 20718 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Complete | Finalized | 715000 | 715000
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Award | Jay Surprenant | 1700000 | 138595.02
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | crowhus_10312024_FRP |  |  | 1539500
|  |  |  | Total transfers from FRP cash |  |  | 1700000
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line - FY 23 | Warranty or Construction Closeout | Hans Mooy | 1987500 | 1785460.4
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | crowhus_12192023_FRP | BAC-2 |  | 1964100
|  |  |  | Total transfers from FRP cash |  |  | 1987500
|  |  |  | Balance |  |  | 0

## 20735 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Complete | Finalized | 300000 | 300000
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | crowhus_06302024_FRP | FX2-1 |  | -23500
|  |  |  | Total transfers from FRP cash |  |  | 276500
|  |  |  | Balance |  |  | 23500

## 20767
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Six Magnolia Circle - Foundation Repairs | Warranty or Construction Closeout | Jay Surprenant | 148299 | 125699
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 148299
|  |  |  | Total transfers from FRP cash |  |  | 148299
|  |  |  | Balance |  |  | 0

## 20771 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized | 25000 | 24997
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -7025
|  |  |  | Total transfers from FRP cash |  |  | 17972
|  |  |  | Balance |  |  | 7025

## 20792 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized | 400000 | 483440
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | crowhus_02292024_FRP | FX |  | -32665
|  |  |  | Total transfers from FRP cash |  |  | 450775
|  |  |  | Balance |  |  | 32665

## 20831 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20831 | 8230 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20832 | 8220 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20833 | 8215 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement (Design Services) | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20772
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20772 | 8675 | CP_400235 | 20000 - Owen: Office of the Dean | OGSM Old Mechanical- Slate Roof & Window Replacement | Construction | Ben Bedock | 3200000 | 2911828.14
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 1600000
|  |  |  | crowhus_07312024_FRP | BAC-1 |  | 1600000
|  |  |  | Total transfers from FRP cash |  |  | 3200000
|  |  |  | Balance |  |  | 0

## 20811
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20811 | 8729 | CP_400224 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Retaining Wall Repair | Warranty or Construction Closeout | Ben Bedock | 285233.27 | 121573.71
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 285233.27
|  |  |  | Total transfers from FRP cash |  |  | 285233.27
|  |  |  | Balance |  |  | 0
Original budget (BAC-1) for $2,640 set up as a Facilities capital project, owning org 37000. It has been determined this is an FRP project and will be assigned to Peabody. Owning org has been updated in Oracle.

## 20812
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Patio Repairs | Design | Sean Rewers | 38500 | 4500
Funding transfers
|  |  |  | crowhus_08312024_FRP | BAC-1 |  | 4500
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 34000
|  |  |  | Total transfers from FRP cash |  |  | 38500
|  |  |  | Balance |  |  | 0

## 20857
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Elevator Modernization | Construction | Ben Bedock | 499184 | 243906.27
Funding transfers
|  |  |  | crowhus_10312023_FRP | BAC-1 |  | 17600
|  |  |  | crowhus_01302024_FRP | BAC-2 |  | 4000
|  |  |  | crowhus_03312024_FRP | BAC-3 |  | 477584
|  |  |  | Total transfers from FRP cash |  |  | 499184
|  |  |  | Balance |  |  | 0

## 20884
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20884 | 8807 | CP_400251 | 17100 - Law: Business Affairs | Law School - Exterior Window Painting | Financial Closeout | Ben Bedock | 675650 | 480318
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-3 |  | 675650
|  |  |  | Total transfers from FRP cash |  |  | 675650
|  |  |  | Balance |  |  | 0

## 20885
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20885 | 8676 | 0 | 12000 - Arts and Science: Office of the Dean | NMR - Replace Air Compressors | Construction | Sean Rewers | 143053.4 | 97943.4
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-2 |  | 98341
|  |  |  | crowhus_05312024_FRP | BAC-3 |  | 14712.4
|  |  |  | crowhus_09302024_FRP | BAC-4 |  | 30000
|  |  |  | Total transfers from FRP cash |  |  | 143053.4
|  |  |  | Balance |  |  | 0

## 20911
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20911 | 8819 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Elevator Upgrades | Warranty or Construction Closeout | Ben Bedock | 61045 | 54613
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 56945
|  |  |  | Total transfers from FRP cash |  |  | 61045
|  |  |  | Balance |  |  | 0

## 20912
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20912 | 8822 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Hall - Elevator Upgrades | Warranty or Construction Closeout | Ben Bedock | 59798 | 27741.06
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 55698
|  |  |  | Total transfers from FRP cash |  |  | 59798
|  |  |  | Balance |  |  | 0

## 20913
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20913 | 8818 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Elevator Upgrades | Warranty or Construction Closeout | Ben Bedock | 96612 | 45263.09
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 92512
|  |  |  | Total transfers from FRP cash |  |  | 96612
|  |  |  | Balance |  |  | 0

## 20922
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Vaughn Home - Exterior Improvements | Warranty or Construction Closeout | Jay Surprenant | 197150 | 170000
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 197150
|  |  |  | Total transfers from FRP cash |  |  | 197150
|  |  |  | Balance |  |  | 0

## 20924
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20924 | 8737 | 0 | 19000 - Nursing: Office of the Dean | Frist Hall - Stairwell Roof Replacement | Financial Closeout | Ben Bedock | 30570 | 24500
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 30570
|  |  |  | Total transfers from FRP cash |  |  | 30570
|  |  |  | Balance |  |  | 0

## 20936
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20936 | 8814 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Lighting Retrofit for 103 and 126 | Warranty or Construction Closeout | Jay Surprenant | 404655.91 | 357255.91
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 404655.91
|  |  |  | Total transfers from FRP cash |  |  | 404655.91
|  |  |  | Balance |  |  | 0

## 20940
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20940 | 8412 | CP_400291 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Security System Replacement | Construction | Sean Rewers | 309548.64 | 22423.67
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 294789
|  |  |  | crowhus_01312025_FRP | BAC-3 |  | 14759.64
|  |  |  | Total transfers from FRP cash |  |  | 309548.64
|  |  |  | Balance |  |  | 0

## 20945
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20945 | 8905 | 0 | 10000 - Chancellor | Seigenthaler Building - HVAC Improvements | Financial Closeout | Sean Rewers | 99000 | 70200
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 99000
|  |  |  | Total transfers from FRP cash |  |  | 99000
|  |  |  | Balance |  |  | 0

## 20958
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Furman Hall - Elevator Modernization | Construction | Ben Bedock | 261629 | 77312.4
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 243454
|  |  |  | Total transfers from FRP cash |  |  | 261629
|  |  |  | Balance |  |  | 0

## 20962
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20962 | 8754 | 0 | 12000 - Arts and Science: Office of the Dean | Vaughn Home - Roof Replacement | Award | Ben Bedock | 1800 | 0
Funding transfers
|  |  |  | crowhus_01312025_FRP | BAC-1 |  | 1800
|  |  |  | Total transfers from FRP cash |  |  | 1800
|  |  |  | Balance |  |  | 0

## 20982
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20982 | 8442 | CP_400270 | 17100 - Law: Business Affairs | Law School - Elevator 1 Modernization | Construction | Ben Bedock | 272000 | 11175
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_10312024_FRP | BAC-2 |  | 253825
|  |  |  | Total transfers from FRP cash |  |  | 272000
|  |  |  | Balance |  |  | 0

## 20984
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20984 | 8712 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - 1st Floor Urinal Replacement | Warranty or Construction Closeout | Hans Mooy | 167000 | 122986
Funding transfers
|  |  |  | crowhus_09302024_FRP | BAC-1 |  | 167000
|  |  |  | Total transfers from FRP cash |  |  | 167000
|  |  |  | Balance |  |  | 0

## 21004
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21004 | 1010 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Programming or Planning | Jay Surprenant | 54000 | 35200
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 54000
|  |  |  | Total transfers from FRP cash |  |  | 54000
|  |  |  | Balance |  |  | 0

## 21010
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21010 | 0 | CP_400312 | 15000 - Engineering: Office of the Dean | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Award | Sean Rewers | 126024 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 126024
|  |  |  | Total transfers from FRP cash |  |  | 126024
|  |  |  | Balance |  |  | 0

## 21066
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21066 | 0 | CP_400314 | 12100 - Arts and Science: Business Affairs | SC2 - MEP Feasibility Study | Programming or Planning | Sean Rewers | 29160 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 29160
|  |  |  | Total transfers from FRP cash |  |  | 29160
|  |  |  | Balance |  |  | 0

## 21067
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21067 | 0 | CP_400311 | 19000 - Nursing: Office of the Dean | Godchaux Hall - Phase 2 HVAC Upgrades | Design | Sean Rewers | 46600 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 33600
|  |  |  | crowhus_02282025_FRP | BAC-2 |  | 13000
|  |  |  | Total transfers from FRP cash |  |  | 46600
|  |  |  | Balance |  |  | 0

## 21068
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21068 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Insulate First Floor Slab | Bidding | Jay Surprenant | 34837.4 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 34837.4
|  |  |  | Total transfers from FRP cash |  |  | 34837.4
|  |  |  | Balance |  |  | 0

## 21071
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21071 | 0 | CP_400313 | 12000 - Arts and Science: Office of the Dean | SC1 - MEP Feasibility Study | Award | Sean Rewers | 19440 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 19440
|  |  |  | Total transfers from FRP cash |  |  | 19440
|  |  |  | Balance |  |  | 0

## 21094
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21094 | 0 | 0 | 19100 - Nursing: Business Affairs | Godchaux Hall - Replace Fire Pump | Award | Sean Rewers | 0 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 87500
|  |  |  | Total transfers from FRP cash |  |  | 87500
|  |  |  | Balance |  |  | -87500

## 21108
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21108 | 0 | 0 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Electrical and HVAC Study | Award | Sean Rewers | 5000 | 0
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 5000
|  |  |  | Total transfers from FRP cash |  |  | 5000
|  |  |  | Balance |  |  | 0

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26 | 93.94%
| Balance | 567212.74 | 6.057%

## JE LOG_FY24
Project Status'!A1
Completed journal entries
Sources
| crowhus_08072023_FRP | 11029283.29
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| crowhus_10312023_FRP | -45721
| crowhus_12192023_FRP | 1964100
| crowhus_01302024_FRP | 893319.04
| crowhus_02292024_FRP | -11229.32
| crowhus_03312024_FRP | 638993.64
| crowhus_04302024_FRP | 1384584.18
| crowhus_05312024_FRP | 230037.4
| crowhus_06302024_FRP | 1594675
| Total Uses | 11427472.94
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 169023.09 | DB: | CR:
|  |  | 7025 | 24933
|  |  | 36379 | 17600
44850
|  |  | 88254 | 42533 | 130787
-45721
|  |  | DB: | CR:
|  |  | 1964100 | 1964100
|  |  | 1964100 | 1964100
|  |  | 3928200 | 3928200
0
|  |  | DB: | CR:
649263
244457
4000
4400.96
|  |  | 4400.96 | 897720 | 902120.96
893319.04
|  |  | DB: | CR:
12300
98341
59283.32
29922
32665
|  |  | 121870.32 | 110641 | 232511.32
-11229.32
|  |  | DB: | CR:
148299
|  |  | 47290 | 477584
|  |  | 43231.36 | 56945
|  |  | 119221 | 55698
|  |  | 22537 | 92512
|  |  | 58765 | 99000
|  |  | 291044.36 | 930038 | 1221082.36
638993.64
|  |  | DB: | CR:
285233.27
675650
30570
404655.91
11525
|  |  | 11525 | 1396109.18 | 1407634.18
1384584.18
|  |  | 460074.8 | 230037.4
|  |  | DB: | CR:
18175
1600000
23500
|  |  | 23500 | 1618175 | 1641675
1594675

## JE LOG_FY25
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 12857284.4623 | tbd | 0
| Total sources | 12857284.4623
Uses
| crowhus_07312024_FRP | 1600000
| crowhus_08312024_FRP | 188988.14
| crowhus_09302024_FRP | 197000
| crowhus_10312024_FRP | 3219114
| crowhus_12312024_FRP | 1398860
| crowhus_01312025_FRP | 16559.64
| crowhus_02282025_FRP | 348561.4
| Total Uses | 6969083.18
| plus carryforward | 169023.09
| (less) TBD | 0 |  |  | DB: | CR:
38500
| Balance | 6057224.3723 |  |  |  | 243454
92965.86
[5 empty] | 92965.86 | 281954 | 374919.86
188988.14
[5 empty] | DB: | CR:
1800
14759.64
33119.28
[5 empty] | 33119.28 | 16559.64 | 49678.92
-16559.64

## lookup
eBuilder | Summary
12000 - Arts and Science: Office of the Dean | Arts & Science
12100 - Arts and Science: Business Affairs | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17000 - Law: Office of the Dean | Law
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | SOM Basic Sciences
19000 - Nursing: Office of the Dean | Nursing
19100 - Nursing: Business Affairs | Nursing
20000 - Owen: Office of the Dean | Owen
21000 - Peabody College: Office of the Dean | Peabody

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.