## Timeline
Date | Owner | Change# | Hardware Migrations to Nexus 7710s | Start Time | End Time | Notes
2016-08-11 |  | C0069743 | Nexus 5k's supporting rows 45 and 49 |  |  | Complete
2016-08-12 |  | C0070630 | Star-VUH36 firewall cluster |  |  | Complete
2016-08-12 |  | C0070630 | VUH-HS firewall cluster |  |  | Complete
2016-08-15 |  | C0070632 | VUH-DC firewall cluster |  |  | Complete
2016-08-15 |  | C0070632 | Star-VUH42 firewall cluster |  |  | Complete
2016-08-15 |  | C0070632 | Check Point log server |  |  | Complete
2016-08-16 |  | C0070633 | Juniper SRX firewall cluster |  |  | Complete
2016-08-17 |  | C0069665 | Nexus 5k's supporting row 17 |  |  | Complete
2016-08-18 |  | C0070917 | Viprions/GTMs |  |  | Complete
2016-08-19 |  | C0070450 | Nexus 5k's supporting rows B45 and B49 |  |  | Complete
2016-08-25 |  | C0070445 | Nexus 5k's supporting row B42 |  |  | Complete
2016-08-31 | CM |  | COMM: Meeting with HealthIT to review the change |  |  | Complete
2016-09-08 |  | C0071659 | Mainframe (non GIE) |  |  | Complete
2016-09-08 |  | C0071815 | Hill DC |  |  | Complete
2016-09-21 |  | C0072413 | 3750 - 10.109.0.147 & 10.109.0.116 |  |  | Complete
TBD |  | TBD | 3750 - 10.109.0.23, 10.109.0.91, 10.109.0.92 |  |  | In progress
2016-10-03 | CM |  | COMM: General communication to all of VUIT regarding the change advise of community meeting
2016-10-10 | CM |  | COMM: Community meeting to review change Q & A session
2016-10-13 |  | C0072410 | Imagecast Upgrade or Move |  |  | Complete
2016-10-17 |  | PAC-C0073938 | Migrate Mainframe HMC |  |  | Complete
2016-10-19 |  | C0073821 | 3750 - 10.109.0.41
2016-10-30 |  | C0071679 | Mainframe (GIE)
2016-11-07 | CM |  | COMM: Final reminder of change
2016-11-11 |  | C0068671 | Cutover
2016-11-16 |  |  | Move directory services from HSFW to new PAN 7050 |  |  | 11/9 cutover is not dependent on this change
NIGHT OF CHANGE
2016-11-11 |  | C0068671 | Layer 2 and 3 cutover to Nexus 7710s
2016-11-11 |  |  | Gather the troops | 9:30 p.m. |  | Hill Center
2016-11-11 | Chris |  | Go / No go call from Nancy Evans | 10:55 p.m. | 11:00 p.m.
2016-11-11 | Chris |  | Start technical group IM | 11:00 p.m. | Completion
2016-11-11 | Chris |  | Start conference bridge - General | 11:00 p.m. | Completion
2016-11-11 | DBA's |  | Shut down all silver level applications | 11:35 p.m. | 12:05 a.m.
2016-11-11 | DBA's |  | Fail over to one node all gold level applications | 11:35 p.m. | 12:05 a.m.
2016-11-12 |  |  | BEGIN THE CHANGE | 12:05 a.m.
2016-11-12 | Josh |  | Config, verify routing / switching | 12:05 a.m. | 1:05 a.m.
2016-11-12 | Dave |  | Config, verify routing / switching | 12:05 a.m. | 1:05 a.m.
2016-11-12 | Barry |  | Verify routing / switching | 12:45 a.m. | Completion
2016-11-12 | Ed |  | Verify switches | 12:45 a.m. | Completion
2016-11-12 | Nick |  | Verify switches | 12:45 a.m. | Completion
2016-11-12 | Erik |  | Verify firewalls | 12:45 a.m. | Completion
2016-11-12 | Katie |  | Verify firewalls | 12:45 a.m. | Completion
2016-11-12 | James (Chad backup) |  | Verify Viprions / GTM | 12:45 a.m. | Completion
2016-11-12 |  |  | BEGIN TESTING | 1:30 a.m. | Completion
2016-11-12 | DBA's |  | Restart all silver level applications | 1:30 a.m. | 2:00 a.m.
2016-11-12 | DBA's |  | Restore secondary nodes for gold level applications | 1:30 a.m. | 2:00 a.m.
2016-11-12 | ALL |  | CLOSE CHANGE / END CONFERENCE BRIDGES | 2:00 a.m.

## Gold
GOLD level applications will fail over to the DR node
MC01PRD | Amanita
MC01PRD | Application Roles
MC01PRD | APPTDIAGHISTADM
MC01PRD | Bamboo
MC01PRD | Bedboard
MC01PRD | Brms
MC01PRD | Combo
MC01PRD | Compounds
MC01PRD | Core Data
MC01PRD | Decision Support
MC01PRD | DMT
MC01PRD | DSAudit
MC01PRD | EIS
MC01PRD | Explicit Roles
MC01PRD | FDB
MC01PRD | Gen Services
MC01PRD | HiTech
MC01PRD | Ilog
MC01PRD | Infoscan
MC01PRD | Lab Alerts
MC01PRD | LifeFlight
MC01PRD | Micro Biology
MC01PRD | My Health
MC01PRD | OPOC
MC01PRD | Patient Summary Service
MC01PRD | Physician Referral
MC01PRD | Problem Knowledge Base
MC01PRD | Quill
MC01PRD | RxInteroperability
MC01PRD | RxStar
MC01PRD | Rxstar Advisory
MC01PRD | RxStar Printing Service
MC01PRD | Sepsis
MC01PRD | Signature
MC01PRD | Star Transforms
MC01PRD | Team Member
MC01PRD | Terminology
MC01PRD | Voom
MC01PRD | Voom Reporting
MC01PRD | Vpnpp
MC01PRD | Vumc Notify
MC01PRD | Whiteboard/Triage
MC02PRD | Bi Interface
MC02PRD | Central Line
MC02PRD | DB2 Interface
MC02PRD | Enterprise Patient Index
MC02PRD | Gen Services
MC02PRD | GIE Interface
MC02PRD | ICD
MC02PRD | Opoc
MC02PRD | Order Set Analyzer
MC02PRD | Ormis Scheduling
MC02PRD | Patient History
MC02PRD | Physician Compliance
MC02PRD | Quality and Patient Safety
MC02PRD | Racf
MC02PRD | Star Factr Form
MC02PRD | Whiteboard Screen Shot
MC14PRD | Lexicon/Terminology (health lang/clinical terminology service)
MC25PRD | Tibco

## Silver
SILVER level applications will be shutdown during the change
HMM and HED/HEO will most likely have to be stopped as well pending verification from the support teams.
These are the databases that will be coming down due to the stopping of the Red Hat Cluster servers:
MC03PRD | Admitting ED-bereavement | MC apps
MC03PRD | Adult Primary Care | · Apex: apex.mc.vanderbilt.edu
MC03PRD | BAA | · Confluence: confluence.mc.vanderbilt.edu
MC03PRD | Charge Monitoring | · Confluence: mcit-confluence.mc.vanderbilt.edu
MC03PRD | Confluence
MC03PRD | Database Metrics | Health IT apps
MC03PRD | Disease Tracking System | Asm00
MC03PRD | DRC | o medrecon (MC10)
MC03PRD | E-Docs | o PTA (MC03)
MC03PRD | EIE | o stardocservice (MC22)
MC03PRD | Enterprise Software Solutions | Asm10
MC03PRD | Epic | o amanita (MC22)
MC03PRD | Fitness | o clinsysproviderlookup (MC22)
MC03PRD | Hed Suggestions | o DCP (MC22)
MC03PRD | Information Workflow | o icdservice (MC22)
MC03PRD | ISS | o auditservice (MC03)
MC03PRD | Max Fax | o labAlerts (MC09)
MC03PRD | MCIS | o coredata (MC13, AQ)
MC03PRD | Pager | o cardiopw (MC22)
MC03PRD | Patient Compass | o vios (MC22)
MC03PRD | Physician/Provider Time Away | Asm20
MC03PRD | RAC Audit | o HPCIS (MC03)
MC03PRD | RPTB | o webpager (MC03
MC03PRD | SAM | o voisservices (MC22)
MC03PRD | Survey | o central_appts (MC22)
MC03PRD | Unsigned Documents | o tpndash (MC22)
MC03PRD | Vanderbilt Patient Visit Notification | o GIElab (AQ)
MC03PRD | Vistar | o voom (AQ)
MC03PRD | WEB TIMESHEET | Jam
MC03PRD | Xplanner | o carenet (MC02, MC13)
MC05PRD | CERME | o carenetie (MC02, MC13)
MC05PRD | Utilization Mgmt | o vandyworks (MC09), plus mailer & scheduler
MC07PRD | DBA Confluence | o mirth (MC13)
MC08PRD | Home Care | OAS
MC09PRD | Workbrain | o alerts (MC09, AQ)
MC10PRD | RxStar | o tdqorders (AQ)
MC10PRD | Whiteboard Screen Shot | Tibco
MC10PRD | CME data | o patientpreferences (MC03)
MC11PRD | RemitMgmt (OnBase)
MC12PRD | Bone Marrow Transplant | Batch jobs
MC13PRD | CareNet | · Developers will have to help determine if any batch jobs need to be disabled that run on ORB03LP.
MC13PRD | CIN
MC15PRD | StemSoft (BMT replacement)
MC16PRD | Provation
MC17PRD | HUGS
MC18PRD | Oracle APEX (pharmacy)
MC19PRD | Proteus LIMS System
MC20PRD | Cancer Center
MC21PRD | Quality and Patient Safety
MC22PRD | Cardio Pathways
MC22PRD | Discharge Wizard
MC22PRD | PAML
MC22PRD | Predict
MC22PRD | VOIS
MC24PRD | Cancer Center
MC26PRD | TeraMedica
MC27PRD | Cancer Center
MC28PRD | Lexicon/Terminology
MC29PRD | DAR-Advance
MC30PRD | Coeus
MC31PRD | Trinisys/Convergence
MC33PRD | ALM
ADIPRD
ADMPRD
ADIPRD
ADMPRD
ARPRD
CCPRD
PTPROD
TPZPRD
BOOPRD
BOX4PRD
FLUPRD
VUPROD
FNPROD
FSPRD
PBUD
HRPROD
PIPROD
VU02PROD
VU03PRD
HYEPMPRD
HYFDMPRD
HYPLNPRD